## Sheet1
|  | ORIG | REV |  | UNIT | TOTAL | CONTRACT | COMPLETE | EARNINGS | QUANTITY | EARNINGS | THIS | THIS
ITEM | DESCRIPTION | QUANTITY | QTYS | UNIT | PRICE | AMOUNT | AMOUNT | TO DATE | TO DATE | TO DATE | TO DATE | PERIOD | PERIOD
1 | Mobilization | 1 |  | LS | 99000 | 99000 |  | 1 | 99000 | 1 | 99000 | 0 | 0 | 2e-10
2 | Field Engineering | 1 |  | LS | 15000 | 15000 |  | 1 | 14999.9999 | 1 | 14999.9999 | 0 | 0 | 5.95e-09
3 | Quality Control | 1 |  | LS | 25000 | 25000 |  | 1 | 25000 | 1 | 25000 | 0 | 0 | 0
4 | Work Zone Traffic Control | 1 |  | LS | 21600 | 21600 |  | 1 | 21600 | 1 | 21600 | 0 | 0 | 0
5 | Preconstruction Services | 1 |  | LS | 5000 | 5000 |  | 1 | 5000 | 1 | 5000 | 0 | 0 | 0
6 | Erosion Control | 1 |  | LS | 1500 | 1500
7 | Track Excavation in Agg. Base | 235 |  | CY | 20 | 4700
8 | Track Excavation in AC (6"-8" AC, Agg.) 10' Wide | 935 |  | SY | 8 | 7480 |  | 59.8 | 478.4 | 59.8 | 478.4 | 0 | 0 | 875.2
9 | Track Excavation in Concrete (9" PCC, 4" ATB, Agg.) 10' Wide | 165 |  | SY | 12 | 1980 |  | 1013 | 12156 | 1013 | 12156 | 0 | 0 | -848
10 | PCC Roadway Excavation (9" PCC) Outside Track Exc. | 165 |  | SY | 10 | 1650 |  | 309.69 | 3096.9 | 309.69 | 3096.9 | 0 | 0 | -144.69
11 | Remove Existing Curb and Gutter | 170 |  | LF | 6 | 1020
12 | 1.52mm PVC Geomembrane (3 meter x 2.5 meter) | 10 |  | EA | 150 | 1500 |  | 4 | 600 | 4 | 600 | 0 | 0 | 6
13 | 8" SDR 35 PVC Track Drain Leads | 70 |  | LF | 120 | 8400 |  | 150.3 | 18036 | 150.3 | 18036 | 0 | 0 | -80.3
14 | Construct Reinforced PCC Pavement (9" Thick) | 200 |  | SY | 100 | 20000
15 | Construct Curb and 18" - 24" Gutter | 170 |  | LF | 20 | 3400
16 | Asphalt Paving Special Staging | 1 |  | LS | 10500 | 10500
17 | Temporary Asphalt Paving | 35 |  | Ton | 150 | 5250
18 | Furnish Ri59 Head Hardened Girder Rail (HSHM) | 220.564 |  | Ton | 1678.29 | 370170.3556
19 | Haul and Unload Materials | 1 |  | LS | 16750 | 16750
20 | Pre-Bend Tangent Girder Rail | 1 |  | LS | 3000 | 3000
21 | Install Ri59 Paved Track - Tangent | 2200 |  | TF | 317 | 697400 |  | 46 | 14582 | 46 | 14582 | 0 | 0 | 2154
22 | Install Ri59 Paved Track - Curved | 60 |  | TF | 375 | 22500 |  | 664 | 249000.002 | 664 | 249000.002 | 0 | 0 | -604
23 | Furnish and Install Track Drain - Ri59 | 9 |  | EA | 2200 | 19800 |  | 19 | 41800 | 19 | 41800 | 0 | 0 | -10
| Subtotal |  |  |  |  | 1362600.3556 | 0 | 37.09% | 505349.3119 |  | 505349.3119 |  | 0
| CM/GC Fee (3.5%) |  |  |  |  | 47691.0124 |  |  | 17687.2359 |  | 17687.2359 |  | 0
| Total Construction Cost |  |  |  |  | 1410291.368