## Slide 1
Technology Oversight Committee
Quarterly Report
October – December 2018

## Slide 2
Project Name: Portland Online Permitting System (POPS)
Bureau: Bureau of Technology Services, Bureau of Development Services
Reporting Date: 17 December 2018
 | Initial Estimate at TOC Intake 10/10/2017 | Planned at Baseline | Current Revision 10/15/2018 | QA Assessment |  |  | TOC Assessment |  | 
Expected Completion | 9/30/2018 |  | TBD | Oct | Nov | Dec | Oct | Nov | Dec
Confidence Level | Medium |  | Medium | Yellow | Yellow | Yellow | Yellow | Yellow | Yellow
Budget | TBD |  | $11,997,231 | Yellow | Green | Green | Yellow | Yellow | Green
Confidence Level | TBD |  | Medium |  |  |  |  |  | 
Scope Stability Confidence Level | Medium |  | Medium | Yellow | Yellow | Yellow | Yellow | Yellow | Green

## Slide 3
 | Initial Estimate at TOC Intake 4/16/2018 | Planned at Baseline 8/21/2018 | Current Revision | QA Assessment |  |  | TOC Assessment |  | 
Expected Completion | 12/1/18 | 12/1/18 |  | Oct | Nov | Dec | Oct | Nov | Dec
Confidence Level | Medium | Medium |  | Yellow | Green | Green | Green | Green | Green
Budget | $1,080,000 | $869,530 |  | Yellow | Green | Green | Green | Green | Green
Confidence Level | TBD | Medium |  |  |  |  |  |  | 
Scope Stability Confidence Level | Medium | Medium |  | Yellow | Yellow | Green | Green | Green | Green
Project Name: BFM Implementation
Bureau: City Budget Office
Reporting Date: 17 December 2018