## Slide 1: Technology oversight committee
Quarterly Report
April – June 2019

## Slide 2: Project Name: Portland Online Permitting System (POPS) Bureau: Bureau of Technology Services, Bureau of Development Services Reporting Date: 24 June 2019
 | Initial Estimate at TOC Intake 10/10/2017 | Planned at Baseline | Current Revision 6/24/2019 | QA Assessment |  |  | TOC Assessment |  | 
Expected Completion | 9/30/2018 |  | 11/4/2019 | April | May | June | April | May | June
Confidence Level | Medium |  | High | Yellow | Yellow | Yellow | Yellow | Yellow | Yellow
Budget | TBD |  | $11,997,231 | Green | Yellow (cost) | Yellow (cost) | Green | Green | Green
Confidence Level | TBD |  | High |  | Green (budget) | Green (budget) |  |  | 
Scope Stability | Medium |  | High | Yellow | Yellow | Yellow | Green | Green | Green
Confidence Level |  |  |  |  |  |  |  |  | 

## Slide 3: Project Name: Portland Online Permitting System (POPS) Bureau: Bureau of Technology Services, Bureau of Development Services Reporting Date: 24 June 2019
 | Initial Estimate at TOC Intake 10/10/2017 | Planned at Baseline | Current Revision 6/18/2019 | QA Assessment |  |  | TOC Assessment |  | 
Expected Completion | 9/30/2018 |  | 9/1/2019 | April | May | June | April | May | June
Confidence Level | Medium |  | Medium | Not enough information available to rate. | Yellow | Yellow | Red | Red | Red
Budget | TBD |  | $347,750 | Not enough information available to rate. | Green | Yellow | Yellow | Green | Green
Confidence Level | TBD |  | High |  |  |  |  |  | 
Scope Stability | Medium |  | High | Not enough information available to rate. | Yellow | Green | Yellow | Green | Green
Confidence Level |  |  |  |  |  |  |  |  |