## Budget
CITY OF PORTLAND OPEN RESERVOIR STUDY
PHASE II BUDGET SUMMARY
|  | Project Manager | Principal Engineer | Project Engineer | Public Involvement | Permitting Specialist | Landscape Architect | Geotechnical Engineer | Storage Analysis | Site Security/ Equipment Specialist | Floating Cover Expert | Surveyor | Supervising Engineer | Professional Engineer/ Architect/ CADD | Administration | Word Processing | Total Labor Hours | Non-Labor | TOTAL COST
|  | Glicker | EES/Kreft | Mallon | Garner | Crockett | Murase | Cornforth | MSA |  | Neal/Way
|  | 150 | 165 | 115 | 99 | 135 | 120 | 120 | 125 | 175 | 100 | 100 | 90 | 75 | 55 | 55
ELEMENT I - DEVELOP INTERIM ACTION PLAN
| Task I.1 Project Initiation & Local Storage Volumes | 60 |  | 120 | 24 | [8 empty] | 20 |  | 4 | 228 | 2530 | 29400
| Task I.2 Site Security | 2 |  | 12 | [5 empty] | 80 | [7 empty] | 2400 | 18100
| Task I.3 Preliminary Evalulation and Recommendations | 20 | 40 | 60 |  |  |  | 400 |  | 40 | 80 |  | 60 | 60 | 12 | 24 | 796 | 22670 | 114100
| Task I.4 Reservoir Barrier and Park Amenities | 8 |  | 16 |  |  | 80 | [6 empty] | 40 |  |  | 144 | 1480 | 17100
| Task I.5 Public Involvement | 24 |  | 24 | 240 |  | 80 | [8 empty] | 16 | 384 | 1480 | 42100
| Task I.6 Mt. Tabor Park Improvements Prelim. Dsg | 8 | 40 | 60 |  |  | 40 | 40 | 80 | 40 | 80 | 80 | 160 | 120 | 12 | 40 | 800 | 7200 | 90800
| Task I.7 Permitting | 2 |  | 4 |  | 80 | [9 empty] | 4 | 90 | 1675 | 13500
| Sub-Total | 124 | 80 | 296 | 264 | 80 | 200 | 440 | 80 | 160 | 160 | 80 | 220 | 240 | 24 | 88 | 2442 |  | 325100
ELEMENT II - WASHINGTON PARK IMPROVEMENTS
| Task II.1 Preliminary Design | 4 | 40 | 80 | 24 |  | 48 | 20 |  |  | 40 | 40 | 60 | 80 |  | 16 | 452 | 2900 | 50100
| Task II.2 Detailed Design | 4 | 120 | 180 |  |  | 60 | 40 |  |  | 60 |  | 160 | 260 |  | 60 | 944 | 5930 | 102200
| Task II.3 Bid Phase Services | 4 | 24 | 24 | [10 empty] | 20 | 40 | 112 | 1160 | 11800
| Task II.4 Services During Construction |  | 40 | 120 | [6 empty] | 24 |  | 40 | 40 | 40 |  | 304 | 2480 | 34100
| Task II.5 Post-Construction Services |  | 24 | 60 | [6 empty] | 16 | [5 empty] | 100 | 1070 | 13500
| Task II.6 Land Use Permit Application |  | 8 | 12 |  | 48 | [7 empty] | 8 |  | 4 | 80 | 1040 | 11000
| Sub-Total | 12 | 256 | 476 | 24 | 48 | 108 | 60 | 0 | 0 | 140 | 40 | 260 | 388 | 60 | 120 | 1992 |  | 222700
ELEMENT III DEVELOP LONG TERM STORAGE PLAN
| Task III.1 Decision Process | 8 |  | 4 | 40 | [11 empty] | 52 | 590 | 6200
| Task III.2 Obtain Community Input | 16 |  |  | 120 | [11 empty] | 136 | 620 | 14900
| Task III.3 Public Outreach Materials |  |  | 8 | 40 | [10 empty] | 20 | 68 | 710 | 6700
| Task III.4 Input & Outreach Summary | 4 |  | 8 | 40 | [11 empty] | 52 | 590 | 6100
| Task III.5 RMP | 8 | 100 | 8 | [9 empty] | 160 |  | 40 | 316 | 2120 | 34900
| Task III.6 Storage Volumes and Evaluation Criteria | 4 |  | 32 |  |  |  |  | 8 |  |  |  |  | 24 |  |  | 68 | 1110 | 7200
| Task III.7 Identify Potential Reservoir Sites | 4 |  | 40 |  |  |  |  | 20 |  |  |  | 24 | 80 |  | 20 | 188 | 2010 | 16500
| Task III.8 Develop Conceptual Alternatives | 8 |  | 60 |  |  | 60 | 64 | 40 |  |  |  |  | 120 |  | 16 | 368 | 2430 | 35300
| Task III.9 Permitting | 4 |  | 4 |  | 40 | [9 empty] | 8 | 56 | 1020 | 7900
| Task III.10 Develop Design Concepts | 16 |  | 80 |  |  | 120 | 40 | [5 empty] | 140 |  |  | 396 | 2370 | 43700
| Task III.11 Prepare Storage and Implementation Plan | 16 |  | 80 | [9 empty] | 80 |  | 40 | 216 | 2220 | 22000
| Task III.12 Project Management | 40 |  | 120 | [10 empty] | 60 |  | 220 | 2250 | 25400
| Sub-Total | 128 | 100 | 444 | 240 | 40 | 180 | 104 | 68 | 0 | 0 | 0 | 24 | 604 | 60 | 144 | 2136 |  | 226800
| TOTAL HOURS | 252 | 180 | 740 | 504 | 120 | 380 | 544 | 148 | 160 | 160 | 80 | 244 | 844 | 84 | 232 | 4578 |  | 774600