## Sheet1
Fee Bookings
| HDR Portland |  | HDR Security
| 2002 | 2003 | 2002 | 2003
John H
John L
Bryan

## Sheet2
HDR Portland / Security Net Fee Split
Portland Vulnerability Assessment
| HDR |  |  | HDR Portland |  |  | HDR Security
| Labor | Expense | Total | Labor | Expense | Total | Labor | Expense | Total
2002 assured | 215911.1034 | 18777.2993 | 234688.4027 | 148222.0477 | 4694.3248 | 152916.3725 | 67689.0557 | 14082.9745 | 81772.0302
2002 with option | 279551.2627 | 25518.5745 | 305069.8372 | 188462.2714 | 6379.6436 | 194841.915 | 91088.9914 | 19138.9309 | 110227.9222
2003 assured | 41471.7408 | 3523.9429 | 44995.6837 | 23123.1024 | 880.9857 | 24004.0881 | 18348.6384 | 2642.9572 | 20991.5956
2003 with option | 105111.9001 | 10265.2181 | 115377.1182 | 63363.3261 | 2566.3045 | 65929.6306 | 41748.5741 | 7698.9135 | 49447.4876
Total assured | [5 empty] | 176920.4606 |  |  | 102763.6257
Total with options | [5 empty] | 260771.5455 |  |  | 159675.4098
Assuming Bosco takes 50% of Holroyd Fee
2002 assured | 215911.1034 | 18777.2993 | 234688.4027 | 120678.0477 | 4694.3248 | 125372.3725 | 95233.0557 | 14082.9745 | 109316.0302
2002 with option | 279551.2627 | 25518.5745 | 305069.8372 | 152778.2714 | 6379.6436 | 159157.915 | 126772.9914 | 19138.9309 | 145911.9222
2003 assured | 41471.7408 | 3523.9429 | 44995.6837 | 22419.1024 | 880.9857 | 23300.0881 | 19052.6384 | 2642.9572 | 21695.5956
2003 with option | 105111.9001 | 10265.2181 | 115377.1182 | 54519.3261 | 2566.3045 | 57085.6306 | 50592.5741 | 7698.9135 | 58291.4876
Total assured | [5 empty] | 148672.4606 |  |  | 131011.6257
Total with options | [5 empty] | 216243.5455 |  |  | 204203.4098

## Summary
Vulnerability Assessment and Related Security Planning
City of Portland
(revised 8/6/02)
| 3.2 | 138.432 | 131.2 | 200 | 176 | 92.32 | 114.048 | 126.4 | 176 | 169.6 | 164.992 | 70.912 | 63.68 | 91.2
|  | 43.26 | 41 | 62.5 | 55 | 28.85 | 35.64 | 39.5 | 55 | 53 | 51.56 | 22.16 | 19.9 | 28.5
|  | Lang | Bosco | Fitzgerald | Holroyd | Anderson | Black | Furne | Woolcott | Beehler | Ballantyne | Kuhns | Merrill | Harrison |  | 8%
|  | Labor Resources | [12 empty] | HDR |  |  | Westin |  |  | EQE
Task No. | Task Description | Project Principal | QA/QC | Proj Manager | Sec Proj. Manager | Security Prof. | Envirn Engineer RAM-W | Proj. Engineer RAM-D | Industrial Health | Westin SCADA & Cyber Sec. | EQE Natural Disaster | CADD | Word Process. | Proj. Cntrlr | Labor Total | Direct Expense | Task Subtotal | Labor Total | Subcontrctr Markup | Task Subtotal | Labor Total | Subcontrctr Markup | Task Subtotal | Task Total | Hour split
PHASE 1
100 | Security Planning Team and Background Information | [23 empty] | HDR | Westin | EQE | Total
110 | Establish Security Planning Team | 2 | 2 | 8 | 3 | 0 | 6 | 8 | 0 | 0 | 0 | 0 | 2 | 8 | 5219.712 | 417.577 | 5637.289 | 0 | 0 | 0 | 0 | 0 | 0 | 5637.289 | 29 | 0 | 0 | 29
120 | Collect and Review Background Information | 2 | 2 | 6 | 24 | 0 | 15 | 12 | 8 | 12 | 4 | 0 | 3 | 6 | 11198.0612 | 895.8449 | 12093.9061 | 2139.4221 | 171.1538 | 2310.5759 | 694.7087 | 55.5767 | 750.2854 | 15154.7674 | 69 | 12 | 4 | 85
130 | Determine and Rank Water Utility Mission Objectives | 2 | 2 | 12 | 2 | 0 | 35 | 24 | 0 | 20 | 8 | 0 | 20 | 8 | 11785.5573 | 942.8446 | 12728.4019 | 3773.5619 | 301.885 | 4075.4469 | 1472.5608 | 117.8049 | 1590.3656 | 18394.2144 | 77 | 20 | 8 | 105
140 | Perform Threat Analysis | 2 | 2 | 8 | 20 | 0 | 24 | 20 | 0 | 6 | 0 | 0 | 20 | 6 | 12611.9867 | 1008.9589 | 13620.9457 | 1150.8293 | 92.0663 | 1242.8956 | 0 | 0 | 0 | 14863.8413 | 76 | 6 | 0 | 82
150 | Contaminant Monitoring | 2 | 3 | 2 | 0 | 0 | 24 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 3807.616 | 304.6093 | 4112.2253 | 678.4 | 54.272 | 732.672 | 0 | 0 | 0 | 4844.8973 | 31 | 4 | 0 | 35
| Task Subtotal | 10 | 11 | 36 | 49 | 0 | 104 | 64 | 8 | 42 | 12 | 0 | 45 | 28 | 44622.9332 | 3569.8347 | 48192.7679 | 7742.2133 | 619.3771 | 8361.5904 | 2167.2695 | 173.3816 | 2340.651 | 58895.0093
200 | Site Characterization
210 | Site Characterization | 2 | 2 | 16 | 16 | 0 | 35 | 40 | 0 | 32 | 32 | 40 | 20 | 8 | 19846.3226 | 1587.7058 | 21434.0284 | 5725.3507 | 458.0281 | 6183.3788 | 5577.8947 | 337.2316 | 5915.1263 | 33532.5334 | 151 | 32 | 32 | 215
220 | Site Assessment Workshop | 2 | 3 | 12 | 16 | 12 | 8 | 8 | 0 | 12 | 0 | 0 | 12 | 8 | 10166.0984 | 813.2879 | 10979.3863 | 2280.7496 | 182.46 | 2463.2096 | 0 | 0 | 0 | 13442.5958 | 61 | 12 | 0 | 73
230 | On-Site Physical Assessment | 2 | 3 | 16 | 72 | 88 | 66 | 32 | 0 | 48 | 0 | 0 | 16 | 6 | 37574.7887 | 2995.9831 | 40570.7718 | 8370.6833 | 669.6547 | 9040.338 | 0 | 0 | 0 | 49611.1098 | 279 | 48 | 0 | 327
240 | Risk Analysis | 2 | 3 | 16 | 8 | 50 | 56 | 40 | 0 | 16 | 40 | 0 | 24 | 8 | 23047.6975 | 1843.8158 | 24891.5133 | 2869.9927 | 229.5994 | 3099.5921 | 6990.6618 | 559.2529 | 7549.9148 | 35541.0202 | 175 | 16 | 40 | 231
250 | Evaluate Upgrades to Existing Protection Systems | 2 | 3 | 16 | 6 | 40 | 16 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 10444.032 | 835.5226 | 11279.5546 | 1356.8 | 108.544 | 1465.344 | 0 | 0 | 0 | 12744.8986 | 83 | 8 | 0 | 91
| Task Subtotal | 10 | 14 | 76 | 118 | 190 | 181 | 120 | 0 | 116 | 72 | 40 | 72 | 30 | 101078.9392 | 8076.3151 | 109155.2543 | 20603.5763 | 1648.2861 | 22251.8624 | 12568.5565 | 896.4845 | 13465.041 | 144872.1578
300 | Final Report
310 | Preliminary Report | 2 | 4 | 12 | 90 | 0 | 40 | 32 | 0 | 32 | 16 | 8 | 96 | 8 | 33666.7878 | 2693.343 | 36360.1308 | 6355.0481 | 508.4039 | 6863.452 | 3103.7961 | 248.3037 | 3352.0998 | 46575.6826 | 188 | 32 | 16 | 236
320 | Final Report and Implementation Plan | 2 | 3 | 13 | 24 | 0 | 20 | 18 | 0 | 20 | 8 | 0 | 24 | 8 | 13723.1573 | 1097.8526 | 14821.0099 | 3810.1333 | 304.8107 | 4114.944 | 1487.1893 | 118.9751 | 1606.1645 | 20542.1184 | 80 | 20 | 8 | 108
| Task Subtotal | 4 | 7 | 25 | 114 | 0 | 60 | 50 | 0 | 52 | 24 | 8 | 120 | 16 | 47389.9451 | 3791.1956 | 51181.1407 | 10165.1815 | 813.2145 | 10978.396 | 4590.9854 | 367.2788 | 4958.2642 | 67117.801
| Basic Services PHASE 1 Subtotal | 24 | 32 | 137 | 281 | 190 | 345 | 234 | 8 | 210 | 108 | 48 | 237 | 74 | 193091.8175 | 15437.3454 | 208529.1629 | 38510.9711 | 3080.8777 | 41591.8488 | 19326.8114 | 1437.1449 | 20763.9563 | 270884.968
PHASE 2
400 | Operating Procedures and Policies
410 | Emergency Response Procedures | [23 empty] | 0 | 0 | 0 | 0
420 | Security Procedures Outline | [23 empty] | 0 | 0 | 0 | 0
430 | Draft Operational Procedures | [23 empty] | 0 | 0 | 0 | 0
440 | Final Draft Operational Procedures | [23 empty] | 0 | 0 | 0 | 0
PHASE 2 Subtotal
500 | Phase 1 New Tasks - Subcntrcts/ Mtgs
510 | Tech Support - Crane and Merseth (WBE) | [22 empty] | 10800 |  |  |  |  | 9.051%
520 | Tech Support - Vigil-Agrimis Inc. (MBE) | [22 empty] | 7560 |  |  |  |  | 6.336%
530 | Monthly Progress Meetings (8) |  |  |  | 32 |  | 32 | [5 empty] | 32 |  | 11319.296 | 905.5437 | 12224.8397 | 0 | 0 | 0 | 0 | 0 | 0 | 12224.8397 | 64 | 0 | 0 | 64
540 | Project Review Meetings (4) | 6 | 36 | 8 | 12 |  | 8 |  |  | 16 | 10 | 12 |  |  | 11029.12 | 2382.3296 | 13411.4496 | 2713.6 | 217.088 | 2930.688 | 1649.92 | 131.9936 | 1781.9136 | 18124.0512 | 82 | 16 | 10 | 108
550 | Additional Conceptual Security Planning | 2 | 4 | 24 | 32 |  | 32 |  |  | 24 |  |  | 16 | 8 | 16631.68 | 1330.5344 | 17962.2144 | 4070.4 | 325.632 | 4396.032 |  |  |  | 22358.2464 | 94 | 24 | 0 | 118
560 | Additional Cyber Assessment Effort | [16 empty] | 33110 | 2648.8 | 35758.8 |  |  |  | 35758.8
570 | Additional RAM-D Assesssment | [6 empty] | 12500 | [15 empty] | 12500
| Task Subtotal | 8 | 40 | 32 | 76 | 0 | 72 | 0 | 0 | 40 | 10 | 12 | 48 | 8 | 38980.096 | 4618.4077 | 43598.5037 | 39894 | 3191.52 | 43085.52 | 1649.92 | 131.9936 | 1781.9136 | 119325.9373
| PROJECT TOTALS | 8 | 40 | 32 | 76 | 0 | 72 | 0 | 0 | 40 | 10 | 12 | 48 | 8 | 38980.096 | 4618.4077 | 43598.5037 | 39894 | 3191.52 | 43085.52 | 1649.92 | 131.9936 | 1781.9136 | 119325.9373
| PHASE 1 Subtotal | [22 empty] | 390210.9053
PHASE 1A
600 | Security Planning Team and Background Information | [23 empty] | HDR | Westin | EQE | Total
610 | Establish Security Planning Team | [23 empty] | 0 | 0 | 0 | 0
620 | Collect and Review Background Information | [23 empty] | 0 | 0 | 0 | 0
630 | Determine and Rank Water Utility Mission Objectives | [23 empty] | 0 | 0 | 0 | 0
640 | Perform Threat Analysis | [23 empty] | 0 | 0 | 0 | 0
Task Subtotal
700 | Site Characterization
710 | Site Characterization | [23 empty] | 0 | 0 | 0 | 0
720 | Site Assessment Workshop | [23 empty] | 0 | 0 | 0 | 0
730 | On-Site Physical Assessment | [23 empty] | 0 | 0 | 0 | 0
740 | Risk Analysis | [23 empty] | 0 | 0 | 0 | 0
Task Subtotal
800 | Final Report
810 | Preliminary Report | [23 empty] | 0 | 0 | 0 | 0
820 | Final Report and Implementation Plan | [23 empty] | 0 | 0 | 0 | 0
Task Subtotal
| PHASE 1A Subtotal | [22 empty] | 75000
0%
0%
[25 empty] | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0
| PROJECT TOTALS PHASE 1 and 1A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465210.9053 | 1539 | 250 | 118 | 1907
|  |  | 0.5 | [11 empty] | HDR |  |  | HDR Portland |  |  | HDR Security
[15 empty] | Labor | Expense | Total | [6 empty] | HDR Port lab | HDR Port Exp
| 2002 assured | 4429.824 | 40862.4 | 33800 | 31416 | 17540.8 | 47558.016 | 29577.6 | 1408 |  |  | 4254.72 | 14646.567 | 6035.2688 | 231529.1958 | 20055.7531 | 251584.9488 | 126857.7179 | 5013.9383 | 131871.6562 | 104671.4779 | 15041.8148 | 119713.2927 | 0.5 | 0.25
0.5 | 2002 with option | 4429.824 | 40862.4 | 33800 | 31416 | 17540.8 | 47558.016 | 29577.6 | 1408 |  |  | 4254.72 | 14646.567 | 6035.2688 | 231529.1958 | 20055.7531 | 251584.9488 | 126857.7179 | 5013.9383 | 131871.6562 | 104671.4779 | 15041.8148 | 119713.2927
| 2003 assured | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2003 with option | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62832
62832
0
0