## Final Estimate
CITY OF PORTLAND, OREGON
BUREAU OF TRANSPORTATION ENGINEERING AND DEVELOPMENT
Construction
Copenhagen Utilities & Construction Inc.
|  | Base Contract | 2483242
|  | Changes in Quantities | 210865.25
|  | Change Orders | 458746.79
3152854.04
Construction Claim
|  | Partial Payment | 230056.54
|  | Final Payment | 227980.18
|  | Construction Claim |  | 458036.72
| Construction Total |  |  |  | 3610890.76
Engineering
Design Engineering
|  | Street | 64719.16
|  | Stormwater | 117861.82
182580.98
Construction Engineering
|  | Street | 225365.88
|  | Stormwater | 10223.7
235589.58
Credits
|  | Water Bureau | -17409.07
|  | Portland Office of Transportation | -45.08
-17454.15
| Engineering Total |  |  |  | 400716.41
Project Management |  |  |  |  | 62624.69
SUBTOTAL INCURRED COSTS |  |  |  |  | 4074231.86
Auditor's Costs
| Advertising |  |  | 130.5
| LID Construction Fund - Progress Payment Interest through 9/18/02 |  |  | 1012626.37
| LID Construction Fund - Interest Credit |  |  | -10144.57
| LID Construction Fund - Superintendence |  |  | 22236.58
1024848.88
Project Management
| Project Closeout |  |  | 1877.1973
| Advertising for Final Assessment Ordinance |  |  | 125
2002.1973
Overhead
| Administrative overhead on project management and engineering @ 23.36% |  |  |  | 108704.1943
SUBTOTAL PENDING COSTS |  |  |  |  | 1135555.2716
TOTAL PROJECT COSTS |  |  |  |  | 5209787.1316
Property Owner Share
| Nauru payment prior to LID formation |  |  |  | 27520
| Estimated assessment at LID formation |  | 3194644.6
| Increase (decrease) from estimated to final assessment |  | 1776079.15
| Total property owner billing |  |  | 4970723.75
| Payment from escrow due upon final assessment |  |  |  | 2949483.84
| Total Local Improvement District billing |  |  |  | 2021239.91
Other Funding
| Slide Repair |  |  | 38172.38
| Project Closeout |  |  | 64626.8873
| Other Credit |  |  | 39.92
| Absorption of Overhead |  |  | 108704.1943
| Portland Office of Transportation |  |  |  | 211543.3816
TOTAL PROJECT FUNDING |  |  |  |  | 5209787.1316
STATEMENT of the various kinds of work performed in the improvement of 4
APPROVED: ______________________________ ___________________ CONTRACTOR Date ______________________________ ___________________ PUBLIC WORKS REP. Date
I, VICTOR F. RHODES, P.E., City Engineer of said City, hereby certify that the above statement and map, show in detail the correct amounts of all work required to complete the improvement under the above named Ordinance. Dated: Approved: ___________________________ Approved: ____________________________ Principal Engineer City Engineer
FINAL ESTIMATE of the various kinds of work performed in the improvement of: NW Thompson Road from 600 Feet West of NW Pinnacle Drive to City Limits