## Project Costs
River Access and Transportation Phase I | [5 empty] | Page: | 1
Summary of Project Costs - Quarterly Report | [5 empty] | Date: | 2026-07-29 03:07 |  |  |  |  | Bid No. | 98222
Shaded items are estimated costs.
Summary of Project Cost - Construction
Description |  | 90% Estimate |  | Budget |  | Actual
|  | Costs | Totals | Costs | Totals | Costs | Totals
Bid Tab
| General - Schedule A |  |  | 880845 |  | 907538.01
| Westbank - Schedule B | 71000 |  | 51980 |  | 55017.72
| Steel Bridge - Schedule C | 2123000 |  | 2424986 |  | 2449830.06
| Eastbank - Schedule D | 2087000 |  | 2792470 |  | 2736382.49
| Hinged Light Poles - Schedule F | 2087000 |  | 12000 |  | 12000
| Change Orders | 2087000 |  | 0 |  | 408146.2575
| Owner Furnished Items ($1,098.35, $3,850, $1697.71) | 2087000 |  | 0 |  | 6628.06
| Future Potential Change Orders (UPRR Flagging) |  |  | 0 |  | 38500
| UPRR Protective Service | 100000 |  | 100000 |  | 100000
| Total (Includes a 8% contingency) | 851360 | 11493360 |  | 6262281 |  | 6714042.5975
Current Additional Items
| Haul Road | 4500 |  | 4500 |  | 4500
| Power Center (Put on hold, included with HNTB Est.) | 0 |  | 0 |  | 0
| CL-8 Fence | 7200 |  | 7200 |  | 7200
| Freeway Protective Fence (PDC Defaulted on IGA Work. Delete $12,000 payment to PDC) | 12000 |  | 12000 |  | 0
| Power Poles | 4500 |  | 4500 |  | 4500
| 3-Phase Overhead Wire | 900 |  | 900 |  | 900
| Total (0% contingency) | 0 | 29100 | 0 | 29100 | 0 | 17100
Future Additional Items
| Relocate MCI Line (2 MH at $3,000 400 LF of Conduit at $15) | 12000 |  | 0 |  | 0
| Drinking Fountain ( 5K, Include with MPU) | 0 |  | 0 |  | 0
| Telephone ($750 include with MPU) | 0 |  | 0 |  | 0
| Fire Hydrant (5K, include with MPU) | 0 |  | 0 |  | 0
| Automatic Gates on Lift Span | 70000 |  | 0 |  | 0
| Cameras on Lower Deck (Transferred $26 K of work to F. E. Ward) | 118200 |  | 26900 |  | 0
| CCTV Control Center, cameras, FCC License ($8,567+ $10,690.07) | 50500 |  | 18000 |  | 19257.07
| CCTV Spare Equipment (Carried in-stock) | 14600 |  | 8600 |  | 0
| CCTV Event Recorder |  |  | 0 |  | 18777
| FCC Frequency Coordinator Fee ($150, included above) |  |  | 0 |  | 0
| FCC License Application Prep Fee (WNS $1,800 included above) |  |  | 0 |  | 0
| Overlook Fence (112 LF at $125, installation price included above) | 14000 |  | 0 |  | 0
| Sloped PAVERS (350' x 10') ($9 per SF) | 31500 |  | 0 |  | 0
| Lifting Guide Fix (16 x $3,125) See narrative | 50000 |  | 0 |  | 0
| Lead Paint Removal Adder | 0 |  | 0 |  | 0
| Additional Fences (50LF at RT wall, 20 lf at abutment at $18 per LF) | 1260 |  | 0 |  | 0
| Emergency Access to Lift Span Walkway | 4000 |  | 0 |  | 0
| Re-align Track Crossing | 1000 |  | 0 |  | 0
| Interpretive Signs (Add to PDC work) | 6000 |  | 6000 |  | 0
| Supplemental Spare Parts |  |  | 0 |  | 9574.44
| LID Plaque | 6000 |  | 0 |  | 1315
| PDOT LID Payment |  |  | 135746.53 |  | 135746.53
| LID Assessment Fees |  |  | 6847.99 |  | 6847.99
| Grand Opening Ribbon |  |  | 0 |  | 5650
| First year landscape and irrigation maintenance |  |  | 0 |  | 10000
| Second year landscape and irrigation maintenance |  |  | 0 |  | 10000
| Add three Inlets on east side of retaining wall | 3000 |  | 0 |  | 0
| DEQ Small Quantity Generator Status Fee |  |  | 0 |  | 300
| Pacific Power - Underground Electrical Service | 3000 |  | 0 |  | 13272 |  | Match Check
| Pacific Power Credit for Salvaged Power Poles |  |  | 0 |  | 0 |  | 6961882.6275
| Total (CCTV contingency) | 16140.8 | 401200.8 | 10750 | 212844.52 | 0 | 230740.03
Total Construction w/o future change orders
Total |  |  | 11923660.8 |  | 6504225.52 |  | 6961882.6275 | 419157.1075
Net Change | [5 empty] | 7.036% | 457657.1075
River Access and Transportation Phase I | [5 empty] | Page: | 2
Summary of Project Costs - Quarterly Report | [5 empty] | Date: | 2026-07-29 03:07
Summary of Project Cost - UPRR
Description |  | 90% Estimate |  | Budget |  | Actual
|  | Costs | Totals | Costs | Totals | Costs | Totals
Signal Relocation
| Signal Adjacent to the Steel Bridge | 4500 |  | 5000 |  | 5000
| Signal Near Oak Street along Haul Road | 0 |  | 3300 |  | 3300
| Flange Oiler near Steel Bridge | 0 |  | 0 |  | 1000
| Signal on the Steel Bridge (VE to $50K) See narrative | 300000 |  | 0 |  | 0
| Total | 32500 | 337000 | 0 | 8300 | 0 | 9300
Property Purchase
| Appraisal | 5000 |  | 0 |  | 0
| Property (Was $1,100,000) | 65000 |  | 650000 |  | 307012
| Closing Fees | 5000 |  | 5000 |  | 5000
| Total (15% contingency) | 11250 | 86250 | 0 | 655000 | 0 | 312012
Attorney Fees
| Operation and Maintenance Agreement | 15000 |  | 15000 |  | 15000
| Construction Agreement | 10000 |  | 0 |  | 0
| Total (15% contingency) | 3750 | 28750 | 0 | 15000 | 0 | 15000
UPRR Agreements
| Construction Agreement | 5000 |  | 0 |  | 0
| Lease and Operating (Annual Fee of $44,200) | 5000 |  | 0 |  | 342988
| Beautification Lease | 5000 |  | 0 |  | 22500
| Supplemental to the Wire Line Crossing | 65000 |  | 0 |  | 500
| Drainage Facility and Waterway | 65000 |  | 0 |  | 4800
| Permit Fee | 65000 |  | 0 |  | 3055
| Permit Fee | 65000 |  | 0 |  | 3055
| Pipeline Crossing | 5000 |  | 0 |  | 4200
| Total (15% contingency) | 42000 | 322000 | 0 | 0 | 0 | 381098
UPRR Staff
| Staff Time | 50000 |  | 25000 |  | 0
| Contract Administration (Consultant fee for shop drawing review) | 50000 |  | 0 |  | 0
| Total (15% contingency) | 15000 | 115000 | 3750 | 28750 | 0 | 0
Math Check
Total |  |  | 889000 |  | 707050 |  | 717410 | 717410
Net Change | [5 empty] | 1.465% | 10360
River Access and Transportation Phase I | [5 empty] | Page: | 3
Summary of Project Costs - Quarterly Report | [5 empty] | Date: | 2026-07-29 03:07
Summary of Project Cost - Design Engineering
Description |  | 90% Estimate |  | Budget |  | Actual
|  | Costs | Totals | Costs | Totals | Costs | Totals
HNTB
| Original Contract | 564900 |  | 564900 |  | 564900
| Amendment No. 1 | 38850 |  | 38850 |  | 38850
| Amendment No. 2 | 136000 |  | 136000 |  | 136000
| Amendment No. 3 | 0 |  | 0 |  | 0
| Amendment No. 4, See narrative | 278000 |  | 220000 |  | 220000
| Total (0% contingency) | 0 | 1017750 | 0 | 959750 | 0 | 959750
Fishman
| Facilitate Permit Acquisition | 1300 |  | 940 |  | 940
| Total (0% contingency) | 0 | 1300 | 0 | 940 | 0 | 940
Lloyd Lindley
| Plan-in-hand slide show | 2750 |  | 2750 |  | 2750
| Presentation Drawing Boards | 0 |  | 2250 |  | 2245.67
| Total (0% contingency) | 0 | 2750 | 0 | 5000 | 0 | 4995.67
ODOT
| Contract Administration | 75000 |  | 25000 |  | 0
| HAER Large Format Historic Photographs | 2000 |  | 0 |  | 0
| Total (8% contingency) | 6160 | 83160 | 0 | 25000 | 0 | 0
City Staff Costs - Design
| Project No. 00992 - Design | 39267 |  | 61934.06 |  | 120440.91
| Project No. 03011 - Match |  |  | 0 |  | 0
| Project No. 03383 - Grant | 25789 |  | 158194 |  | 92099.44
| Project No. 03547 - Construction |  |  |  |  | 49.41
| Parks and Recreation |  |  |  |  | 1516.76
| Total (0% contingency) | 0 | 65056 | 0 | 220128.06 | 0 | 214106.52
Other City Incurred Miscellaneous Costs
| Misc. Other Costs for 00992 Steel Bridge Design |  |  | 0 |  | -1145.47
| Misc. Other Costs for 03383 River Access Grant |  |  | 0 |  | 15480.34
1500
| Total (8% contingency) | #REF! | #REF! |  | 0 | 0 | 14334.87
Permits
| Right of Entry Agreement | 250 |  | 250 |  | 250
| DSL Easement Fee | 5000 |  | 0 |  | 0
| Staging Yard Lease Agreement | 250 |  | 250 |  | 0
| Total (0% contingency) | 0 | 5500 | 0 | 500 | 0 | 250
Larkin
| Facilitate Permit Acquisition | 18000 |  | 19125 |  | 19125
| Total (0% contingency) | 0 | 18000 | 0 | 19125 | 0 | 19125
Other
| Facilitate Public Involvement for Coast Guard Permit | 10000 |  | 17500 |  | 17500
| F. E. Ward (Manner-Method, Accelerated Contract Cost Analysis) | 0 |  | 5360 |  | 5360
| Total (15% contingency) | 1500 | 11500 | 0 | 22860 | 0 | 22860
DEA
| Value Engineering | 18000 |  | 18000 |  | 18000
| Total (0% contingency) | 0 | 18000 | 0 | 18000 | 0 | 18000
Match Check
Total |  |  | #REF! |  | 1271303.06 |  | 1254362.06 | 1254362.06
Net Change | [5 empty] | -1.333% | -16941
River Access and Transportation Phase I | [5 empty] | Page: | 4
Summary of Project Costs - Quarterly Report | [5 empty] | Date: | 2026-07-29 03:07
Summary of Project Cost - Construction Engineering
Description |  | 90% Estimate |  | Budget |  | Actual
|  | Costs | Totals | Costs | Totals | Costs | Totals
HNTB
| Construction Support | 208800 |  | 356334.71 |  | 338017
| Additional Design Services | 72000 |  | 23550 |  | 24227
| Pre-award Services | 27000 |  |  |  | 31470 |  | Net Add
| Amendment No. 1 |  |  |  |  | 85000 |  | 48425.74
| Unused funds |  |  |  |  | -36574.26 |  | 14.33%
| Total |  | 307800 |  | 379884.71 |  | 442139.74
City Staff and Miscellaneous Other Costs
| Office Space and Other Miscellaneous Costs | 14500 |  | 10655 |  | 22513.35
| Phones | 2800 |  | 2425 |  | 0
| Testing (Moved to Construction Contract Costs) | 10000 |  | 0 |  | 0
| Field Office Drafting Station and Software | 0 |  | 5730 |  | 687.5
| Miscellaneous other costs |  |  | 0 |  | 14211.85
| Project No. 00992 - Design |  |  |  |  | 14262.9
| Project No. 03011 - Match |  |  |  |  | 46.53
| Project No. 03383 - Grant |  |  |  |  | 57233.23
| Project No. 03547 - Construction | 320500 |  | 379650 |  | 287707.44
| City Staff (06/30/2001 to 11/01/2001) | 320500 |  | 0 |  | 43019
| Total (Contingency 4.54%) |  | 668300 | 19171.3 | 417631.3 |  | 439681.8
City (Other)
| Park's (8 hours x $45 x 30 days) | 10800 |  | 10800 |  | 2223.81
| BES (8 hours x $45 x 10 days) | 5400 |  | 3600 |  | 0
| Total (Contingency 5%) |  | 16200 | 720 | 15120 |  | 2223.81
Partnering
| Facilitator | 0 |  | 9000 |  | 2800
| Room Rental/Food | 0 |  | 1000 |  | 933.94
| Total (Contingency 5%) | 0 | 0 | 500 | 10500 |  | 3733.94
ODOT
| Engineering | 18000 |  | 0 |  | 0
| HARE Pictures |  |  | 0 |  | 0
| Testing | 1000 |  | 0 |  | 0
| Total |  | 19000 |  | 0 |  | 0
Match Check
Total (5% contingency) |  | 50565 | 1061865 | -22.48% | 823136.01 |  | 887779.29 | 887779.29
Net Change | [5 empty] | 7.853% | 64643.28
River Access and Transportation Phase I | [5 empty] | Page: | 5
Summary of Project Costs - Quarterly Report | [5 empty] | Date: | 2026-07-29 03:07
Summary of Project Cost
Description |  | 90% Estimate |  | Budget |  | Actual
|  | Percentage | Totals |  | Totals | Percent Change | Totals |  |  | 2nd Low Bid | 6613539.85
[10 empty] | FE Ward Bid | 6162281
Construction
| Construction |  | 11923660.8 |  | 6504225.52 | 7.036% | 6961882.6275 | 457657.1075 |  | Left on table | 451258.85
| UPRR Construction Costs |  | 889000 |  | 707050 | 1.465% | 717410 | 10360 |  | Total Const Increase | 468017.1075
Total Construction |  |  | 12812660.8 |  | 7211275.52 | 6.49% | 7679292.6275 | 468017.1075 |  | Amount saved | -16758.2575
Engineering
| Design Engineering | #REF! | #REF! |  | 1271303.06 | 16.33% | 1254362.06 | -16941
| Construction Engineering | 8.288% | 1061865 |  | 823136.01 | 11.56% | 887779.29 | 64643.28
Total Engineering |  |  | #REF! |  | 2094439.07 |  | 2142141.35 | 47702.28 | Match Check
Grand total |  |  | #REF! |  | 9305714.59 |  | 9821433.9775 | 515719.3875 | 9821433.9775
Net Change | [5 empty] | 5.542% | 515719.3875
Summary of Project Financial Requirements Versus Revenue
Description |  | 90% Estimate |  | Budget |  | Actual
|  | Costs | Totals | Costs | Totals | Costs | Totals
Financial Requirements
| Project Development |  | 1392300 |  | 1271303.06 |  | 1254362.06
| HNTB | 1017750 |  | 959750 |  | 959750
| Other Consultants | 51550 |  | 65925 |  | 65920.67
| ODOT | 83000 |  | 25000 |  | 0
| City Staff | 232000 |  | 220128.06 |  | 228441.39
| Permits | 8000 |  | 500 |  | 250
| Construction |  | 5152000 |  | 6504225.52 |  | 6961882.6275
| UPRR |  | 567000 |  | 707050 |  | 717410
| Construction Management |  | 742000 |  | 823136.01 |  | 887779.29
| HNTB | 323000 |  | 379884.71 |  | 442139.74
| City Staff | 399000 |  | 432751.3 |  | 441905.61
| Partnering | 0 |  | 10500 |  | 3733.94
| ODOT | 20000 |  | 0 |  | 0
Total Requirements |  |  | 7853300 |  | 9305714.59 |  | 9821433.9775
Financial Resources
| CMAQ Grant |  | 1585000 |  | 953000 |  | 953000
| PDOT (Trust & GTR) |  | 780000 |  | 780000 |  | 780000
| LGIP Deposit to date | 130000 |  | 130000 |  | 130000
| Estimated Trust $ available | 650000 |  | 650000 |  | 650000
| PDC (includes CMAQ swap) |  | 1136000 |  | 3936000 |  | 3936000
| ODOT |  | 500000 |  | 500000 |  | 500000
| LID |  | 1500000 |  | 1500000 |  | 1500000
| Loan for Property Purchase |  | 0 |  | 650000 |  | 650000
| Additional Funds from PDC |  |  |  | 1000000 |  | 1000000
| Additional Funds from PDOT |  |  |  | 420000 |  | 420000
| Additional Funds to cover lift span gate issue |  |  |  | 0 |  | 0
| Additional Funds from HNTB (CO 68) |  |  |  | 0 |  | 53682.24
| Additional Funds from HNTB (CO 73) |  |  |  | 0 |  | 24077
| Additional Funds from Street Lighting (CO 59) | [5 empty] | 4674.74
Total Resources |  |  | 5501000 |  | 9739000 |  | 9821433.98
Total (Negative = shortfall, Positive = Contingency) |  |  | -2352300 |  | 433285.41 | 5.668e-07% | 0.0024557
|  |  |  | Expended | Original |  | Remaining
Total Contingency |  |  |  | 433285.4075 | 433285.41 |  | 0.0024557
Percentage in relation to total budget |  |  |  |  | 4.656% |  | 2.5e-08%
Percentage in relation to total construction cost of $6,162,281 |  |  |  |  | 7.031% |  | 3.985e-08%
[5 empty] | Original Anticipated Contingency |  | 614791
[5 empty] | Actual Contingency |  | 433285.41
[5 empty] | Net Loss in contingency |  | 181505.59
[5 empty] | Net % loss in contingency |  | 29.52%
Summary of Project Cost - Contingencies
Description |  | 90% Estimate |  | Budget |  | Actual
|  | Costs | Totals | Costs | Totals | Costs | Totals
Construction
| Bid Tab | 851360 |  | 233000 |  | 233000
| Current Additional Items | 0 |  | 0 |  | 0
| Future Additional Items | 16140.8 |  | 10750 |  | 10750
| Cameras on Lower Deck (Transferred $26 K of work to F. E. Ward) | 18185.38 |  | 0 |  | 0
| CCTV Control Center, cameras, FCC License ($8,567+ $10,690.07) | 7773.14 |  | 0 |  | 0
| CCTV Spare Equipment (Carried in-stock) | 2174.08 |  | 0 |  | 0
| Total | #VALUE! | 895633.4 |  | 243750 |  | 243750
UPRR
| Signal Relocation | 32500 |  | 0 |  | 0
| Property Purchase | 11250 |  | 0 |  | 0
| Attorney Fees | 3750 |  | 0 |  | 0
| UPRR Staff | 15000 |  | 3750 |  | 3750
| Total | #VALUE! | 62500 |  | 3750 |  | 3750
Design Engineering
| HNTB | 0 |  | 0 |  | 0
| Fishman | 0 |  | 0 |  | 0
| Lloyd Lindley | 0 |  | 0 |  | 0
| ODOT | 6160 |  | 0 |  | 0
| City Staff Costs - Design | 0 |  | 0 |  | 0
| Other City Incurred Miscellaneous Costs | #REF! |  | 0 |  | 0
| Permits | 0 |  | 0 |  | 0
| Larkin | 0 |  | 0 |  | 0
| Other | 1500 |  | 0 |  | 0
| DEA | 0 |  | 0 |  | 0
| Total | #REF! | #REF! |  | 0 |  | 0
Construction Engineering
| HNTB | 15390 |  | 0 |  | 0
| City Staff and Miscellaneous Other Costs | 33415 |  | 19171.3 |  | 19171.3
| City (Other) | 810 |  | 720 |  | 720
| Partnering | 0 |  | 500 |  | 500
| ODOT | 950 |  | 0 |  | 0
| Total | #VALUE! | 50565 |  | 20391.3 |  | 20391.3
Total |  |  | #REF! |  | 267891.3 | 0% | 267891.3
River Access and Transportation Phase I | [5 empty] | Page: | 6
Other Project Costs | [5 empty] | Date: | 2026-07-29 03:07
Summary of Project Cost - Long Term Operating Cost
Description |  | 90% Estimate |  | Budget |  | Actual
|  | Costs | Totals | Costs | Totals | Costs | Totals
UPRR
| Labor | 142000 |  | 0 |  | 0
| Power cost for Bridge Lifts ($3,000 per month) | 36000 |  | 36000 |  | 36000
| Cable Replacement ($2,000 per month) | 24000 |  | 8200 |  | 8200
| Total |  | 202000 |  | 44200 |  | 44200
City
| $10 Million Insurance | 25000 |  | 25000 |  | 25000
| Debris Removal | 5000 |  | 5000 |  | 5000
| Log Boom | 10000 |  | 40000 |  | 40000
| Closing manual gates during high water | 1000 |  | 1000 |  | 1000
| Lighting | 2000 |  | 2000 |  | 2000
| Annual Inspection | 3000 |  | 3000 |  | 3000
| Landscape Maintenance | 12000 |  | 12000 |  | 12000
| Clean Inlets | 2000 |  | 2000 |  | 2000
| Trash Removal | 12000 |  | 12000 |  | 12000
| Total |  | 72000 |  | 102000 |  | 102000
Total |  |  | 274000 |  | 146200 |  | 146200

## City only Staff Costs
City Cost for Construction of RAT I | [9 empty] | 2026-07-29 03:07
Budgeted | [9 empty] | 46232.1296
Office Space 301 NE 2nd Ave., Suite 300 |  |  |  |  | City Staff
Description |  | Duration in Months | Cost | Amount | Description |  | Duration in Days | Duration in Weeks | Cost | Amount
Carpet |  | 1 | 500 | 500 | Section Manger (Karen) | ($125,000/260 days) | 80 | 16 | 490 | 39200
Carpet Removal |  | 1 | 250 | 250 | Engineer (Teresa and Katharine) | ($100,000/260 days) | 30 | 6 | 390 | 11700
Field Office Rent |  | 13 | 400 | 5200 | PM (Rob) (17 months) | ($100,000/260 days) | 365 | 73 | 390 | 142350
DSL Line |  | 13 | 185 | 2405 | Inspector (Dan) (13 months) | ($385.00 per day) | 280 | 56 | 385 | 107800
[5 empty] | Inspector O.T. | ($12.50 premium X 8 hours) | 30 | 6 | 100 | 3000
Outhouse move-in |  | 0 | 75 | 0 | Field Tech (14 months) | ($30 X 8 hours) | 300 | 60 | 240 | 72000
Outhouse move-out |  | 0 | 75 | 0 | Field Tech O.T. | ($7.50 premium X 8 hours) | 60 | 12 | 60 | 3600
Weekly Service Fee |  | 0 | 18.5 | 0
Supplies |  | 13 | 100 | 1300 | Total |  |  |  |  | 379650
Trash |  | 0 | 30 | 0
Move-in Cost for Office |  | 1 | 500 | 500
Move-out Cost for Office |  | 1 | 500 | 500
Total |  |  |  | 10655
Field Office Phones |  |  |  |  | Construction Support
Owner | Quantity | Ave. Monthly Cost | Installation | Amount | Description |  | Duration |  | Cost | Amount
Rob | 13 | 36 | 125 | 593 | Testing: City Materials Lab | ($2500 per month) | 0 |  | 2500 | 0
Inspector | 12 | 36 | 125 | 557 | Testing: ODOT Lab | ($500 per month) | 0 |  | 500 | 0
Tech | 12 | 36 | 125 | 557 | ODOT Staff | ($1500 per month) | 0 |  | 1500 | 0
Engineer | 0 | 36 | 125 | 125 | Field Office Drafting Station |  | 1 |  | 3300 | 3300
Fax | 13 | 36 | 125 | 593 | Microstation Version J License |  | 1 |  | 2300 | 2300
Data | 13 | 36 | 125 | 593 | Annual Software Maintenance |  | 1 |  | 130 | 130
Total |  |  | 750 | 2425 | Total |  |  |  |  | 5730
Summary |  |  |  |  | Project Phase |  | Start | Finish | Duration in Weeks | Duration in Working Days
Description |  |  | Cost
[5 empty] | Bidding |  | 1999-11-15 | 2000-01-31 | 11 | 55
Office Space 301 NE 2nd Ave., Suite 300 |  |  | 10655 |  | Construction |  | 2000-02-01 | 2001-02-01 | 52 | 260
Staff (City) |  |  | 379650 |  | Contract Extension for Change Orders |  | 2001-02-01 | 2001-03-01 | 4 | 20
ODOT-City Testing |  |  | 0 |  | Project Close-out |  | 2001-03-01 | 2001-04-15 | 6 | 30
Field Office Phones |  |  | 2425
Field Office Drafting Station and Software |  |  | 5730 |  | Total |  |  |  | 73 | 365
Grand Total |  |  | 398460 |  | Total Duration in Months |  |  |  |  | 17
[7 empty] | Actual | Percentage | Budgeted | Difference
[5 empty] | Construction |  | 6162281
[5 empty] | Consultant Engineering |  | 395000 | 6.41% | 356334 | 38666
[5 empty] | City Engineering |  | 398460 | 6.466% | 454327 | -55867
[5 empty] | Partnering |  | 3525 |  | 10500 | -6975
[5 empty] | Total Construction Engineering |  | 796985 | 12.93% | 821161 | -24176
Budgeted Construction Engineering
Math Check |  | 398460
City only cost |  | 398460

## Actual City Staff Costs
City Cost for Construction of RAT I | [8 empty] | 2026-07-29 03:07
Actual Costs | [8 empty] | 46232.1296
Total Office Space and Other Miscellaneous Costs |  |  |  | City Staff without Overhead
Description | Duration in Months | Cost | Amount | Description |  | Duration in Days | Duration in Weeks | Cost | Amount
Design
|  |  |  | Actual City Staff Costs FY 1994-1999 |  |  |  |  | 148290.9
Carpet ($415.36 + $75) | 1 | 490.36 | 490.36 | Actual City Staff Costs FY 1999-2000 (AP1 to AP5) |  |  |  |  | 64298.86 | 235861.79 | Now | End | Total Days | Weeks | Work Days Remaining | Percentage | Days to bill project | Duration in Weeks
Construction
Field Office Rent | 13.3808 | 400 | 5352.3 | Actual City Staff Costs FY 1999-2000 (AP6 to AP13) |  |  |  |  | 133701.9
|  |  |  | Actual City Staff Costs FY 2000-2001 |  |  |  |  | 225548.2
Communication Services | 1 | 15110.51 | 15110.51
Future Staff Costs 7-1-2001 to 10-1-2001
Water | 12.4218 | 25.25 | 313.65 | Section Manger (Karen) | ($130,000/260 days) | 1 | 0.2 | 500 | 500 | 80217.42 | 2001-07-01 | 2001-10-01 | 92 | 13.1429 | 65.7143 | 2% | 1.3143 | 0.26286 | Section Manger (Karen)
|  |  |  | Engineer (Teresa and Katharine) | ($113,890/260 days) | 0 | 0 | 438 | 0 |  | 2001-07-01 | 2001-10-01 | 92 | 13.1429 | 65.7143 | 0% | 0 | 0 | Engineer (Teresa and Katharine)
Other Misc. Items (See Other Cost Tab) | 1 | 14211.85 | 14211.85 | PM (Rob) | ($113,890/260 days) | 63 | 13 | 438 | 27594 |  | 2001-07-01 | 2001-10-01 | 92 | 13.1429 | 65.7143 | 96.55% | 63.4483 | 12.6897 | PM (Rob) (17 months)
|  |  |  | PM Part-time (Rob) |  | 0 | 0 | 200 | 0 |  | 2001-07-01 | 2001-10-01 | 92 | 13.1429 | 65.7143 | 0% | 0 | 0
|  |  |  | PM (LID Manager Andrew) | ($113,890/260 days) | 15 | 3 | 438 | 6570
Move-in Cost for Office | 1 | 586.53 | 586.53 | Inspector (Dan) | ($385.00 per day) | 3 | 1 | 385 | 1155 |  | 2001-07-01 | 2001-10-01 | 92 | 13.1429 | 65.7143 | 4% | 2.6286 | 0.52571 | Inspector (Dan) (13 months)
|  |  |  | Inspector O.T. | ($12.50 premium X 8 hours) | 0 | 0 | 100 | 0 |  | 2001-07-01 | 2001-10-01 | 92 | 13.1429 | 65.7143 | 0% | 0 | 0 | Inspector O.T.
Move-out Cost for Office (500) | 1 | 660 | 660 | Inspector Part-time (Dan) |  | 0 | 0 | 193 | 0 |  | 2001-07-01 | 2001-10-01 | 92 | 13.1429 | 65.7143 | 0% | 0 | 0
|  |  |  | Intern for Archiving | ($30 X 8 hours) | 30 | 6 | 240 | 7200 |  | 2001-07-01 | 2001-10-01 | 92 | 13.1429 | 65.7143 | 34% | 22.3429 | 4.4686 | Field Tech (14 months)
Total |  |  | 36725.2 | Field Tech O.T. | ($7.50 premium X 8 hours) | 0 | 0 | 60 | 0 |  | 2001-07-01 | 2001-10-01 | 92 | 13.1429 | 65.7143 | 0% | 0 | 0 | Field Tech O.T.
Total Office Space and Other Miscellaneous Costs |  |  | 22513.35 | Total |  |  |  | 43019 | 614858.86
[10 empty] | Construction Engineering |  | Labor Percentage
[10 empty] | 402269.1 |  | 5.991%
Construction Costs
Summary | [9 empty] | 6714042.5975
Description |  | Cost |  | Construction Support
Total Office Space and Other Miscellaneous Costs |  | 36725.2 |  | Description |  | Duration |  | Cost | Amount
City Staff without Overhead |  | 614858.86 |  | Field Office Drafting Station | 33000 | 0 | Not Charged to Project | 3300 | 0 | A review of the full detail reports revealed that this was not billed
|  |  |  | Microstation Version J License | 23000 | 0 | Not Charged to Project | 2300 | 0 | to the project as indicated on the e-mail from Karen Rabiner to Steven Koch dated 2-8-2000
Field Office Drafting Station and Software |  | 687.5 |  | Annual Software Maintenance |  | 1 |  | 687.5 | 687.5
Grand Total |  | 652271.56 |  | Total |  |  |  |  | 687.5
|  |  |  | Project Phase |  | Start | Finish | Duration in Weeks | Duration in Working Days
|  |  |  | Bidding |  | 1999-11-15 | 2000-01-31 | 11 | 55
|  |  |  | AP 6 to AP 12 portion of Construction |  | 2000-02-01 | 2000-05-24 | 16 | 80
|  |  |  | Remaining Portion of Construction |  | 2000-05-25 | 2001-02-01 | 36 | 180
|  |  |  | Contract Extension for Change Orders |  | 2001-02-01 | 2001-05-20 | 15 | 75
|  |  |  | Project Close-out |  | 2001-05-21 | 2001-10-01 | 19 | 95
|  |  |  | Total |  |  |  | 97 | 485
|  |  |  | Total Duration in Months |  |  |  |  | 22
[5 empty] | Full-time | Part-time (from) | Part-time (to) | Weeks | Work Days
|  |  |  | Dan Moyer | 2001-04-02 | 2001-04-02 | 2001-05-28 | 8 | 40
|  |  |  | Michael Trabacca | 2001-04-06
|  |  |  | Rob Barnard | 2001-06-03 | 2001-06-04 | 2001-08-27 | 12 | 60
[6 empty] | Actual | Percentage | Budgeted | Difference
|  |  |  | Construction |  | 6162281
|  |  |  | Consultant Engineering |  | 395000 | 6.41% | 356334 | 38666
|  |  |  | City Engineering |  | 652271.56 | 10.58% | 454327 | 197944.56
|  |  |  | Partnering |  | 3525 |  | 10500 | -6975
|  |  |  | Total Construction Engineering |  | 1050796.56 | 17.05% | 821161 | 229635.56
Budgeted Construction Engineering
Math Check | #VALUE!
City only cost | #VALUE!

## Other Costs
River Access and Transportation Phase I | [5 empty] | Page: | 1
Detail for City Staff and Other Project Costs | [5 empty] | Date: | 2026-07-29 03:07
Other Costs - Project No 03547
Steel Bridge Construction
Description |  | Duration in Months | Cost | Amount
Printing and Interoffice Mail |  | 1 | 2777.65 | 2777.65
Office of Transportation (Less Change Order 1, 4, 7 and 59) |  | 1 | 11377.35 | 11377.35
| CO No. 1 City Furnished Staging Yard Illumination |  |  | -1098.35 | Costs included on Project Cost worksheet
| CO No. 4 City Furnished Twin Ornamental |  |  | -3850 | Costs included on Project Cost worksheet
| CO No. 7 City Furnished Single Ornamental |  |  | -1679.71 | Costs included on Project Cost worksheet
| CO No. 59: Street Light Funded CO. |  |  | -4674.74 | Journal Entry Error
Bob Bomber to Fix 9/6/2001
Office of Transportation (less $75 for field office carpet) |  | 1 | 45.69 | 45.69 | Should be shown as a minus project cost
(i.e., credit)
Computer Hard Drive Replacement (office Depot) |  | 1 | 149.99 | 149.99
ZGF Review of MSE Wall Coping |  | 1 | 460 | 460
Federal Express |  | 1 | 1575.59 | 1575.59
Wolf Camera (Film Processing) |  | 1 | 105.4 | 105.4
Graphic Information System (Project Logo and Ground Breaking Sign) |  | 1 | 238.65 | 238.65
Just Right Awards and Engraving (Plaque for UPRR) |  | 1 | 154.75 | 154.75
Order to Render Services for ODOT Staff Plan Review |  | 1 | 2197.87 | 2197.87
Pronto Messenger |  | 1 | 18.5 | 18.5
Aztec Signs and Graphics (Grand Opening Sign) |  | 1 | 167 | 167
Frog Legs (Ground Breaking Magnets) |  | 1 | 191.62 | 191.62
Facility Services |  | 1 | 240 | 240
Office Supplies and Equipment (Purchase card)
| FY 2000 |  |  | 3976.35
| FY 2001 (less $4,825 for the grand opening ribbon) |  |  | 1838.24
Total Construction Engineering |  |  |  | 14211.85
River Access and Transportation Phase I | [5 empty] | Page: | 2
Detail for City Staff and Other Project Costs | [5 empty] | Date: | 2026-07-29 03:07
Other Costs - Project No 03383
River Access Grant
Description |  | Duration in Months | Cost | Amount
Federal Express |  | 1 | 1405.27 | 1405.27
Moba Media Express |  | 1 | 55 | 55
Pronto Messenger |  | 1 | 295 | 295
Diners Club |  | 1 | 273 | 273
Bank of America |  | 1 | 4653.47 | 4653.47
Wolf Camera |  | 1 | 18.71 | 18.71
Graphic Information Systems |  | 1 | 816.1 | 816.1
Office of Transportation |  | 1 | 276.11 | 276.11
Printing Distribution Services |  | 1 | 7579.76 | 7579.76
Fleet Services |  | 1 | 27.92 | 27.92
Facilities Services/Rent |  | 1 | 80 | 80
Total Design Engineering |  |  |  | 15480.34
Other Costs - Project No 00992
Steel Bridge Design
Description |  | Duration in Months | Cost | Amount
Federal Express |  | 1 | 120.03 | 120.03
Pronto Messenger |  | 1 | 20 | 20
Diners Club |  | 1 | 205.51 | 205.51
Revere Graphics |  | 1 | 75.44 | 75.44
Bank of America |  | 1 | 716.21 | 716.21
Wolf Camera |  | 1 | 20.3 | 20.3
Office of Transportation ($34.93 - $3,220.00) |  | 1 | -3185.07 | -3185.07
Printing Distribution Services |  | 1 | 717.72 | 717.72
Fleet Services |  | 1 | 56.39 | 56.39
Facilities Services/Rent |  | 1 | 108 | 108
Total Design Engineering |  |  |  | -1145.47
River Access and Transportation Phase I | [5 empty] | Page: | 3
Detail for City Staff and Other Project Costs | [5 empty] | Date: | 2026-07-29 03:07
| Design Engineering Staff Costs without Overhead | Project Number
|  | 00992 | 03011 | 03383 | 03547
| Life to date for FY 1994-1999 | 93356.49 | 0 | 54934.41 | 0
Grand Total FY 1998-1999
| Life to date for FY 1994-1999 Totals | 93356.49 | 0 | 54934.41 | 0 | 148290.9
FY 1999-2000
| AP1: 7-21-1999 | 6013.16 | 0 | 440.83 | 0
| AP2: 8-18-1999 | 8313.34 | 0 | 3058.42 | 0
| AP 3: 9-15-1999 | 11113.2 | 0 | 3802.36 | 0
| AP 4: 10-13-1999 | 101.69 | 0 | 16287.5 | 0
| AP 5: 11-10-1999 | 1543.03 | 0 | 13575.92 | 49.41
Grand Total FY 1999-2000 (AP1-AP5)
| FY 1999-2000 Totals | 27084.42 | 0 | 37165.03 | 49.41 | 64298.86
Grand Total Design
| Total for Design Engineering | 120440.91 | 0 | 92099.44 | 49.41 | 212589.76
| Construction Engineering Staff Costs without Overhead | Project Number
|  | 00992 | 03011 | 03383 | 03547
FY 1999-2000
| AP 6: 12-8-1999 | 0 | 0 | 14211.79 | 0
| AP 7: 1-5-2000 | 4054.8 | 0 | 10382.31 | 385.16
| AP 8: 2-2-2000 | 4246.22 | 0 | 12419.5 | 259.92
| AP 9: 3-1-2000 | 0 | 0 | 12405.22 | 0
| AP 10: 3-29-2000 | 2968.23 | 0 | 6206.79 | 3983.9
| AP 11: 4-26-2000 | 0 | 46.53 | 509.64 | 18680.11
| AP 12: 5-24-2000 | 68.08 | 0 | 630.47 | 19180.91
| AP-13: 6-30-2000 | 22.67 | 0 | 467.51 | 22572.14
Grand Total FY 1999-2000 (AP6-AP13)
| FY 1999-2000 Totals | 11360 | 46.53 | 57233.23 | 65062.14 | 133701.9
FY 2000-2001
| AP-1: 8-2-2000 | 93.87 | 0 | 0 | 18995.08
| AP-2: 8-30-2000 | 2184.41 | 0 | 0 | 17586.88
| AP-3: 9-27-2000 | 140.66 | 0 | 0 | 23624.33
| AP 4: 10-25-2000 | 209.79 | 0 | 0 | 20589.94
| AP 5: 11-22-2000 | 157.48 | 0 | 0 | 21905.73
| AP 6: 12-20-2000 | 0 | 0 | 0 | 18096.04
| AP 7: 1-17-2001 | 46.94 | 0 | 0 | 13015.45
| AP 8: 2-14-2001 | 0 | 0 | 0 | 19300.73
| AP 9: 3-14-2001 | 0 | 0 | 0 | 19434.23
| AP 10: 4-11-2001 | 23.02 | 0 | 0 | 18897.87
| AP 11: 5-9-2001 | 0 | 0 | 0 | 11049.87
| AP 12: 6-6-2001 | 0 | 0 | 0 | 12060.99
| AP-13: 6-30-2001 | 46.73 | 0 | 0 | 8088.16
Grand Total FY 2000-2001
| FY 2000-2001 Totals | 2902.9 | 0 | 0 | 222645.3 | 225548.2
Grand Total Construction Engineering
| Totals for Construction Engineering | 14262.9 | 46.53 | 57233.23 | 287707.44 | 359250.1
River Access and Transportation Phase I | [5 empty] | Page: | 4
Detail for City Staff and Other Project Costs | [5 empty] | Date: | 2026-07-29 03:07
| Construction Engineering Staff Costs without Overhead | Project Number
|  | 00992 | 03011 | 03383 | 03547
Life to date for FY 1994-1999
| Full Time Regular Wages | 57243.79 |  | 31171.29
| Part Time Regular Wages | 175.5 |  | 3673.2
| Premium Wages | 971.31 |  | 34.5
| Benefits | 20225.41 |  | 11363.6
| Accrued Leave Rate | 14740.48 |  | 8691.82
Grand Total FY 1994-1999
| FY 1994-1999 Total | 93356.49 |  | 54934.41 |  | 148290.9
| See ACTUAL CITY STAFF COST worksheet for costs from 7-1-2001 to 10-1-2001 |  |  | Estimated Future Staff Costs |  | Match Check Design | Match Check Construction
|  |  |  | 43019 |  | 212589.76 | 359250.1
|  |  |  | Match Check All |  | 614858.86

## Estimated Co's
River Access and Transportation, Phase I | [8 empty] | Page No. |  | 1
Steel Bridge Pedestrian and Bicycle Crossing | [8 empty] | Contract No. |  | 32854
Summary of Final Construction Contract Costs (Exhibit "A") | [8 empty] | Ordinance No. |  | 174096
[9 empty] | Project No. |  | 03547
| Original Contract Amount | 6162281
| Quantity Variance | -1512.72 |  | -0.02455%
| Revised Total | 6160768.28
| Change Orders | 408146.2575 |  | 6.623%
| Final Contract Amount | 6568914.5375 |  | 106.6%
CO. | Description | Estimated | Unit | Unit Price | Estimated | Actual |  |  | Total all Change Orders
No. |  | Quantity |  |  | Amount | Quantity | Amount | Percentage Change | Amount | Percentage Change | Revised Contract Total
001 | City Furnished Staging Yard Illumination Materials | 1 | L.S. | -1098.35 | -1098.35 | 1 | -1098.35 | -0.01782% | -1098.35 | -0.01782% | 6161182.65 | -1098.35
002 | Improve Stark Street construction access route | 1 | L.S. | 1536 | 1536 | 1 | 1536 | 0.02493% | 437.65 | 0.007102% | 6162718.65
003 | Remove off-site and legally dispose of unforeseen concrete and other non-native debris from stockpile | 1 | L.S. | 3195 | 3195 | 1 | 3195 | 0.05185% | 3632.65 | 0.05895% | 6165913.65
004 | Owner Furnished Twin Ornamental | 1 | L.S. | -3850 | -3850 | 1 | -3850 | -0.06248% | -217.35 | -0.003527% | 6162063.65 | -3850
005 | Curb Removal at Westbank | 1 | L.S. | 245.4 | 245.4 | 1 | 245.4 | 0.003982% | 28.05 | 0.0004552% | 6162309.05
006 | Overexcavation at Westbank | 1 | L.S. | 730 | 730 | 1 | 730 | 0.01185% | 758.05 | 0.0123% | 6163039.05
007 | Owner Furnished Single Ornamental | 1 | L.S. | -1700 | -1700 | 1 | -1700 | -0.02759% | -941.95 | -0.01529% | 6161339.05 | -1700
008 | Steel Bridge Chain Link Fence 4' instead of 6' | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | -941.95 | -0.01529% | 6161339.05
009 | Temporary Aggregate at Westbank for Rose Festival | 1 | L.S. | 1655.55 | 1655.55 | 1 | 1655.55 | 0.02687% | 713.6 | 0.01158% | 6162994.6
010 | Temporary Concrete Barriers at Eastbank | 1 | L.S. | 6400 | 6400 | 1 | 6400 | 0.1039% | 7113.6 | 0.1154% | 6169394.6
011 | 2" Deep Grass Mulch at Eastbank | 1 | L.S. | 3800 | 3800 | 1 | 3800 | 0.06167% | 10913.6 | 0.1771% | 6173194.6
012 | Temporary 6' Fence at Eastbank | 1 | L.S. | 593.77 | 593.77 | 1 | 593.77 | 0.009636% | 11507.37 | 0.1867% | 6173788.37
013 | Schedule 40 PVC Laterals | 1 | L.S. | 1570.08 | 1570.08 | 1 | 1570.08 | 0.02548% | 13077.45 | 0.2122% | 6175358.45
014 | Subexcavation and Backfill at MSE Wall K | 1 | L.S. | 8530.61 | 8530.61 | 1 | 8530.61 | 0.1384% | 21608.06 | 0.3507% | 6183889.06
015 | MSE Wall Backfill instead of Existing Borrow at Wall K | 550 | C.Y. | 27 | 14850 | 550.3 | 14858.1 | 0.2411% | 36466.16 | 0.5918% | 6198747.16
016 | MCI WorldCom Conduits Schedule 80 to 40 PVC | 1 | L.S. | -779.31 | -779.31 | 1 | -779.31 | -0.01265% | 35686.85 | 0.5791% | 6197967.85 | -779.31
017 | Structural Backfill Between UPRR Overcrossing Bent 2 and 3 | 700 | L.S. | 27 | 18900 | 411.2 | 11102.4 | 0.1802% | 46789.25 | 0.7593% | 6209070.25
018 | UPRR Overcrossing Detail Changes per RFI 7 & CLR 4 | 1 | L.S. | 1091.48 | 1091.48 | 1 | 1091.48 | 0.01771% | 47880.73 | 0.777% | 6210161.73
019 | Steel Bridge 2" Steel Grating Revisions | 1 | L.F. | 9063 | 9063 | 1 | 9063 | 0.1471% | 56943.73 | 0.9241% | 6219224.73
020 | UPRR Overcrossing Bent 2 Rebar Conflict | 1 | L.S. | 2570.73 | 2570.73 | 1 | 2570.73 | 0.04172% | 59514.46 | 0.9658% | 6221795.46
021 | Change Bark Mulch type ($40 CY) | 370 | C.Y. | 40 | 14800 | 368.75 | 14750 | 0.2394% | 74264.46 | 1.205% | 6236545.46
022 | High Voltage Raceway Revisions | 1 | L.S. | -11427.62 | -11427.62 | 1 | -11427.62 | -0.1854% | 62836.84 | 1.02% | 6225117.84 | -11427.62
023 | Delete Seal Welds at Counterweights | 1 | L.S. | -3500 | -3500 | 1 | -3500 | -0.0568% | 59336.84 | 0.9629% | 6221617.84 | -3500
024 | MSE Wall "B" Footing Survey Error | 1 | L.S. | 237.21 | 237.21 | 1 | 237.21 | 0.003849% | 59574.05 | 0.9668% | 6221855.05
025 | Lower UPRR Domestic Water Supply Line | 1 | L.S. | 721.97 | 721.97 | 1 | 721.97 | 0.01172% | 60296.02 | 0.9785% | 6222577.02
026 | Anti-graffiti coating at slope pavers | 4200 | S.F. | 1.16 | 4872 | 4331.5 | 5024.54 | 0.08154% | 65320.56 | 1.06% | 6227601.56
027 | 8-inch ADS N-12 Storm Sewer Pipe ($55.50) | 370 | L.S. | 55.5 | 20535 | 457.2 | 25374.6 | 0.4118% | 90695.16 | 1.472% | 6252976.16 | 25374.6
028 | MSE Wall and Related Item Acceleration | 1 | L.S. | 24154.2 | 24154.2 | 0.41403 | 10000.6675 | 0.1623% | 100695.8275 | 1.634% | 6262976.8275
029 | Revision to Steel Bridge Walkway Brackets D & E (angles) | 1 | L.S. | 2226 | 2226 | 1 | 2226 | 0.03612% | 102921.8275 | 1.67% | 6265202.8275
030 | Revision to Steel Bridge Walkway Brackets D & E (bolts) | 1 | L.S. | 2171.33 | 2171.33 | 1 | 2171.33 | 0.03524% | 105093.1575 | 1.705% | 6267374.1575
River Access and Transportation, Phase I | [8 empty] | Page No. |  | 2
Steel Bridge Pedestrian and Bicycle Crossing | [8 empty] | Contract No. |  | 32854
Summary of Final Construction Contract Costs (Exhibit "A") | [8 empty] | Ordinance No. |  | 174096
[9 empty] | Project No. |  | 03547
Original Contract Amount
6162281
CO. | Description | Estimated | Unit | Unit Price | Estimated | Actual |  |  | Total all Change Orders
No. |  | Quantity |  |  | Amount | Quantity | Amount | Percentage Change | Amount | Percentage Change | Revised Contract Total
031 | Delete Fabric Around Storm Water Pipe Located in MSE Wall Backfill | 1 | L.S. | -500 | -500 | 1 | -500 | -0.008114% | 104593.1575 | 1.697% | 6266874.1575 | -500
032 | Furnish and Install Quazite Electrical Junction Boxes instead of OZ Gedney | 1 | L.S. | -6804.6 | -6804.6 | 1 | -6804.6 | -0.1104% | 97788.5575 | 1.587% | 6260069.5575 | -6804.6
033 | Delete Installation of DTI Washers on the Steel Bridge | 1 | L.S. | -750 | -750 | 1 | -750 | -0.01217% | 97038.5575 | 1.575% | 6259319.5575 | -750
034A | Installation of CCTV Items per RFP No. 12 | 1 | L.S. | 24119.21 | 24119.21 | 1 | 24119.21 | 0.3914% | 121157.7675 | 1.966% | 6283438.7675
034B | Steel Bridge Upper Deck Lane Closures for Installation of Owner Furnished Coaxial | 4 | EA | 500 | 2000 | 4 | 2000 | 0.03246% | 123157.7675 | 1.999% | 6285438.7675
035 | Schedule 80 PVC Unions on each side of Irrigation Zone Valves A1 to A17 | 1 | L.S. | 2127.19 | 2127.19 | 1 | 2127.19 | 0.03452% | 125284.9575 | 2.033% | 6287565.9575
036 | Replacement Steel Bridge Pier Anchors | 1 | L.S. | 6506.75 | 6506.75 | 1 | 6506.75 | 0.1056% | 131791.7075 | 2.139% | 6294072.7075
037 | Supplemental Reinforcing Steel at Trench Drains 17 & 19 | 1 | L.S. | 350 | 350 | 1 | 350 | 0.00568% | 132141.7075 | 2.144% | 6294422.7075
038 | Overlook Stair Modifications at Upper Landing | 1 | L.S. | 1523.81 | 1523.81 | 1 | 1523.81 | 0.02473% | 133665.5175 | 2.169% | 6295946.5175
039 | Signal, CCTV and Light Pole support bracket modifications | 1 | L.S. | 1997.31 | 1997.31 | 1 | 1997.31 | 0.03241% | 135662.8275 | 2.202% | 6297943.8275
040 | Relocate Southern MCI Manhole 165' South | 1 | L.S. | 6794.58 | 6794.58 | 1 | 6794.58 | 0.1103% | 142457.4075 | 2.312% | 6304738.4075
041 | Lower HV power line by Retaining Wall "A" | 1 | L.S. | 2294.65 | 2294.65 | 1 | 2294.65 | 0.03724% | 144752.0575 | 2.349% | 6307033.0575
042 | Stair Conflict Modifications, west fixed span | 1 | L.S. | 5209.69 | 5209.69 | 1 | 5209.69 | 0.08454% | 149961.7475 | 2.434% | 6312242.7475
043 | Dedicated Power for CCTV Life-Safety Equipment | 1 | L.S. | 1238.04 | 1238.04 | 1 | 1238.04 | 0.02009% | 151199.7875 | 2.454% | 6313480.7875
044 | Revise Electrical Panel Board "M" to GE Type | 1 | L.S. | 1329.09 | 1329.09 | 1 | 1329.09 | 0.02157% | 152528.8775 | 2.475% | 6314809.8775
045 | Furnish Ballast Rock between UPRR tracks and Overlook Slope | 1 | L.S. | 1918.89 | 1918.89 | 1 | 1918.89 | 0.03114% | 154447.7675 | 2.506% | 6316728.7675
046 | Re-engineering MSE Retaining Wall "B" | 1 | L.S. | 5905 | 5905 | 1 | 5905 | 0.09582% | 160352.7675 | 2.602% | 6322633.7675
047 | Revise GE Series 90 PLC card to GE VersaMax Micro | 1 | L.S. | 956.34 | 956.34 | 1 | 956.34 | 0.01552% | 161309.1075 | 2.618% | 6323590.1075
048 | Revise Framing and Harbor Wall Connection Detail at West Approach Span | 1 | L.S. | 1610 | 1610 | 1 | 1610 | 0.02613% | 162919.1075 | 2.644% | 6325200.1075
049 | Delete installation of expansion joint system at 4" and 6" concrete surfacing | 218 | L.F. | -3.75 | -817.5 | 218 | -817.5 | -0.01327% | 162101.6075 | 2.631% | 6324382.6075
050 | Lift Span Life Safety Electrical Modifications | 1 | L.S. | 9325.7 | 9325.7 | 1 | 9325.7 | 0.1513% | 171427.3075 | 2.782% | 6333708.3075
River Access and Transportation, Phase I | [8 empty] | Page No. |  | 3
Steel Bridge Pedestrian and Bicycle Crossing | [8 empty] | Contract No. |  | 32854
Summary of Final Construction Contract Costs (Exhibit "A") | [8 empty] | Ordinance No. |  | 174096
[9 empty] | Project No. |  | 03547
Original Contract Amount
6162281
Item | Item of Work | Estimated | Unit | Unit Price | Estimated | Actual |  |  | Total all Change Orders
No. |  | Quantity |  |  | Amount | Quantity | Amount | Percentage Change | Amount | Percentage Change | Revised Contract Total
CO51A | Vibration Isolation at Lift Span Electrical | 1 | L.S. | 2349.54 | 2349.54 | 1 | 2349.54 | 0.03813% | 173776.8475 | 2.82% | 6336057.8475
CO51B | Ventilation Louvers at Lift Span Un-interruptible Power Supply Enclosure | 1 | L.S. | 545.01 | 545.01 | 1 | 545.01 | 0.008844% | 174321.8575 | 2.829% | 6336602.8575
CO52A | Lift Span Navigation Light and Access Platform Modifications | 1 | L.S. | 2123.62 | 2123.62 | 1 | 2123.62 | 0.03446% | 176445.4775 | 2.863% | 6338726.4775
CO52B | Delete Removal of South Side Lift Span Navigation Light Access Platform (C-3) | 1 | L.S. | -500 | -500 | 1 | -500 | -0.008114% | 175945.4775 | 2.855% | 6338226.4775
CO-53 | UPRR Overcrossing Luminaire and Protection Cage Modifications | 1 | L.S. | 3791.85 | 3791.85 | 1 | 3791.85 | 0.06153% | 179737.3275 | 2.917% | 6342018.3275
CO-54 | Modify Grate Elevation at CB 6 from 32.96 to read 32.26 | 1 | L.S. | 354.67 | 354.67 | 1 | 354.67 | 0.005755% | 180091.9975 | 2.922% | 6342372.9975
CO-55 | Overlook Stair Modifications and Minor Related Items | 1 | L.S. | 6895.58 | 6895.58 | 1 | 6895.58 | 0.1119% | 186987.5775 | 3.034% | 6349268.5775
CO-56 | Revise Quick Coupler in OZ Gedney Box to a Zurn Ground Hydrant | 1 | L.S. | -650 | -650 | 1 | -650 | -0.01055% | 186337.5775 | 3.024% | 6348618.5775
CO-57 | Rebar at Western Edge of Lower Ramp Curb/Thickened Edge from Station 10+04 to 11+00 | 1 | L.S. | 384.12 | 384.12 | 1 | 384.12 | 0.006233% | 186721.6975 | 3.03% | 6349002.6975
CO-58 | Black Vinyl Coated Chain Link Fence - 4' high ($40/LF Savings from BI D63) | 92 | L.F. | 35 | 3220 | 88.6 | 3101 | 0.05032% | 189822.6975 | 3.08% | 6352103.6975
CO-59 | Fuses, holders, and insulating boots at Holophane and Spectra fixtures | 1 | L.S. | 4674.74 | 4674.74 | 1 | 4674.74 | 0.07586% | 194497.4375 | 3.156% | 6356778.4375
CO-60 | Correct Survey Error at MSE Walls B, E, and H Coping | 1 | L.S. | 53682.24 | 53682.24 | 1 | 53682.24 | 0.8711% | 248179.6775 | 4.027% | 6410460.6775
CO-61 | Maintenance Access Road Revisions and Landscape | 1 | L.S. | 6747.04 | 6747.04 | 1 | 6747.04 | 0.1095% | 254926.7175 | 4.137% | 6417207.7175
CO-62 | Remove four luminaire protective cages at UPRR Overcrossing Structure | 1 | L.S. | 1409.33 | 1409.33 | 1 | 1409.33 | 0.02287% | 256336.0475 | 4.16% | 6418617.0475
CO-63 | Furnish and install 4 bollards adjacent to the transformer and power distribution panel | 1 | L.S. | 876 | 876 | 1 | 876 | 0.01422% | 257212.0475 | 4.174% | 6419493.0475
CO-64 | Furnish and install one LID plaque pedestal and 2 Owner furnished LID plaques | 1 | L.S. | 1000 | 1000 | 1 | 1000 | 0.01623% | 258212.0475 | 4.19% | 6420493.0475
CO-65 | Furnish and install lift span limit switch and Steel Bridge | 1 | L.S. | 597.69 | 597.69 | 1 | 597.69 | 0.009699% | 258809.7375 | 4.2% | 6421090.7375
CO-66 | Pressure sewer crossing hood and in-fill panel revisions | 1 | L.S. | 6631.06 | 6631.06 | 1 | 6631.06 | 0.1076% | 265440.7975 | 4.308% | 6427721.7975
CO-67 | Supplemental lift span walkway luminaires | 1 | L.S. | 5726.24 | 5726.24 | 1 | 5726.24 | 0.09292% | 271167.0375 | 4.4% | 6433448.0375
CO-68 | Lift span Life safety equipment modifications | 1 | L.S. | 30508.14 | 30508.14 | 1 | 30508.14 | 0.4951% | 301675.1775 | 4.896% | 6463956.1775
CO-69 | Overhead protective fence at I-5 to I-84 interchange | 1 | L.S. | 28424.08 | 28424.08 | 1 | 28424.08 | 0.4613% | 330099.2575 | 5.357% | 6492380.2575
CO-70 | Staging yard fence modifications | 1 | L.S. | 2000 | 2000 | 1 | 2000 | 0.03246% | 332099.2575 | 5.389% | 6494380.2575
CO-71 | Delete custom fence at Steel Bridge signal platforms | 1 | L.S. | -3723 | -3723 | 1 | -3723 | -0.06042% | 328376.2575 | 5.329% | 6490657.2575
CO-72 | Extended warranty at Steel Bridge concrete filled grating | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 328376.2575 | 5.329% | 6490657.2575
CO-73 | Lift span flagging and radio modem troubleshooting | 1 | L.S. | 24077 | 24077 | 1 | 24077 | 0.3907% | 352453.2575 | 5.72% | 6514734.2575
CO-74 | Lift span flagging and release and waiver of all claims arising out of or relating to the Contract | 1 | L.S. | 57000 | 57000 | 1 | 57000 | 0.925% | 409453.2575 | 6.645% | 6571734.2575
CO-75 | Temporary Power Pole Salvage Value Credit | 1 | L.S. | -1307 | -1307 | 1 | -1307 | -0.02121% | 408146.2575 | 6.623% | 6570427.2575
[6 empty] | 6.731% |  | 0
Original Contract Amount |  |  |  |  | 6162281 | 414794.6075 | 408146.2575 | Math Check
River Access and Transportation, Phase I | [8 empty] | Page No. |  | 4
Steel Bridge Pedestrian and Bicycle Crossing | [8 empty] | Contract No. |  | 32854
Anticipated Add Items Log | [8 empty] | Ordinance No. |  | 174096
[9 empty] | Project No. |  | 03547
Original Contract Amount
6162281
CO. | Description | Estimated | Unit | Unit Price | Estimated | Actual |  |  | Total all Change Orders
No. |  | Quantity |  |  | Amount | Quantity | Amount | Percentage Change | Amount | Percentage Change | Revised Contract Total
0 |  | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 408146.2575 | 6.623% | 6570427.2575
0 |  | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 408146.2575 | 6.623% | 6570427.2575
0 |  | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 408146.2575 | 6.623% | 6570427.2575
0
0 |  | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 408146.2575 | 6.623% | 6570427.2575
0 |  | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 408146.2575 | 6.623% | 6570427.2575
0 |  | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 408146.2575 | 6.623% | 6570427.2575
0 | Additional UPRR Flagging Costs (March, April, May at Full-time. June to July 12 half-time) | 3.5 | Months | 11000 | 38500 | 3.5 | 38500 | 0.6248% | 446646.2575 | 7.248% | 6608927.2575
0 |  | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 446646.2575 | 7.248% | 6608927.2575
0 | 38500 | 0 | Hr | 0 | 0 | 0 | 0 | 0% | 446646.2575 | 7.248% | 6608927.2575
0 |  | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 446646.2575 | 7.248% | 6608927.2575
0 |  | 1 | L.S. | 0 | 0 | 1 | 0 | 0% | 446646.2575 | 7.248% | 6608927.2575
0 |  | 1 | L.F. | 0 | 0 | 1 | 0 | 0% | 446646.2575 | 7.248% | 6608927.2575
Original Contract Amount |  |  |  |  | 6162281 | 0.6248% | 38500 | Math Check | 446646.2575 |  | 446646.2575
River Access and Transportation, Phase I | [8 empty] | Page No. |  | 5
Steel Bridge Pedestrian and Bicycle Crossing | [8 empty] | Contract No. |  | 32854
Change Order Log | [8 empty] | Ordinance No. |  | 174096
[9 empty] | Project No. |  | 03547
Summary of Contingency Expended By Major Cost Category
|  |  |  | Percentage | Amount |  | Total Project Funds |  | 9821433.98
Original Contract Contingency Amount |  |  |  |  | 433285.41
Additional funds from Street Lighting - CO No. 59 |  |  |  |  | 4674.74 |  | Remaining Contingency |  | 0.0024557
Additional funds from HNTB - Errors/Omission - CO No. 60 |  |  |  |  | 53682.24
Additional funds from HNTB - Errors/Omission - CO No. 74 |  |  |  |  | 24077 |  | Percentage |  | 2.5e-08%
Potential additional funds Required |  |  |  |  | 0
Revised Contingency |  |  |  |  | 515719.39
Project Development Increases |  |  |  | -3.285% | -16941
UPRR Increases |  |  |  | 2.009% | 10360
Construction |  |  |  | 88.74% | 457657.1075
Construction Engineering |  |  |  | 12.53% | 64643.28
Net Remaining Un-encumbered Contingency |  |  |  | 4.762e-07% | 0.0024557
[7 empty] | 614791 | Original Anticipated Contingency
[7 empty] | 4674.74 | Added funds
[7 empty] | 53682.24 | Added funds
[7 empty] | 24077 | Added funds
[7 empty] | 697224.98 | Total revised contingency if original funds available
[7 empty] | -515719.3875 | Less total added costs
[7 empty] | 181505.5925 | Net Remaining if original contingency amount was available

## LID
River Access and Transportation, Phase I | [5 empty] | Page No. |  | 1
Steel Bridge Pedestrian and Bicycle Crossing | [5 empty] | Contract No. |  | 32854
LID Assessment | [5 empty] | Ordinance No. |  | 174096
[6 empty] | Project No. |  | 03547
[6 empty] | LID File |  | C-9976
Item Number | R-Numbers |  | Property Owner | Actual Final Assessment | Superintendency (Funded by PDOT) | Recording Fee (Funded by PDOT) | Total Auditor Assessment Fees (Funded by PDOT) | Net Effective Assessment
1 | R182157 | R396200960 | City of Portland - PDC | 136363 | 597.2699 | 28 | 625.2699 | 135737.7301
2 | R305188 | R903701000 | City of Portland - PDOT | 136369.1 | 597.2967 | 28 | 625.2967 | 135743.8033
3 | R305200 | R903701950 | Louis Dreyfus | 68181 | 298.6328 | 28 | 326.6328 | 67854.3672
4 | R141438 | R180236220 | H. Naito Corporation | 136363 | 597.2699 | 28 | 625.2699 | 135737.7301
| R141436 | R180236180
5 | R305195 | R903701720 | Kalberer Hotel Supply | 68181 | 298.6328 | 28 | 326.6328 | 67854.3672
| R305196 | R903701730
6 | R140354 | R180200760 | Port of Portland (Contract Purchaser from NW Natural Gas) | 136363 | 597.2699 | 28 | 625.2699 | 135737.7301
7 | R140386 | R180201520 | NW Natural Gas | 136363 | 597.2699 | 28 | 625.2699 | 135737.7301
8 | R140952 | R180217300 | Hoyt Street Properties, Inc. | 136363 | 597.2699 | 28 | 625.2699 | 135737.7301
| R141027 | R180220350
9 | R305194 | R903701460 | METRO | 204545.45 | 895.9091 | 28 | 923.9091 | 203621.5409
10 | R316801 | R941340390 | Oregon Arena/Aegean | 204545.45 | 895.9091 | 28 | 923.9091 | 203621.5409
| R215941 | R553000500
11 | R291745 | R850600250 | PDC for GSL Properties | 136363 | 597.2699 | 28 | 625.2699 | 135737.7301
Totals |  |  |  | 1500000 | 6570 | 308 | 6878 | 1493122
[6 empty] | Math Check |  | 1493122
|  | Superintendency | 4.38 | per thousand |  | Total PDOT Funded Fees |  | 6878
|  | Recording Fee | 28
| Base LID |  | 1500000 | 1500000 |  | Funds received from LID |  | 1493152.01
| Less PDOT Share |  | -136369.1 | -136369.1 |  | PDOT Payment to LID |  | -136369.1
-6225.42 | Less Auditor Fees |  | -6847.99 |  |  | Plus PDOT fees included above |  | 622.57
| Plus Auditor Fee included above |  | 622.57
| Net LID Funding |  | 1357405.48 | 1363630.9 |  | NET LID Funding |  | 1357405.48
1363630.9
Auditor's Fees*
Seq | Tax Lot | Owner / Mailing Address | Account # | Real Mkt. Value | PDOT Assessment | Auditor Assessment | Revised Assessment | Final Assessment | Superintendency | Recording | Total | Final Billing | V/A Ratio | TSDC Credit
1 |  | City of Portland (PDC) | R182157 | 1756080 | 136363.64 | 136363 | 136363 | 135740.46 | 594.54 | 28 | 622.54 | 136363 | 12.878 | 0
|  | 1120 SW Fifth Ave. #1100 | (R396200960)
Portland, OR 97204
2 |  | City of Portland (PDOT) | R305188 | 51170 | 136363.64 | 136363 | 136369.1 | 135746.53 | 594.57 | 28 | 622.57 | 136369.1 | 0.37523 | 0
|  | 1120 SW Fifth Ave. #802 | (R903701000)
Portland, OR 97204
3 |  | Louis Dreyfus Corp. | R305200 | 3572640 | 68181.82 | 68181 | 68181 | 67855.79 | 297.21 | 28 | 325.21 | 68181 | 52.3993 | 48303.17
|  | 10 Westport Rd. | (R903701950)
Wilton, CT 06897-0810
4 |  | H. Naito Corporation | R141438 | 1287200 | 136363.64 | 136363 | 136363 | 135740.46 | 594.54 | 28 | 622.54 | 136363 | 9.4395 | 96606.33
|  | 5 NW Naito Pkwy. | (R180236220)
Portland, OR 97209
5 |  | H. Naito Corporation | R141436 | 390080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 NW Naito Pkwy. | (R180236180)
Portland, OR 97209
6 |  | Kalberer Hotel Supply | R305195 | 456600 | 68181.82 | 0 | 68181 | 67855.79 | 297.21 | 28 | 325.21 | 68181 | 6.6969 | 48303.17
|  | 733 SW Second Ave. #215 | (R903701720)
Portland, OR 97204
7 |  | Kalberer Hotel Supply | R305196 | 28200 | 0 | 68181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 733 SW Second Ave. #215 | (R903701730)
Portland, OR 97204
8 |  | Port of Portland | R140354 | 20050000 | 136363.64 | 136363 | 136363 | 135740.46 | 594.54 | 28 | 622.54 | 136363 | 147.034 | 96606.33
|  | P.O. Box 3529 | (R903701760)
Portland, OR 97208
9 |  | NW Natural Gas | R140386 | n/a | 136363.64 | 136363 | 136363 | 135740.46 | 594.54 | 28 | 622.54 | 136363 | n/a | 96606.33
|  | 220 NW Second Ave. | (R180201520)
Portland, OR 97209
10 |  | Hoyt Street Properties, LLC | R140952 | 11300000 | 0 | 136363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 809 NW 11th Ave. | (R180217300)
|  | Portland, OR 97209 | subdivided
11 |  | Hoyt Street Properties, LLC | R141027 | 4050000 | 136363.64 | 0 | 136363 | 135740.46 | 594.54 | 28 | 622.54 | 136363 | 29.7001 | 96606.33
|  | 809 NW 11th Ave. | (R180220350)
Portland, OR 97209
12 |  | Metropolitan Service District | R305194 | 187106040 | 204545.45 | 204548.5 | 204545.45 | 203625.57 | 891.88 | 28 | 919.88 | 204545.45 | 914.7407 | 144909.5
|  | 600 NE Grand Ave. | (R903701460)
Portland, OR 97232
13 |  | Aegean (Oregon Arena Corp.) | R316801 | 218250 | 0 | 204548.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | One Center Ct. #200 | (R941340390)
Portland, OR 97227
14 |  | Aegean (Oregon Arena Corp.) | R215941 | 4807320 | 204545.45 | 0 | 204545.45 | 203625.57 | 891.88 | 28 | 919.88 | 204545.45 | 23.5025 | 144909.5
|  | One Center Ct. #200 | (R553000500)
Portland, OR 97227
15 |  | PDC (for GSL Properties) | R291745 | 1306380 | 136363.64 | 136363 | 136363 | 135740.46 | 594.54 | 28 | 622.54 | 136363 | 9.5802 | 96606.33
|  | 1120 SW Fifth Ave. #1102 | (R850600250)
Portland, OR 97204
|  |  |  | 236379960 | 1500000.02 | 1500000 | 1500000 | 1493152.01 | 6539.99 | 308 | 6847.99 | 1500000 | 157.5866 | 869456.99
*Includes superintendency (project creation) fee of $4.38 per $1,000 assessed plus recording fee of $28.00 per property assessed. | [11 empty] | LID Fee Paid By PDOT
[11 empty] | 6847.99 | LID Fees
Steel Bridge LID Final Book.xls | [10 empty] | -622.57 | Less Fees included in PDOT Bill |  | 2026-07-29 03:07
[11 empty] | 6225.42 | Net Remaining Fees

## Final Bid Tab
City of Portland, Oregon
Bureau of Engineering and Development
Final Estimate
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Schedule A - General Requirements, Mobilization and Traffic Control
00210 | A-1 | Mobilization | 1 | L.S. | 610000 |  | 610000 | 1 | 610000 | 0 | 0 | 1 | 610000 | 1 | 610000 | 0 | 0% | 0
106 | A-2 | Testing and Inspection Services (Allowance) | 1 | L.S. | 25000 |  | 25000 | 1.6624 | 41561.01 | 0 | 0 | 1.6624 | 41561.01 | 1.6624 | 41561.01 | 0 | 0% | 0
111 | A-3 | Project Schedule | 1 | L.S. | 30000 |  | 30000 | 1 | 30000 | 0 | 0 | 1 | 30000 | 1 | 30000 | 0 | 0% | 0
112 | A-4 | Project Record Documents | 1 | L.S. | 28000 |  | 28000 | 1 | 28000 | 0 | 0 | 1 | 28000 | 1 | 28000 | 0 | 0% | 0
00215 | A-5 | Construction Staging Yard | 1 | L.S. | 48000 |  | 48000 | 1 | 48000 | 0 | 0 | 1 | 48000 | 1 | 48000 | 0 | 0% | 0
00215 | A-6 | Construction Staging Yard Illumination | 1 | L.S. | 14500 |  | 14500 | 1 | 14500 | 0 | 0 | 1 | 14500 | 1 | 14500 | 0 | 0% | 0
00225 | A-7 | Temporary Protection and Direction of Traffic | 1 | L.S. | 75000 |  | 75000 | 1 | 75000 | 0 | 0 | 1 | 75000 | 1 | 75000 | 0 | 0% | 0
00225 | A-8 | Temporary Plastic Drums | 24 | Each | 80 |  | 1920 | 24 | 1920 | 0 | 0 | 24 | 1920 | 24 | 1920 | 0 | 0% | 0
00225 | A-9 | Temporary Delineators | 200 | Each | 20 |  | 4000 | 210 | 4200 | 0 | 0 | 210 | 4200 | 210 | 4200 | 0 | 0% | 0
00225 | A-10 | Sequential Arrow Sign | 2 | Each | 3300 |  | 6600 | 2 | 6600 | 0 | 0 | 2 | 6600 | 2 | 6600 | 0 | 0% | 0
00225 | A-11 | Flaggers | 650 | Hour | 32 |  | 20800 | 1069.25 | 34216 | 0 | 0 | 1069.25 | 34216 | 1069.25 | 34216 | 0 | 0% | 0
00225 | A-12 | Orange Safety Fence (4' High) | 465 | L.F. | 5 |  | 2325 | 347 | 1735 | 0 | 0 | 347 | 1735 | 347 | 1735 | 0 | 0% | 0
00280 | A-13 | Erosion Control | 1 | L.S. | 7500 |  | 7500 | 1 | 7500 | 0 | 0 | 1 | 7500 | 1 | 7500 | 0 | 0% | 0
00280 | A-14 | Silt Fence, Supported | 1000 | L.F. | 4 |  | 4000 | 1076.5 | 4306 | 0 | 0 | 1076.5 | 4306 | 1076.5 | 4306 | 0 | 0% | 0
00280 | A-15 | Silt Fence, Supported with Orange Safety Fence | 400 | L.F. | 8 |  | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
26693.01
Total Schedule A - General Requirements, Mobilization and Traffic Control | [6 empty] | 880845 | 103% | 907538.01 |  | 0 |  | 907538.01 |  | 907538.01 |  | 0% | 0
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Schedule B - Westbank Connection
00310 | B-1 | Removal of Structures and Obstructions | 1 | L.S. | 5000 |  | 5000 | 1 | 5000 | 0 | 0 | 1 | 5000 | 1 | 5000 | 0 | 0% | 0
00320 | B-2 | Clearing and Grubbing | 1 | L.S. | 500 |  | 500 | 1 | 500 | 0 | 0 | 1 | 500 | 1 | 500 | 0 | 0% | 0
00641 | B-3 | Aggregate Base, 4-Inches Thick | 23 | S.Y. | 6 |  | 138 | 394 | 2364 | 0 | 0 | 394 | 2364 | 394 | 2364 | 0 | 0% | 0
00759 | B-4 | Concrete Curb (15"X18") | 55 | L.F. | 58 |  | 3190 | 66.5 | 3857 | 0 | 0 | 66.5 | 3857 | 66.5 | 3857 | 0 | 0% | 0
00759 | B-5 | Concrete Surfacing, 6-in. thick | 406 | S.Y. | 42 |  | 17052 | 390.16 | 16386.72 | 0 | 0 | 390.16 | 16386.72 | 390.16 | 16386.72 | 0 | 0% | 0
01010 | B-6 | Topsoil | 15 | C.Y. | 30 |  | 450 | 12 | 360 | 0 | 0 | 12 | 360 | 12 | 360 | 0 | 0% | 0
01035 | B-7 | Sod Lawn | 1200 | S.F. | 1 |  | 1200 | 1400 | 1400 | 0 | 0 | 1400 | 1400 | 1400 | 1400 | 0 | 0% | 0
01040 | B-8 | Tree Grate | 2 | EA | 1100 |  | 2200 | 2 | 2200 | 0 | 0 | 2 | 2200 | 2 | 2200 | 0 | 0% | 0
01040 | B-9 | Relocate Trees | 1 | EA | 800 |  | 800 | 1 | 800 | 0 | 0 | 1 | 800 | 1 | 800 | 0 | 0% | 0
01040 | B-10 | Deciduous Tree (4-1/2" Cal.) | 1 | EA | 700 |  | 700 | 2 | 1400 | 0 | 0 | 2 | 1400 | 2 | 1400 | 0 | 0% | 0
01120 | B-11 | Irrigation System | 1 | L.S. | 750 |  | 750 | 1 | 750 | 0 | 0 | 1 | 750 | 1 | 750 | 0 | 0% | 0
01401 | B-12 | Electrical Work | 1 | L.S. | 20000 |  | 20000 | 1 | 20000 | 0 | 0 | 1 | 20000 | 1 | 20000 | 0 | 0% | 0
3037.72
Total Schedule B - Westbank Connection | [6 empty] | 51980 | 105.8% | 55017.72 |  | 0 |  | 55017.72 |  | 55017.72 |  | 0% | 0
River Access and Transportation, Phase I | [15 empty] | Page No. |  | 2
Steel Bridge Pedestrian and Bicycle Crossing | [15 empty] | Contract No. |  | 32854
Final Estimate | [15 empty] | Ordinance No. |  | 174096
[16 empty] | Project No. |  | 03547
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Schedule C - Steel Bridge
00305 | C-1 | Construction Survey Work | 1 | L.S. | 25000 |  | 25000 | 1 | 25000 | 0 | 0 | 1 | 25000 | 1 | 25000 | 0 | 0% | 0
00305 | C-2 | Extra for Additional Survey Work | 50 | Hour | 160 |  | 8000 | 22 | 3520 | 0 | 0 | 22 | 3520 | 22 | 3520 | 0 | 0% | 0
00501 | C-3 | Bridge Removal Work | 1 | L.S. | 8500 |  | 8500 | 1 | 8500 | 0 | 0 | 1 | 8500 | 1 | 8500 | 0 | 0% | 0
00510 | C-4 | Structure Excavation | 1 | L.S. | 4500 |  | 4500 | 1 | 4500 | 0 | 0 | 1 | 4500 | 1 | 4500 | 0 | 0% | 0
00510 | C-5 | Shoring, Cribbing, Etc. | 1 | L.S. | 5000 |  | 5000 | 1 | 5000 | 0 | 0 | 1 | 5000 | 1 | 5000 | 0 | 0% | 0
00510 | C-6 | Granular Wall Backfill | 76 | C.Y. | 30 |  | 2280 | 77.87 | 2336.1 | 0 | 0 | 77.87 | 2336.1 | 77.87 | 2336.1 | 0 | 0% | 0
00530 | C-7 | Reinforcement | 1 | L.S. | 2500 |  | 2500 | 1 | 2500 | 0 | 0 | 1 | 2500 | 1 | 2500 | 0 | 0% | 0
00540 | C-8 | Structural Concrete, Class 3300 (25-37.5) | 1 | L.S. | 35000 |  | 35000 | 1 | 35000 | 0 | 0 | 1 | 35000 | 1 | 35000 | 0 | 0% | 0
00560 | C-9 | Structural Steel | 1 | L.S. | 950000 |  | 950000 | 1 | 950000 | 0 | 0 | 1 | 950000 | 1 | 950000 | 0 | 0% | 0
00561 | C-10 | West Approach Gate | 1 | L.S. | 6000 |  | 6000 | 1 | 6000 | 0 | 0 | 1 | 6000 | 1 | 6000 | 0 | 0% | 0
00562 | C-11 | Structural Aluminum | 1 | L.S. | 280000 |  | 280000 | 1 | 280000 | 0 | 0 | 1 | 280000 | 1 | 280000 | 0 | 0% | 0
00581 | C-12 | 6" Steel Drain Pipe | 1081 | L.F. | 90 |  | 97290 | 1263.5 | 113715 | 0 | 0 | 1263.5 | 113715 | 1263.5 | 113715 | 0 | 0% | 0
00592 | C-13 | Concrete Filled Steel Grating | 6917 | S.F. | 40 |  | 276680 | 6903.1 | 276124 | 0 | 0 | 6903.1 | 276124 | 6903.1 | 276124 | 0 | 0% | 0
00940 | C-14 | Permanent Signs in Place | 90 | S.F. | 28 |  | 2520 | 67.32 | 1884.96 | 0 | 0 | 67.32 | 1884.96 | 67.32 | 1884.96 | 0 | 0% | 0
01401 | C-15 | Electrical Work | 1 | L.S. | 225000 |  | 225000 | 1 | 225000 | 0 | 0 | 1 | 225000 | 1 | 225000 | 0 | 0% | 0
01402 | C-16 | Automatic Gates and Signals | 1 | L.S. | 125000 |  | 125000 | 1 | 125000 | 0 | 0 | 1 | 125000 | 1 | 125000 | 0 | 0% | 0
01403 | C-17 | Audible Warning and Public Address System | 1 | L.S. | 28000 |  | 28000 | 1 | 28000 | 0 | 0 | 1 | 28000 | 1 | 28000 | 0 | 0% | 0
01415 | C-18 | Operation and Maintenance Manual | 1 | L.S. | 5600 |  | 5600 | 1 | 5600 | 0.75 | 4200 | 0.25 | 1400 | 1 | 5600 | 0 | 0% | 0
01565 | C-19 | Lift Span Balancing | 1 | L.S. | 40000 |  | 40000 | 1 | 40000 | 0 | 0 | 1 | 40000 | 1 | 40000 | 0 | 0% | 0
01565 | C-20 | Balance-SH Rails | 69960 | LB | 1.2 |  | 83952 | 72669 | 87202.8 | 0 | 0 | 72669 | 87202.8 | 72669 | 87202.8 | 0 | 0% | 0
01565 | C-21 | Balance-New Steel | 178470 | LB | 1.2 |  | 214164 | 187456 | 224947.2 | 0 | 0 | 187456 | 224947.2 | 187456 | 224947.2 | 0 | 0% | 0
24844.06
Total Schedule C - Steel Bridge | [6 empty] | 2424986 | 101% | 2449830.06 |  | 4200 |  | 2445630.06 |  | 2449830.06 |  | 0% | 0
River Access and Transportation, Phase I | [15 empty] | Page No. |  | 3
Steel Bridge Pedestrian and Bicycle Crossing | [15 empty] | Contract No. |  | 32854
Final Estimate | [15 empty] | Ordinance No. |  | 174096
[16 empty] | Project No. |  | 03547
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Schedule D - Eastbank Connection
00310 | D-1 | Removal of Structures and Obstructions | 1 | L.S. | 85000 |  | 85000 | 1 | 85000 | 0 | 0 | 1 | 85000 | 1 | 85000 | 0 | 0% | 0
00320 | D-2 | Clearing and Grubbing | 1.58 | ACRE | 10000 |  | 15800 | 1.25 | 12500 | 0 | 0 | 1.25 | 12500 | 1.25 | 12500 | 0 | 0% | 0
00330 | D-3 | General Excavation | 3800 | C.Y. | 15 |  | 57000 | 1795.5 | 26932.5 | 0 | 0 | 1795.5 | 26932.5 | 1795.5 | 26932.5 | 0 | 0% | 0
00330 | D-4 | Embankment in Place | 1900 | C.Y. | 6 |  | 11400 | 1515.2 | 9091.2 | 0 | 0 | 1515.2 | 9091.2 | 1515.2 | 9091.2 | 0 | 0% | 0
00330 | D-5 | Foundation Excavation | 1155 | C.Y. | 10 |  | 11550 | 953 | 9530 | 0 | 0 | 953 | 9530 | 953 | 9530 | 0 | 0% | 0
00350 | D-6 | Subgrade Geotextile | 12601 | S.F. | 1 |  | 12601 | 2438 | 2438 | 0 | 0 | 2438 | 2438 | 2438 | 2438 | 0 | 0% | 0
00390 | D-7 | Loose Rip Rap-Cl. 1000 | 50 | C.Y. | 45 |  | 2250 | 130 | 5850 | 0 | 0 | 130 | 5850 | 130 | 5850 | 0 | 0% | 0
00430 | D-8 | 4-inch Drain Pipe | 65 | L.F. | 14 |  | 910 | 43 | 602 | 0 | 0 | 43 | 602 | 43 | 602 | 0 | 0% | 0
00430 | D-9 | 8-inch Drain Pipe | 384 | L.F. | 16 |  | 6144 | 367.1 | 5873.6 | 0 | 0 | 367.1 | 5873.6 | 367.1 | 5873.6 | 0 | 0% | 0
00430 | D-10 | Seatwall Drain | 260 | L.F. | 22 |  | 5720 | 267.2 | 5878.4 | 0 | 0 | 267.2 | 5878.4 | 267.2 | 5878.4 | 0 | 0% | 0
00445 | D-11 | 12-inch Storm Sewer Pipe. | 842 | L.F. | 60 |  | 50520 | 346 | 20760 | 0 | 0 | 346 | 20760 | 346 | 20760 | 0 | 0% | 0
00445 | D-12 | 36-inch Storm Sewer Pipe | 56 | L.F. | 115 |  | 6440 | 55 | 6325 | 0 | 0 | 55 | 6325 | 55 | 6325 | 0 | 0% | 0
00470 | D-13 | Concrete Inlet, Type G-2 | 6 | Each | 1000 |  | 6000 | 6 | 6000 | 0 | 0 | 6 | 6000 | 6 | 6000 | 0 | 0% | 0
00470 | D-14 | Concrete Manhole, Type A-P, 48-Inch Dia. | 3 | Each | 3000 |  | 9000 | 3 | 9000 | 0 | 0 | 3 | 9000 | 3 | 9000 | 0 | 0% | 0
00470 | D-15 | Concrete Manhole, Type A-P. 48-Inch Diameter w/Shear Gate | 1 | Each | 3500 |  | 3500 | 1 | 3500 | 0 | 0 | 1 | 3500 | 1 | 3500 | 0 | 0% | 0
00470 | D-16 | Concrete Manhole, Type B-P | 4 | Each | 2500 |  | 10000 | 4 | 10000 | 0 | 0 | 4 | 10000 | 4 | 10000 | 0 | 0% | 0
00470 | D-17 | Precast Concrete Manhole, 60-Inch Diameter | 1 | Each | 4000 |  | 4000 | 1 | 4000 | 0 | 0 | 1 | 4000 | 1 | 4000 | 0 | 0% | 0
00470 | D-18 | Precast Concrete Manhole, 60-Inch Diameter, Type Control Structure | 1 | Each | 4000 |  | 4000 | 1 | 4000 | 0 | 0 | 1 | 4000 | 1 | 4000 | 0 | 0% | 0
00470 | D-19 | Trench Drain | 12 | Each | 200 |  | 2400 | 12 | 2400 | 0 | 0 | 12 | 2400 | 12 | 2400 | 0 | 0% | 0
00470 | D-20 | Gravel Sump | 1 | Each | 300 |  | 300 | 1 | 300 | 0 | 0 | 1 | 300 | 1 | 300 | 0 | 0% | 0
00510 | D-21 | Structure Excavation | 1 | LS | 1000 |  | 1000 | 1 | 1000 | 0 | 0 | 1 | 1000 | 1 | 1000 | 0 | 0% | 0
00510 | D-22 | Shoring, Cribbing, Etc. | 1 | LS | 5000 |  | 5000 | 1 | 5000 | 0 | 0 | 1 | 5000 | 1 | 5000 | 0 | 0% | 0
00510 | D-23 | Granular Wall Backfill | 142 | C.Y. | 30 |  | 4260 | 118.4 | 3552 | 0 | 0 | 118.4 | 3552 | 118.4 | 3552 | 0 | 0% | 0
00530 | D-24 | Reinforcement | 1 | LS | 36000 |  | 36000 | 1 | 36000 | 0 | 0 | 1 | 36000 | 1 | 36000 | 0 | 0% | 0
00540 | D-25 | Structural Concrete, Class 3300 (Class 25-37.5) | 1 | LS | 95000 |  | 95000 | 1 | 95000 | 0 | 0 | 1 | 95000 | 1 | 95000 | 0 | 0% | 0
00540 | D-26 | Structural Concrete, Class 4000 (Class 30-19) | 1 | LS | 160000 |  | 160000 | 1 | 160000 | 0 | 0 | 1 | 160000 | 1 | 160000 | 0 | 0% | 0
00560 | D-27 | Structural Steel | 1 | LS | 500000 |  | 500000 | 1 | 500000 | 0 | 0 | 1 | 500000 | 1 | 500000 | 0 | 0% | 0
00560 | D-28 | Wire Mesh Panels | 3240 | S.F. | 15 |  | 48600 | 2893.9 | 43408.5 | 0 | 0 | 2893.9 | 43408.5 | 2893.9 | 43408.5 | 0 | 0% | 0
00560 | D-29 | Sewer Crossing Screen | 1453 | S.F. | 23 |  | 33419 | 1216.81 | 27986.63 | 0 | 0 | 1216.81 | 27986.63 | 1216.81 | 27986.63 | 0 | 0% | 0
00560 | D-30 | Sewer Crossing Hood | 410 | S.F. | 28 |  | 11480 | 375.28 | 10507.84 | 0 | 0 | 375.28 | 10507.84 | 375.28 | 10507.84 | 0 | 0% | 0
00561 | D-31 | Eastbank Manual Gates | 1 | L.S. | 7500 |  | 7500 | 1 | 7500 | 0 | 0 | 1 | 7500 | 1 | 7500 | 0 | 0% | 0
00585 | D-32 | Compression Joint Seal | 1 | L.S. | 800 |  | 800 | 1 | 800 | 0 | 0 | 1 | 800 | 1 | 800 | 0 | 0% | 0
00596 | D-33 | Retaining Wall, Cast-in-Place Concrete | 442 | S.F. | 40 |  | 17680 | 480 | 19200 | 0 | 0 | 480 | 19200 | 480 | 19200 | 0 | 0% | 0
00596 | D-34 | Retaining Wall, MSE. | 16130 | S.F. | 25 |  | 403250 | 16428 | 410700 | 0 | 0 | 16428 | 410700 | 16428 | 410700 | 0 | 0% | 0
00596 | D-35 | MSE Coping | 1052 | L.F. | 85 |  | 89420 | 1074.7 | 91349.5 | 0 | 0 | 1074.7 | 91349.5 | 1074.7 | 91349.5 | 0 | 0% | 0
River Access and Transportation, Phase I | [15 empty] | Page No. |  | 4
Steel Bridge Pedestrian and Bicycle Crossing | [15 empty] | Contract No. |  | 32854
Final Estimate | [15 empty] | Ordinance No. |  | 174096
[16 empty] | Project No. |  | 03547
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
00599 | D-36 | Concrete Slope Paving | 3430 | S.F. | 13 |  | 44590 | 4352.5 | 56582.5 | 0 | 0 | 4352.5 | 56582.5 | 4352.5 | 56582.5 | 0 | 0% | 0
00599 | D-37 | Slope Paving Curbs | 825 | L.F. | 31 |  | 25575 | 986.4 | 30578.4 | 0 | 0 | 986.4 | 30578.4 | 986.4 | 30578.4 | 0 | 0% | 0
00641 | D-38 | Aggregate Base, 4-Inches Thick | 1096 | S.Y. | 18 |  | 19728 | 2489.1 | 44803.8 | 0 | 0 | 2489.1 | 44803.8 | 2489.1 | 44803.8 | 0 | 0% | 0
00759 | D-39 | 4-inch Concrete Surfacing | 1497 | S.Y. | 34 |  | 50898 | 1243.5 | 42279 | 0 | 0 | 1243.5 | 42279 | 1243.5 | 42279 | 0 | 0% | 0
00759 | D-40 | 6-inch Concrete Surfacing | 925 | S.Y. | 40 |  | 37000 | 1097.6 | 43904 | 0 | 0 | 1097.6 | 43904 | 1097.6 | 43904 | 0 | 0% | 0
00759 | D-41 | Concrete Seatwalls | 283 | L.F. | 138 |  | 39054 | 290.5 | 40089 | 0 | 0 | 290.5 | 40089 | 290.5 | 40089 | 0 | 0% | 0
00759 | D-42 | Concrete Amphitheatre Seating | 25 | C.Y. | 550 |  | 13750 | 28.5 | 15675 | 0 | 0 | 28.5 | 15675 | 28.5 | 15675 | 0 | 0% | 0
00759 | D-43 | Concrete Stairs | 34 | C.Y. | 525 |  | 17850 | 38.6 | 20265 | 0 | 0 | 38.6 | 20265 | 38.6 | 20265 | 0 | 0% | 0
00759 | D-44 | Grass-Crete Pavers | 153 | S.F. | 5 |  | 765 | 134.3 | 671.5 | 0 | 0 | 134.3 | 671.5 | 134.3 | 671.5 | 0 | 0% | 0
00759 | D-45 | Mile Marker Obelisk Foundation | 1 | Each | 2500 |  | 2500 | 1 | 2500 | 0 | 0 | 1 | 2500 | 1 | 2500 | 0 | 0% | 0
00812 | D-46 | Guardrail Type 1 with Handrail | 1405 | L.F. | 115 |  | 161575 | 1396.06 | 160546.9 | 0.86 | 98.9 | 1395.2 | 160448 | 1396.06 | 160546.9 | 0 | 0% | 0
00812 | D-47 | Guardrail Type 2 | 635 | L.F. | 115 |  | 73025 | 610.7 | 70230.5 | -0.05 | -5.75 | 610.75 | 70236.25 | 610.7 | 70230.5 | 0 | 0% | 0
00812 | D-48 | Guardrail Type 3 | 190 | L.F. | 45 |  | 8550 | 183.6 | 8262 | -0.2 | -9 | 183.8 | 8271 | 183.6 | 8262 | 0 | 0% | 0
00812 | D-49 | Guardrail Type 3 with Handrail | 12 | L.F. | 95 |  | 1140 | 14.05 | 1334.75 | -0.12 | -11.4 | 14.17 | 1346.15 | 14.05 | 1334.75 | 0 | 0% | 0
00812 | D-50 | Continuous Handrail | 119 | L.F. | 35 |  | 4165 | 168.25 | 5888.75 | 0 | 0 | 168.25 | 5888.75 | 168.25 | 5888.75 | 0 | 0% | 0
00940 | D-51 | Permanent Signs in Place | 100 | S.F. | 28 |  | 2800 | 43.2221 | 1210.22 | 0 | 0 | 43.2221 | 1210.22 | 43.2221 | 1210.22 | 0 | 0% | 0
01010 | D-52 | Topsoil | 743 | C.Y. | 30 |  | 22290 | 721.5 | 21645 | 0 | 0 | 721.5 | 21645 | 721.5 | 21645 | 0 | 0% | 0
01025 | D-53 | Plant Seeding, Mix No.1 | 0.5 | Acre | 8000 |  | 4000 | 0.19 | 1520 | 0 | 0 | 0.19 | 1520 | 0.19 | 1520 | 0 | 0% | 0
01040 | D-54 | Bark Mulch | 370 | C.Y. | 32 |  | 11840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
01040 | D-55 | Deciduous Trees (4-4 1/2" cal.) | 21 | Each | 850 |  | 17850 | 21 | 17850 | 0 | 0 | 21 | 17850 | 21 | 17850 | 0 | 0% | 0
01040 | D-56 | Deciduous Trees (3" cal.) | 68 | Each | 445 |  | 30260 | 65 | 28925 | 0 | 0 | 65 | 28925 | 65 | 28925 | 0 | 0% | 0
01040 | D-57 | Deciduous Trees (6-8' ht.) | 13 | Each | 75 |  | 975 | 13 | 975 | 0 | 0 | 13 | 975 | 13 | 975 | 0 | 0% | 0
01040 | D-58 | Evergreen Trees (8-10' ht.) | 8 | Each | 150 |  | 1200 | 8 | 1200 | 0 | 0 | 8 | 1200 | 8 | 1200 | 0 | 0% | 0
01040 | D-59 | Shrubs (# 2 cont.) | 914 | Each | 15 |  | 13710 | 949 | 14235 | 0 | 0 | 949 | 14235 | 949 | 14235 | 0 | 0% | 0
01040 | D-60 | Deciduous Shrubs (1-2' ht.) | 753 | Each | 7 |  | 5271 | 842 | 5894 | 0 | 0 | 842 | 5894 | 842 | 5894 | 0 | 0% | 0
01040 | D-61 | Deciduous Shrubs (3-4' ht.) | 573 | Each | 15 |  | 8595 | 612 | 9180 | 0 | 0 | 612 | 9180 | 612 | 9180 | 0 | 0% | 0
01040 | D-62 | Groundcover (#1 cont.) | 795 | Each | 7 |  | 5565 | 883 | 6181 | 0 | 0 | 883 | 6181 | 883 | 6181 | 0 | 0% | 0
01050 | D-63 | Black Vinyl Coated Chain Link Fence - 4' High | 28 | L.F. | 75 |  | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
01050 | D-64 | 8' Chain Link Fence and 12' Wide Gate | 40 | L.F. | 90 |  | 3600 | 41.9 | 3771 | 0 | 0 | 41.9 | 3771 | 41.9 | 3771 | 0 | 0% | 0
01090 | D-65 | Gravel Strip | 153 | C.Y. | 35 |  | 5355 | 48.2 | 1687 | 0 | 0 | 48.2 | 1687 | 48.2 | 1687 | 0 | 0% | 0
01090 | D-66 | River Rock Strip | 20 | C.Y. | 50 |  | 1000 | 28.1 | 1405 | 0 | 0 | 28.1 | 1405 | 28.1 | 1405 | 0 | 0% | 0
01092 | D-67 | Skateblock | 70 | Each | 35 |  | 2450 | 72 | 2520 | 0 | 0 | 72 | 2520 | 72 | 2520 | 0 | 0% | 0
01220 | D-68 | Irrigation System | 1 | L.S. | 36000 |  | 36000 | 1 | 36000 | 0 | 0 | 1 | 36000 | 1 | 36000 | 0 | 0% | 0
01401 | D-69 | Electrical Work | 1 | L.S. | 370000 |  | 370000 | 1 | 370000 | 0 | 0 | 1 | 370000 | 1 | 370000 | 0 | 0% | 0
01412 | D-70 | Utility Vault 264-TA | 2 | Each | 3500 |  | 7000 | 2 | 7000 | 0 | 0 | 2 | 7000 | 2 | 7000 | 0 | 0% | 0
01412 | D-71 | One-Way Utility Conduit | 680 | L.F. | 12.5 |  | 8500 | 618.4 | 7730 | 0 | 0 | 618.4 | 7730 | 618.4 | 7730 | 0 | 0% | 0
00280 | D-72 | Erosion Control Matting | 4000 | S.Y. | 3.5 |  | 14000 | 3388 | 11858 | 0 | 0 | 3388 | 11858 | 3388 | 11858 | 0 | 0% | 0
-56087.51
Total Schedule D - Eastbank Connection | [6 empty] | 2792470 | 97.99% | 2736382.49 |  | 72.75 |  | 2736309.74 |  | 2736382.49 |  | 0% | 0
River Access and Transportation, Phase I | [15 empty] | Page No. |  | 5
Steel Bridge Pedestrian and Bicycle Crossing | [15 empty] | Contract No. |  | 32854
Final Estimate | [15 empty] | Ordinance No. |  | 174096
[16 empty] | Project No. |  | 03547
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Schedule F - Custom Hinged Light and Signal Pole Bases
113.02 | F-1 | Custom Hinged Light and Signal Pole Bases | 1 | L.S. | 12000 |  | 12000 | 1 | 12000 | 0 | 0 | 1 | 12000 | 1 | 12000 | 0 | 0% | 0
Total Schedule F- Custom Hinged Light and Signal Pole Bases | [6 empty] | 12000 |  | 12000 |  | 0 |  | 12000 |  | 12000 |  |  | 0
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total Outstanding Advances |  | Amount Advanced and later deducted
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Materials on Hand
00000 | M-1 | Seco Inv. 6501 - Aluminum Plate | 1 | L.S. | 90540 |  | 90540 | 1 | 90540 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 90540
00000 | M-2 | Foster-Geotech MSE Panels | 5923 | S.F. | 9.05 |  | 53603.15 | 5923 | 53603.15 | 0 | 0 | 0 | 0 | 0 | 0 | 5923 | 100% | 53603.15
00000 | M-3 | Seco Inv. 6501 - Ped Bridge & Mesh | 1 | L.S. | 180462 |  | 180462 | 1 | 180462 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 180462
00000 | M-4 | Seco Inv. 6525 - Structural Steel | 1 | L.S. | 257061.3 |  | 257061.3 | 1 | 257061.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 257061.3
00000 | M-5 | Pro Landscape Invoice Dated 8-16-2000 | 1 | L.S. | 2539 |  | 2539 | 1 | 2539 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 2539
00000 | M-6 | Pro Landscape Invoice Dated 8-22-2000 | 1 | L.S. | 5286 |  | 5286 | 1 | 5286 | 0 | 0 | -5.5511e-17 | -2.9343e-13 | -5.5511e-17 | -2.9343e-13 | 1 | 100% | 5286
00000 | M-7 | Seco Inv. 6520 - Structural Steel | 1 | L.S. | 191177 |  | 191177 | 1 | 191177 | 0 | 0 | -5.5511e-17 | -1.0612e-11 | -5.5511e-17 | -1.0612e-11 | 1 | 100% | 191177
00000 | M-8 | Foster-Geotech MSE Panels | 9898.57 | S.F. | 5.3028 |  | 52490 | 9898.57 | 52490 | 0 | 0 | 0 | 0 | 0 | 0 | 9898.57 | 100% | 52490
00000 | M-9 | Pro Landscape Invoice # 15793 submitted 9/29/00 | 1 | L.S. | 9966 |  | 9966 | 1 | 9966 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 9966
00000 | M-10 | Pro Landscape Inv 15873 submitted 10/25/00 | 1 | L.S. | 6120 |  | 6120 | 1 | 6120 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 6120
00000 | M-11 | Seco Inv. 6550 - Bid Items D46 & D47 | 1 | L.S. | 128000 |  | 128000 | 1 | 128000 | 0 | 0 | 8.3267e-17 | 1.0658e-11 | 8.3267e-17 | 1.0658e-11 | 1 | 100% | 128000
00000 | M-12 | LB Foster Invoice No. 40031 | 1 | L.S. | 112373.52 |  | 112373.52 | 1 | 112373.52 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 112373.52
00000 | M-13 | Seco Inv. 6567 - Bid Items C10, D46-47 | 1 | L.S. | 37110 |  | 37110 | 1 | 37110 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 37110
00000 | M-14 | Seco Inv. 6577 - Bid Items C10 & D46 | 1 | L.S. | 28500 |  | 28500 | 1 | 28500 | 0 | 0 | 4.1633e-17 | 1.1866e-12 | 4.1633e-17 | 1.1866e-12 | 1 | 100% | 28500
Total for Materials on Hand |  |  |  |  | 18.75% |  | 1155227.97 |  | 1155227.97 |  | 0 |  | 9.388e-13 | 8.127e-17% | 9.388e-13 |  | 100% | 1155227.97
River Access and Transportation, Phase I | [15 empty] | Page No. |  | 6
Steel Bridge Pedestrian and Bicycle Crossing | [15 empty] | Contract No. |  | 32854
Final Estimate | [15 empty] | Ordinance No. |  | 174096
[16 empty] | Project No. |  | 03547
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Change Orders
00000 | CO-1 | City Furnished Staging Yard Illumination Materials | 1 | L.S. | -1098.35 |  | -1098.35 | 1 | -1098.35 | 0 | 0 | 1 | -1098.35 | 1 | -1098.35 | 0 | 0% | 0
00000 | CO-2 | Improve Stark Street construction access route | 1 | L.S. | 1536 |  | 1536 | 1 | 1536 | 0 | 0 | 1 | 1536 | 1 | 1536 | 0 | 0% | 0
00000 | CO-3 | Remove off-site and legally dispose of unforeseen concrete and other non-native debris from stockpile | 1 | L.S. | 3195 |  | 3195 | 1 | 3195 | 0 | 0 | 1 | 3195 | 1 | 3195 | 0 | 0% | 0
00000 | CO-4 | Owner Furnished Twin Ornamental | 1 | L.S. | -3850 | -3850 | -3850 | 1 | -3850 | 0 | 0 | 1 | -3850 | 1 | -3850 | 0 | 0% | 0
00000 | CO-5 | Curb Removal at Westbank | 1 | L.S. | 245.4 | 245.4 | 245.4 | 1 | 245.4 | 0 | 0 | 1 | 245.4 | 1 | 245.4 | 0 | 0% | 0
00000 | CO-6 | Overexcavation at Westbank | 1 | L.S. | 730 | 730 | 730 | 1 | 730 | 0 | 0 | 1 | 730 | 1 | 730 | 0 | 0% | 0
00000 | CO-7 | Owner Furnished Single Ornamental | 1 | L.S. | -1700 | -1700 | -1700 | 1 | -1700 | 0 | 0 | 1 | -1700 | 1 | -1700 | 0 | 0% | 0
00000 | CO-8 | Steel Bridge Chain Link Fence 4' instead of 6' | 1 | L.S. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0% | 0
00000 | CO-9 | Temporary Aggregate at Westbank for Rose Festival | 1 | L.S. | 1655.55 | 1655.55 | 1655.55 | 1 | 1655.55 | 0 | 0 | 1 | 1655.55 | 1 | 1655.55 | 0 | 0% | 0
00000 | CO-10 | Temporary Concrete Barriers at Eastbank | 1 | L.S. | 6400 | 6400 | 6400 | 1 | 6400 | 0 | 0 | 1 | 6400 | 1 | 6400 | 0 | 0% | 0
00000 | CO-11 | 2" Deep Grass Mulch at Eastbank | 1 | L.S. | 3800 | 3800 | 3800 | 1 | 3800 | 0 | 0 | 1 | 3800 | 1 | 3800 | 0 | 0% | 0
00000 | CO-12 | Temporary 6' Fence at Eastbank | 1 | L.S. | 593.77 | 593.77 | 593.77 | 1 | 593.77 | 0 | 0 | 1 | 593.77 | 1 | 593.77 | 0 | 0% | 0
00000 | CO-13 | Schedule 40 PVC Laterals | 1 | L.S. | 1570.08 | 1570.08 | 1570.08 | 1 | 1570.08 | 0 | 0 | 1 | 1570.08 | 1 | 1570.08 | 0 | 0% | 0
00000 | CO-14 | Subexcavation and Backfill at MSE Wall K | 1 | L.S. | 8530.61 | 8530.61 | 8530.61 | 1 | 8530.61 | 0 | 0 | 1 | 8530.61 | 1 | 8530.61 | 0 | 0% | 0
00000 | CO-15 | Granular MSE Wall Backfill instead of Existing Borrow | 550 | C.Y. | 27 | 14850 | 14850 | 550.3 | 14858.1 | 0 | 0 | 550.3 | 14858.1 | 550.3 | 14858.1 | 0 | 0% | 0
00000 | CO-16 | Revised MCI WorldCom Conduits From Schedule 80 PVC to Schedule 40 | 1 | L.S. | -779.31 | -779.31 | -779.31 | 1 | -779.31 | 0 | 0 | 1 | -779.31 | 1 | -779.31 | 0 | 0% | 0
0000 | CO-17 | Structural Backfill Between UPRR Overcrossing Bent 2 & 3 | 700 | C.Y. | 27 | 18900 | 18900 | 411.2 | 11102.4 | 0 | 0 | 411.2 | 11102.4 | 411.2 | 11102.4 | 0 | 0% | 0
0000 | CO-18 | UPRR Overcrossing Detail Changes | 1 | L.S. | 1091.48 | 1091.48 | 1091.48 | 1 | 1091.48 | 0 | 0 | 1 | 1091.48 | 1 | 1091.48 | 0 | 0% | 0
0000 | CO-19 | Add Trim Angles at 2" Conc. Filled Deck Panels | 1 | L.S. | 9063 | 9063 | 9063 | 1 | 9063 | 0 | 0 | 1 | 9063 | 1 | 9063 | 0 | 0% | 0
0000 | CO-20 | UPRR Overcrossing Bent 2 Rebar Conflict at Hammerhead | 1 | L.S. | 2570.73 | 2570.73 | 2570.73 | 1 | 2570.73 | 0 | 0 | 1 | 2570.73 | 1 | 2570.73 | 0 | 0% | 0
00000 | CO-21 | Medium Grade Bark Mulch (Hemlock) | 370 | C.Y. | 40 | 14800 | 14800 | 368.75 | 14750 | 0 | 0 | 368.75 | 14750 | 368.75 | 14750 | 0 | 0% | 0
00000 | CO-22 | High Voltage Raceway Revision | 1 | L.S. | -11427.62 | -11427.62 | -11427.62 | 1 | -11427.62 | 0 | 0 | 1 | -11427.62 | 1 | -11427.62 | 0 | 0% | 0
0000 | CO-23 | Delete Seal Welds | 1 | L.S. | -3500 | -3500 | -3500 | 1 | -3500 | 0 | 0 | 1 | -3500 | 1 | -3500 | 0 | 0% | 0
0000 | CO-24 | MSE Wall "B" Footing Survey error Correction | 1 | L.S. | 237.21 | 237.21 | 237.21 | 1 | 237.21 | 0 | 0 | 1 | 237.21 | 1 | 237.21 | 0 | 0% | 0
0000 | CO-25 | Lower UPRR Steel Bridge Domestic Water Supply Line | 1 | L.S. | 721.97 | 721.97 | 721.97 | 1 | 721.97 | 0 | 0 | 1 | 721.97 | 1 | 721.97 | 0 | 0% | 0
00000 | CO-26 | Anti-graffiti coating at slope pavers | 4200 | S.F. | 1.16 | 4872 | 4872 | 4331.5 | 5024.54 | 0 | 0 | 4331.5 | 5024.54 | 4331.5 | 5024.54 | 0 | 0% | 0
0000 | CO-27 | 8-inch ADS N-12 Storm Sewer Pipe ($5 per LF Savings from BI-D11) | 370 | L.F. | 55.5 | 20535 | 20535 | 457.2 | 25374.6 | 0 | 0 | 457.2 | 25374.6 | 457.2 | 25374.6 | 0 | 0% | 0
0000 | CO-28 | MSE Wall and Related Item Acceleration | 1 | L.S. | 24154.2 | 24154.2 | 24154.2 | 41.4% | 10000.6675 | 0% | 0 | 0.41403 | 10000.6675 | 0.41403 | 10000.6675 | 0 | 0% | 0
0000 | CO-29 | Revision to Steel Bridge Walkway Brackets D & E (angles) | 1 | L.S. | 2226 | 2226 | 2226 | 1 | 2226 | 0 | 0 | 1 | 2226 | 1 | 2226 | 0 | 0% | 0
0000 | CO-30 | Revision to Steel Bridge Walkway Brackets D & E (bolts) | 1 | L.S. | 2171.33 | 2171.33 | 2171.33 | 1 | 2171.33 | 0 | 0 | 1 | 2171.33 | 1 | 2171.33 | 0 | 0% | 0
River Access and Transportation, Phase I | [15 empty] | Page No. |  | 7
Steel Bridge Pedestrian and Bicycle Crossing | [15 empty] | Contract No. |  | 32854
Final Estimate | [15 empty] | Ordinance No. |  | 174096
[16 empty] | Project No. |  | 03547
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Change Orders
0000 | CO-31 | Delete Fabric Around Storm Water Pipe Located in MSE Wall Backfill | 1 | L.S. | -500 |  | -500 | 1 | -500 | 0 | 0 | 1 | -500 | 1 | -500 | 0 | 0% | 0
0000 | CO-32 | Furnish and Install Quazite Electrical Junction Boxes instead of OZ Gedney | 1 | L.S. | -6804.6 |  | -6804.6 | 1 | -6804.6 | 0 | 0 | 1 | -6804.6 | 1 | -6804.6 | 0 | 0% | 0
0000 | CO-33 | Delete Installation of DTI Washers on the Steel Bridge | 1 | L.S. | -750 |  | -750 | 1 | -750 | 0 | 0 | 1 | -750 | 1 | -750 | 0 | 0% | 0
0000 | CO34A | Installation of CCTV Items per RFP No. 12 | 1 | L.S. | 24119.21 | 24119.21 | 24119.21 | 1 | 24119.21 | 0 | 0 | 1 | 24119.21 | 1 | 24119.21 | 0 | 0% | 0
0000 | CO34B | Steel Bridge Upper Deck Lane Closures for Installation of Owner Furnished Coaxial | 4 | EA | 500 | 2000 | 2000 | 4 | 2000 | 0 | 0 | 4 | 2000 | 4 | 2000 | 0 | 0% | 0
0000 | CO-35 | Schedule 80 PVC Unions on each side of Irrigation Zone Valves A1 to A17 | 1 | L.S. | 2127.19 | 2127.19 | 2127.19 | 1 | 2127.19 | 0.00017394 | 0.37 | 0.99983 | 2126.82 | 1 | 2127.19 | 0 | 0% | 0
00000 | CO-36 | Replacement Steel Bridge Pier Anchors | 1 | L.S. | 6506.75 | 6506.75 | 6506.75 | 1 | 6506.75 | 0 | 0 | 1 | 6506.75 | 1 | 6506.75 | 0 | 0% | 0
00000 | CO-37 | Supplemental Reinforcing Steel at Trench Drain 17 and 19 | 1 | L.S. | 350 | 350 | 350 | 1 | 350 | 0 | 0 | 1 | 350 | 1 | 350 | 0 | 0% | 0
00000 | CO-38 | Overlook Stair Modifications at Upper Landing | 1 | L.S. | 1523.81 | 1523.81 | 1523.81 | 1 | 1523.81 | 0 | 0 | 1 | 1523.81 | 1 | 1523.81 | 0 | 0% | 0
00000 | CO-39 | Signal, CCTV and Light Pole Support Bracket Modifications | 1 | L.S. | 1997.31 | 1997.31 | 1997.31 | 1 | 1997.31 | 0 | 0 | 1 | 1997.31 | 1 | 1997.31 | 0 | 0% | 0
0000 | CO-40 | Relocate Southern MCI Manhole 165' south | 1 | L.S. | 6794.58 | 6794.58 | 6794.58 | 1 | 6794.58 | 0 | 0 | 1 | 6794.58 | 1 | 6794.58 | 0 | 0% | 0
00000 | CO-41 | Lower HV Power Line by Retaining Wall "A" | 1 | L.S. | 2294.65 | 2294.65 | 2294.65 | 1 | 2294.65 | 0 | 0 | 1 | 2294.65 | 1 | 2294.65 | 0 | 0% | 0
00000 | CO-42 | Stair Conflict Modification | 1 | L.S. | 5209.69 | 5209.69 | 5209.69 | 1 | 5209.69 | 0 | 0 | 1 | 5209.69 | 1 | 5209.69 | 0 | 0% | 0
00000 | CO-43 | Dedicated Power for CCTV Life Safety Monitoring Equipment | 1 | L.S. | 1238.04 | 1238.04 | 1238.04 | 1 | 1238.04 | 0 | 0 | 1 | 1238.04 | 1 | 1238.04 | 0 | 0% | 0
00000 | CO-44 | Revise Electrical Panel Board "M" to a GE Type | 1 | L.S. | 1329.09 | 1329.09 | 1329.09 | 1 | 1329.09 | 0 | 0 | 1 | 1329.09 | 1 | 1329.09 | 0 | 0% | 0
00000 | CO-45 | Furnish and install ballast rock between easternmost UPRR track and Overlook slope | 1 | L.S. | 1918.89 | 1918.89 | 1918.89 | 1 | 1918.89 | 0 | 0 | 1 | 1918.89 | 1 | 1918.89 | 0 | 0% | 0
00000 | CO-46 | Re-engineer MSE retaining wall "B" to accommodate revised station per RFI 39 | 1 | L.S. | 5905 | 5905 | 5905 | 1 | 5905 | 0 | 0 | 1 | 5905 | 1 | 5905 | 0 | 0% | 0
00000 | CO-47 | Revise PLC to GE VersaMax Micro type | 1 | L.S. | 956.34 | 956.34 | 956.34 | 1 | 956.34 | 0 | 0 | 1 | 956.34 | 1 | 956.34 | 0 | 0% | 0
0000 | CO-48 | Revise framing and harbor wall connection detail at west approach span | 1 | L.S. | 1610 | 1610 | 1610 | 1 | 1610 | 0 | 0 | 1 | 1610 | 1 | 1610 | 0 | 0% | 0
0000 | CO-49 | Expansion Joint Credit | 218 | L.F. | -3.75 | -817.5 | -817.5 | 218 | -817.5 | 0 | 0 | 218 | -817.5 | 218 | -817.5 | 0 | 0% | 0
00000 | CO-50 | Lift Span Life Safety Electrical Modifications | 1 | L.S. | 9325.7 | 9325.7 | 9325.7 | 1 | 9325.7 | 0 | 0 | 1 | 9325.7 | 1 | 9325.7 | 0 | 0% | 0
River Access and Transportation, Phase I | [15 empty] | Page No. |  | 8
Steel Bridge Pedestrian and Bicycle Crossing | [15 empty] | Contract No. |  | 32854
Final Estimate | [15 empty] | Ordinance No. |  | 174096
[16 empty] | Project No. |  | 03547
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Change Orders
00000 | CO51A | Vibration Isolation at Lift Span Electrical | 1 | L.S. | 2349.54 |  | 2349.54 | 1 | 2349.54 | 0 | 0 | 1 | 2349.54 | 1 | 2349.54 | 0 | 0% | 0
00000 | CO51B | Ventilation Louvers at Lift Span Un-interruptible Power Supply Enclosure | 1 | L.S. | 545.01 |  | 545.01 | 1 | 545.01 | 0 | 0 | 1 | 545.01 | 1 | 545.01 | 0 | 0% | 0
00000 | CO52A | Lift Span Navigation Light and Access Platform Modifications | 1 | L.S. | 2123.62 |  | 2123.62 | 1 | 2123.62 | 0 | 0 | 1 | 2123.62 | 1 | 2123.62 | 0 | 0% | 0
00000 | CO52B | Delete Removal of South Side Lift Span Navigation Light Access Platform (C-3) | 1 | L.S. | -500 |  | -500 | 1 | -500 | 0 | 0 | 1 | -500 | 1 | -500 | 0 | 0% | 0
00000 | CO-53 | UPRR Overcrossing Luminaire and Protection Cage Modifications | 1 | L.S. | 3791.85 |  | 3791.85 | 1 | 3791.85 | 0 | 0 | 1 | 3791.85 | 1 | 3791.85 | 0 | 0% | 0
00000 | CO-54 | Modify Grate Elevation at CB 6 from 32.96 to read 32.26 | 1 | L.S. | 354.67 | 354.67 | 354.67 | 1 | 354.67 | 0 | 0 | 1 | 354.67 | 1 | 354.67 | 0 | 0% | 0
00000 | CO-55 | Overlook Stair Modifications and Minor Related Items | 1 | L.S. | 6895.58 | 6895.58 | 6895.58 | 1 | 6895.58 | 0 | 0 | 1 | 6895.58 | 1 | 6895.58 | 0 | 0% | 0
00000 | CO-56 | Revise Quick Coupler in OZ Gedney Box to a Zurn Ground Hydrant | 1 | L.S. | -650 | -650 | -650 | 1 | -650 | 0 | 0 | 1 | -650 | 1 | -650 | 0 | 0% | 0
00000 | CO-57 | Rebar at Western Edge of Lower Ramp Curb/Thickened Edge from Station 10+04 to 11+00 | 1 | L.S. | 384.12 | 384.12 | 384.12 | 1 | 384.12 | 0 | 0 | 1 | 384.12 | 1 | 384.12 | 0 | 0% | 0
00000 | CO-58 | Black Vinyl Coated Chain Link Fence - 4' high ($40/LF Savings from BI D63) | 92 | L.F. | 35 | 3220 | 3220 | 88.6 | 3101 | 0 | 0 | 88.6 | 3101 | 88.6 | 3101 | 0 | 0% | 0
00000 | CO-59 | Fuses, holders, and insulating boots at Holophane and Spectra fixtures | 1 | L.S. | 4674.74 | 4674.74 | 4674.74 | 1 | 4674.74 | 0 | 0 | 1 | 4674.74 | 1 | 4674.74 | 0 | 0% | 0
00000 | CO-60 | Correct Survey Error at MSE Walls B, E, and H Coping | 1 | L.S. | 53682.24 | 53682.24 | 53682.24 | 1 | 53682.24 | 0 | 0 | 1 | 53682.24 | 1 | 53682.24 | 0 | 0% | 0
00000 | CO-61 | Maintenance Access Road Revisions and Landscape | 1 | L.S. | 6747.04 | 6747.04 | 6747.04 | 1 | 6747.04 | 0 | 0 | 1 | 6747.04 | 1 | 6747.04 | 0 | 0% | 0
00000 | CO-62 | Remove four luminaire protective cages at UPRR Overcrossing Structure | 1 | L.S. | 1409.33 | 1409.33 | 1409.33 | 1 | 1409.33 | 0 | 0 | 1 | 1409.33 | 1 | 1409.33 | 0 | 0% | 0
00000 | CO-63 | Furnish and install 4 bollards adjacent to the transformer and power distribution panel | 1 | L.S. | 876 | 876 | 876 | 1 | 876 | 0 | 0 | 1 | 876 | 1 | 876 | 0 | 0% | 0
00000 | CO-64 | Furnish and install one LID plaque pedestal and 2 Owner furnished LID plaques | 1 | L.S. | 1000 | 1000 | 1000 | 1 | 1000 | 0 | 0 | 1 | 1000 | 1 | 1000 | 0 | 0% | 0
00000 | CO-65 | Furnish and install lift span limit switch and Steel Bridge | 1 | L.S. | 597.69 | 597.69 | 597.69 | 1 | 597.69 | 0 | 0 | 1 | 597.69 | 1 | 597.69 | 0 | 0% | 0
00000 | CO-66 | Pressure sewer crossing hood and in-fill panel revisions | 1 | L.S. | 6631.06 | 6631.06 | 6631.06 | 1 | 6631.06 | 0 | 0 | 1 | 6631.06 | 1 | 6631.06 | 0 | 0% | 0
00000 | CO-67 | Supplemental lift span walkway luminaires | 1 | L.S. | 5726.24 | 5726.24 | 5726.24 | 1 | 5726.24 | 0 | 0 | 1 | 5726.24 | 1 | 5726.24 | 0 | 0% | 0
River Access and Transportation, Phase I | [15 empty] | Page No. |  | 9
Steel Bridge Pedestrian and Bicycle Crossing | [15 empty] | Contract No. |  | 32854
Final Estimate | [15 empty] | Ordinance No. |  | 174096
[16 empty] | Project No. |  | 03547
Spec. | Item | Item of Work | Estimated | Unit | Unit Price |  | Estimated | Actual |  | This Request |  | Previous |  | Total to Date |  | Remaining
No. | No. |  | Quantity |  |  |  | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Percent | Amount
Change Orders
00000 | CO-68 | Lift span Life safety equipment modifications | 1 | L.S. | 30508.14 | 30508.14 | 30508.14 | 1 | 30508.14 | 1 | 30508.14 | 0 | 0 | 1 | 30508.14 | 0 | 0% | 0
00000 | CO69R | Overhead protective fence at I-5 to I-84 interchange | 1 | L.S. | 28424.08 | 28424.08 | 28424.08 | 1 | 28424.08 | 1 | 28424.08 | 0 | 0 | 1 | 28424.08 | 0 | 0% | 0
00000 | CO-70 | Staging yard fence modifications | 1 | L.S. | 2000 | 2000 | 2000 | 1 | 2000 | 1 | 2000 | 0 | 0 | 1 | 2000 | 0 | 0% | 0
00000 | CO-71 | Delete custom fence at Steel Bridge signal platforms | 1 | L.S. | -3723 | -3723 | -3723 | 1 | -3723 | 1 | -3723 | 0 | 0 | 1 | -3723 | 0 | 0% | 0
00000 | CO-72 | Extended warranty at Steel Bridge concrete filled grating | 1 | L.S. | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0% | 0
00000 | CO-73 | Lift span flagging and radio modem troubleshooting | 1 | L.S. | 24077 | 24077 | 24077 | 1 | 24077 | 1 | 24077 | 0 | 0 | 1 | 24077 | 0 | 0% | 0
00000 | CO74R | Lift span flagging and release and waiver of all claims arising out of or relating to the Contract | 1 | L.S. | 57000 | 57000 | 57000 | 1 | 57000 | 1 | 57000 | 0 | 0 | 1 | 57000 | 0 | 0% | 0
00000 | CO-75 | Temporary Power Pole Salvage Value Credit | 1 | L.S. | -1307 | -1307 | -1307 | 1 | -1307 | 1 | -1307 | 0 | 0 | 1 | -1307 | 0 | 0% | 0
-17119.8925
Total for Change Orders | [6 empty] | 425266.15 | 95.97% | 408146.2575 |  | 136979.59 |  | 271166.6675 |  | 408146.2575 |  | 0% | 0
River Access and Transportation, Phase I | [15 empty] | Page No. |  | 10
Steel Bridge Pedestrian and Bicycle Crossing | [15 empty] | Contract No. |  | 32854
Final Estimate | [15 empty] | Ordinance No. |  | 174096
[16 empty] | Project No. |  | 03547
Project Cost Summary
Schedule Summary
|  | Total Schedule A - General Requirements, Mobilization and Traffic Control |  |  | 9.24% |  | 13.82% | 907538.01
|  | Total Schedule B - Westbank Connection |  |  | 0.5602% |  | 0.8375% | 55017.72
|  | Total Schedule C - Steel Bridge |  |  | 24.94% |  | 37.29% | 2449830.06
|  | Total Schedule D - Eastbank Connection |  |  | 27.86% |  | 41.66% | 2736382.49
|  | Total Schedule F- Custom Hinged Light and Signal Pole Bases |  |  | 0.1222% |  | 0.1827% | 12000
|  | Total for Change Orders |  |  | 4.156% |  | 6.213% | 408146.2575
|  | Construction Contract Total |  |  | 66.88% |  | 100% |  | 6568914.5375
Engineering and Other Construction Costs
|  | Union Pacific Railroad Costs |  |  | 7.305% |  | 22.06% | 717410
|  | Other Constuction Costs |  |  | 4.001% |  | 12.08% | 392968.09
|  | Design Engineering |  |  | 12.77% |  | 38.57% | 1254362.06
|  | Construction Engineering |  |  | 9.039% |  | 27.3% | 887779.29
|  | Total Engineering and Other Costs |  |  | 33.12% |  | 100% |  | 3252519.44
| Total Project Cost | [7 empty] | 9821433.9775
Project Funding
|  | CMAQ Grant | [5 empty] | 953000
|  | PDOT (Trust & GTR) | [5 empty] | 780000
|  | PDC (includes CMAQ swap) | [5 empty] | 3936000
|  | ODOT | [5 empty] | 500000
|  | Loan for Property Purchase | [5 empty] | 650000
|  | Additional Funds from PDC | [5 empty] | 1000000
|  | Additional Funds from PDOT | [5 empty] | 420000
|  | Additional Funds from HNTB (CO 68) | [5 empty] | 53682.24
|  | Additional Funds from HNTB (CO 73) | [5 empty] | 24077
|  | Additional Funds from Street Lighting (CO 59) | [5 empty] | 4674.74
|  | Total Project Funding | [6 empty] | 8321433.98
|  | Property Owner Assessment | [6 empty] | 1499999.9975
0.0024557
I, Brant Williams, P.E., City Engineer of said City, hereby certify that the above statement and map, show in detail the correct amounts of all work required to complete the improvement under the above named Ordinance.
Approved: ___________________________ Approved: ____________________________
Construction Manager City Engineer
Bureau of Transportation Engineering and Development
Dated: ________ _____ Dated: ____________ __
STATEMENT of the various kinds of work performed in the improvements of
River Access and Transportation, Phase I Steel Bridge Pedestrian and Bicycle Crossing Project
according to the provisions of Ordinance No. 174096