EXHIBIT 2

PROJECT SCHEDULE

OHSU/SOUTH WATERFRONT AERIAL TRAM

DESIGN COMPETITION

PORTLAND AERIAL TRANSPORTATION, INC.

# JANUARY 8, 2003

# Preliminary Competition Schedule

# January 8, 2003

| Event | Date |
| --- | --- |
| Interviews with 7 firms | Dec 5-6 |
| PATI Board decision on final 4 competitors | Jan 3 |
| - Notification of final competitors - Transmittal of competition program and background materials to competitors - Arrange for transmittal of competition fees to competitors | Jan 3-6 |
| Mandatory “pre-competition” field visit Competitors identity “teams” Team briefing on scope of design problem; context | Jan 23-24 |
| Competition begins | Jan 25 |
| - Mandatory Portland Visit – Firm 1 – AIA Lecture | Jan 30 |
| - Mandatory Portland Visit – Firm 2 – AIA Lecture | Feb 6 |
| - Mandatory Portland Visit – Firm 3 – AIA Lecture | Feb 13 |
| - Mandatory Portland Visit – Firm 4 – AIA Lecture | Feb 20 |
| Competitors submit materials | Mar 24 |
| Jury convenes – Competitors presentation; Jury develops recommendation to PATI Board | Mar 28 |
| PATI Board receives recommendation on final team; authorizes transmittal of recommendation to City Council | Apr 2 |
| Presentation to City Council on winning team; request authorization to enter into contract for schematic design | Apr 9 |
| PATI negotiate contract for schematic design with winning team | Apr 10 - 21 |
| Begin Schematic Design Process | May 1 |
| Complete Schematic Designs | Oct 1, 03 |
| Present Schematic Design to Council | Oct 8, 03 |

This will be a two day, extensive briefing of the scope of the design problem and its context.  The briefings will be conducted by PATI officials, City officials, OHSU officials, key property owners, and other individuals.  It is anticipated that there will also be a public information session held during the two days.

Competitors will need to have identified all team members before the January 23-24 field briefing.  However, competitors will not be allowed to add either of the two international tram manufacturers to their teams.  Those companies may be contacted for information but may not be included in any design team.  It is anticipated that PATI will enter into a Construction Management General Contractor (GMGC) contract at the completion of  schematic designs and that the CMGC contractor will bid the subcomponents of the system including the tram hardware to the manufacturers.

The American Institute of Architects is organizing a lecture series around the four competitors.  You will each be asked to do a public lecture in that series.  PATI will reimburse each competitor one plane fare for that event although it is expected that the teams will want to take advantage of this trip to do your own additional research in the community.  PATI does not expect to organize any other formal events during this trip so its literary will be entirely up to the teams.