## Budget
BIKE IMPROVEMENTS INTERSTATE MAX
| BOM Charges | From Conceptual Design Report
1 | Bicycle Blvd Improvements Willamette : Interstate to Denver | 10400
2 | Interstate & Willamette Left-turn
3 | Bicycle lanes on Killingsworth from Interstate to Minnesota | 5100
4 | Bicycle lanes on Portland from Denver to Montana | 162000
4a | Driveway at 1415 N Portland Blvd.
5 | Bike Blvd on Dekum from Denver to Interstate | 6400
6 | Bike Blvd on Buffalo from Denver to Interstate inc improvements to one-block unimproved from Fenwick to Concord | 18600
7 | Improvements to concrete pavement on N Denver from Willamette to Portland | 30000
| NOT-TO-EXCEED BUDGET | 232500

## Todd Update
BIKE IMPROVEMENTS INTERSTATE MAX
| BOM Charges | From Conceptual Design Report | Update 1/2003 | Comments / Status
1 | Bicycle Blvd Improvements Willamette : Interstate to Denver | 10400 | 800 | Estimate is good. Lewis will write a Work Order by February. Work completed by BOM by October.
2 | Interstate & Willamette Left-turn |  |  | Included in I-Max work
3 | Bicycle lanes on Killingsworth from Interstate to Minnesota | 5100 | 20000 | Estimate is good. Lewis will write a Work Order by February. Work completed by BOM by October.
4 | Bicycle lanes on Portland from Denver to Montana | 162000 | 28000 | Estimate is good for signing and striping. Lotvy's curb indentation completed by Trimet. Lewis will write a Work Order by February. Work completed by BOM by October.
4a | Driveway at 1415 N Portland Blvd. |  | 2591.72 | Final project cost shown. Project Complete.
5 | Bike Blvd on Dekum from Denver to Interstate | 6400 | 3000 | Estimate is good. Lewis will write a Work Order by February. Work completed by BOM by October.
6 | Bike Blvd on Buffalo from Denver to Interstate inc improvements to one-block unimproved from Fenwick to Concord | 18600 | 80000 | Todd, Dave Hill, Dick Godfrey, Christine, discussing design solution. Next BOM meeting 1/21/03 to review proposals. Estimate is good at this point. Will prioritize BOM work for this summer, complete by fall 2003 (Sept).
7 | Improvements to concrete pavement on N Denver from Willamette to Portland | 30000 | 17000 | Final project cost shown. Project Complete.
| BUDGET | 232500 | 151391.72 | BOM Charges $32,267 through AP6 FY 02/03
| Overhead |  | 34532.4513
| Total |  | 185924.1713
| Staff Charges | Through AP 6 FY 2003 | Estimate to Complete
| Survey & Design of Buffalo |  | 20000
| Chean | 27.17
| Coleman | 227.02
| Geller | 503.31
| Iwata | 113.71
| Wardrip | 154.05 | 3300
| Wintergreen | 2407.61
|  | 3432.87 | 23300
| Overhead | 783.0376 | 5314.73
| Total | 4215.9076 | 28614.73
| TOTAL STAFF COSTS |  | 32830.6376
TOTAL ESTIMATED BIKE IMPROVEMENTS COSTS (as of Jan. 24th, 2003) |  |  | 218754.809
DRAFT