## Adjustments to Scope
INTERSTATE MAX LIGHT RAIL PROJECT - IGA AMEND #1
Adjustments to Scope
2026-07-28
|  | ITEM | WHO DOES WORK | FINANCIAL RESPONSIBILITY | ESTIMATED EXPENSE | Exhibit
PDOT Staff Hour Changes
|  | Enforcement of onstreet parking restrictions | City | TriMet | 15000 | Exhibit B - Amend 1
|  | Installation of Parking Signage | City | TriMet | 26013 | Exhibit B - Amend 1
|  | Provision of on-staff structural engineer | City | TriMet | 206787 | Exhibit B - Amend 1
|  | Provision of additional project inspector | City | TriMet | 55116 | Exhibit B - Amend 1
|  | Adjustments to costs during design | City | TriMet | -113431 | Exhibit B - Amend 1
|  | Other adjustments to staff time during construction | City | TriMet | -69430 | Exhibit B - Amend 1
|  | Adjustments to costs during start-up | City | TriMet | -7471 | Exhibit B - Amend 1
| PDOT M&S Changes |  |  | TriMet
|  | BOM Electric Shop | City | TriMet | 296595 | Exhibit B - Amend 1
|  | Potholing at Greeley to locate I-5 column ftgs | City | TriMet | 7000 | Exhibit B - Amend 1
|  | Smithson Building building permit charges | City | TriMet | 11802 | Exhibit B - Amend 1
|  | Smithson Field Office fiber optic extension | City | TriMet | 5300 | Exhibit B - Amend 1
|  | Temporary Street Light System | City and PGE | TriMet | 90000 | Exhibit B - Amend 1
| PDOT OH for above changes |  | City | TriMet | 118111 | Exhibit B - Amend 1
|  | TOTAL PDOT CHANGE |  |  | 641392
| Right-of-way Scope of Services adjustment |  | City | TriMet | 6409 | Exhibit B - Amend 1
| Storm/sanitary sewer staff cost increase |  | City | TriMet | 356760 | Exhibit B and D - Amend 1
| TRI-MET/BWW MOU and amendment |  | City and TriMet | TriMet | 1402306 | Exhibit E
| Bike Route Modifications (inc OH) |  | City | TriMet | 232500 | Exhibit F
| Relocate Fire Bureau Cable |  | City | TriMet | 25000 | Exhibit G
| Lower Albina Overcrossing Project |  | TriMet | City | 1552482 | Exhibit J
| Installation of Conduit for Future Fiber Optic |  | TriMet | City | 80482 | Exhibit K

## Summary of Costs
INTERSTATE MAX LIGHT RAIL PROJECT - IGA AMEND #1
Summary of Costs
2026-07-28
|  | Original IGA | IGA with Mod #1 | Change
| PDOT | 2784681 | 3426074.3995 | 641393.3995
| Right-of-Way Acquisition | 56565 | 62974 | 6409
| BES MOU | 184172 | 540932 | 356760
| Parks | 19207 | 19207 | 0
| BWW MOU |  | 1402306 | 1402306
| Bike Route Modifications (inc OH) |  | 232500 | 232500
| Relocate Fire Bureau Cable |  | 25000 | 25000
| TriMet Obligation Total | 3044625 | 5708993.3995 | 2664368.3995
| BES MOU | 1000000 | 1218182 | 218182
| Lower Albina Overcrossing Project |  | 1552482 | 1552482
| Installation of Conduit for Future Fiber Optic |  | 80482 | 80482
| City Obligation Total | 1000000 | 1632964 | 632964