## May 03
Lower Albina Overcrossing IGA Amendment
2003-04-01
Tri-Met Obligations
Tri-Met to Contract with Stacy and Witbeck Inc for construction of Overcrossing. Work consists of:
Const of Bridge & Civil - Mod #9 | 6347062.0766
Const of Raising Interstate - Mod #10 | 2315667.58
OCIP Insurance | 177890.5048
Total Obligation | 8840620.1615
Tri-Met Resources
Tri-Met Direct Contribution | 1973467
FTA Grant | 5314671
PDOT (from LID) | 1552482.1615
Total Resources | 8840620.1615
City Obligations
UPRR Work (Lump Sum + flagging) | 645576.6
Glacier NW Settlement (Lump Sum) | 145000
Utility Relocations | 101482.79
Demo Valvoline Building | 56901
Tucker Property Improvements | 60000
ROW Acquisition | 3814676.39
Design Engineering | 1567042.7
PDOT staff (outside IMAX Staff) Construction Admin | 130745.19
Water by BWW crews | 126941
BWW Engineering | 60705
BES Engineering | 37711.32
CH2M Construction Services | 357154.64
Misc Consultants | 180185.76
DEQ | 11336.07
Auditor Fee's | 18946.5
Valvoline Assessment | 6434.95
Contingency | 24867.9285
Total Obligation | 7345707.8385
City Resources
FHWA Design Grant | 600000
ODOT Rail Funds | 600000
UPRR | 1065000
SDC | 2537000
LID | 2222517.8385
BWW for Water Line | 295710
BES for Sewer | 25480
Total Resources | 7345707.8385

## Feb 03
Lower Albina Overcrossing IGA Amendment
2003-02-01
Tri-Met Obligations
Tri-Met to Contract with Stacey Widbeck for construction of Overcrossing. Work consists of:
Const of Bridge & Civil - Mod #9 | 6347062.0766
Const of Raising Interstate - Mod #10 | 2486251
OCIP Insurance | 114671
Total Obligation | 8947984.0766
Tri-Met Resources
Tri-Met Direct Contribution | 1986251
FTA Grant | 5314671
PDOT (from LID) | 1647062.08
Total Resources | 8947984.08
City Obligations
UPRR Work (Lump Sum + flagging) | 645576.6
Glacier NW Settlement (Lump Sum) | 145000
Utility Relocations | 101482.79
Demo Valvoline Building | 56901
Tucker Property Improvements
ROW Acquisition | 3814676.39
Design Engineering | 1567042.7
PDOT staff (outside IMAX Staff) Construction Admin | 121239.45
Water by BWW crews | 126941
BWW Engineering | 60705
BES Engineering | 37711.32
CH2M Construction Services | 357154.64
Misc Consultants | 167285.76
DEQ | 11632.22
Auditor Fee's | 18946.5
Valvoline Assessment | 6434.95
Contingency | 12397.6
Total Obligation | 7251127.92
City Resources
FHWA Design Grant | 600000
ODOT Rail Funds | 600000
UPRR | 1065000
SDC | 2537000
LID | 2127937.92
BWW for Water Line | 295710
BES for Sewer | 25480
Total Resources | 7251127.92

## Sheet2
City Obligations
UPRR Work (Lump Sum + flagging) | 0 | done
Glacier NW Settlement (Lump Sum) | 126941 | done
Utility Relocations | 645576.6 | done
Demo Valvoline Building | 145000 | done
ROW Acquisition | 3814676.39 | outstanding Smith Bros Settlement
Design Engineering | 3821111.34 | done
PDOT staff (outside IMAX Staff) Construction Admin | 130745.19
BWW crews | 8853379.4289 | done but not final number yet
BWW Engineering (PDOT share) | 60705 | closeout left but also not final number yet from BWW
BES Engineering (PDOT share) | 37711.32 | closeout left but also not final number yet from BES
CH2M Construction Services | 357154.64 | final billings needed including for Ater Wynne
Misc Consultants | 168285.76 | URS/DEA, Valvoline leftover appraisal
DEQ | 11336.07 | still working on Tucker and Valvoline
Construction Financing |  | may need some if choose not to assess LID now
Auditor's Fees | 1567042.7
Contingency | 0
Total Obligation | 19739665.4389
Minus Pending Obligations
ROW Acquisition | 10000 | Settlement due January 30 if have not obtained easement from UPRR
PDOT staff (outside IMAX Staff) Construction Admin | 5000 | Closeout, survey monumentation
Const Admin M&S | 0 | Closeout estimated
BWW Crews | 8799423.4289 | Close to Final
BWW Engineering | 36666.87 | Close to Final
BES Engineering | 428 | Closeout estimated
CH2M Const Services | 54378 | As-Built completion, load rating calcs, environmental consultant
URS/DEA | 116469.29 | Waiting for billings from site work and future analysis - should know more 11/8
Valvoline appraisal for sale | 4000 | Reappraisal of left-over property to sell
DEQ | 3500 | Estimate to complete reviews etc.
Construction Financing |  | Unknown - may need some if choose not to assess LID now
Auditor's Fees | 1567042.7
Contingency | 0 | To cover potential environmental requirements from DEQ
10596908.2889

## Sheet3
Expended by PDOT to 9/25/02
Total PDOT Expenses | 19739665.4389
Expenses Pending |  | Based on Budget | Karen Comments
ROW Acquisition |  | 10000 | 10000 | likely
PDOT staff (outside IMAX Staff) Construction Admin |  | 5000 | 6700 | est - may be high
Const Admin M&S |  | 0 | 400 | est - may be high
BWW Crews |  | 8799423.4289 | 71248.14 | s.b. close
BWW Engineering |  | 36666.87 | 38000 | include closeout
BES Engineering |  | 428 | 428 | est - may be low
CH2M Const Services |  | 54378 | 54378 | s.b. close
URS/DEA |  | 116469.29 | 115500 | close
Valvoline appraisal for sale |  | 4000 | 4000 | est - may be high
DEQ |  | 3500 | 3500 | est - may be low
Construction Financing |  | 0 |  | gone
Auditor's Fees |  | 1567042.7 | 16534.5
LID Assessment |  | 24892.6611 | 6500
|  | 10621800.95 | 327188.64
Expenses as of 9/25/2002 | 9117864.4889
City Resources as of 9/25/2002
FHWA Design Grant |  | 600000
ODOT Rail Funds |  | 600000
UPRR |  | 1065000
SDC |  | 2537000
4802000
Outstanding Expenses Not Cost Recovered | 4315864.4889
Future Resources to City
LID |  | #REF! | $3.775M minus $1.7M owed to Tri-Met based on $5.150 Fed Grant
BWW for Water Line (estimate) |  | 295710
BES for Sewer (estimate) |  | 25480
#REF!
Resources to Cover Pending Expenses | #REF!