## Sheet1
PATI Preconstruction Services
TASK ASSESSMENT AND ASSIGNMENT MATRIX | [9 empty] | RAE
8_02_04
|  | POINT / KEY | ESTIMATED MANHOURS | HOURLY RATE | EXTENSION | TARGET START DATE | TARGET COMPLETION DATE | % COMPLETE | PENDING/ACTION | COMMENTS AND NOTES
Meetings |  |  | 132 |  | 11220
I.N - Participate in bi-weekly project management team meetings |  | P | 80 | 85 | 6800
I.N - Participate in OTHER meetings of the PATI Board, the Citizen Advisory Committee, the City and others as requested |  | P | 20 | 85 | 1700
I.N - Participate in Design Team Meetings on a quarterly basis in Los Angeles. |  | P | 32 | 85 | 2720
Schedule |  |  | 74 |  | 5770
I.B - Provide a detailed Project schedule |  | P/EST | 40 | 72 | 2880
I.B - Update Project Schedule as necessary |  | P | 20 | 85 | 1700
I.K - Continuously monitor the Pre-Construction Schedule and advance procurement of any long lead items to ensure delivery by required dates |  | P | 10 | 85 | 850
I.E - Provide a detailed listing of any long-lead items that must be procured prior to completion of design. |  | P | 4 | 85 | 340
Design Management |  |  | 140 |  | 9960
I.A - Consult with, advise, assist and make recommendation to PATI, the City and Project Team on all aspects of the design and of planning for construction |  | P/DC | 80 | 72 | 5760
I.I - Review 100% Design Development Documents and in-process design documents and suggest modification to improve completeness or clarity |  | P/DC | 60 | 70 | 4200
Constructability Reviews |  |  | 220 |  | 13560
I.D - Review in-process design documents and provide input and advise with respect to constructability, alternate materials and methods, availability of materials and labor, and time requirements of procurement and construction. |  | P/DC | 80 | 64 | 5120
I.D - Provide advice on potential areas of cost savings while maintaining the design quality and intent |  | DC | 40 | 50 | 2000
I.C - Provide input as to current construction industry practices |  | DC | 20 | 50 | 1000
I.C - Participate in decisions regarding value engineering, delivery schedules, construction costs, construction methods, materials and systems |  | P/DC | 40 | 68 | 2720
I.I - Review 100% Design Development Documents and in-process design documents and suggest modification to improve completeness or clarity |  | P/DC | 40 | 68 | 2720
Estimating and Quantities |  |  | 284 |  | 16288
I.L - Estimate unit price quantities |  | P/EST | 150 | 55 | 8250
I.L - Confirm accuracy of the Design Team's quantity estimates |  | P/EST | 22 | 65 | 1430
I.M - Provide detailed cost breakdown to substantiate proposed unit prices (see 8.6) |  | P/EST | 112 | 59 | 6608
Permits |  |  | 41 |  | 3485
I.G - Assist, as needed, the City and PATI in negotiating construction permits with ODOT relative to crossing Macadam Ave, I-5, Naito Parkway and Barbur Boulevard. |  | P | 25 | 85 | 2125
I.O - If necessary, apply for and obtain a temporary disturbance permit form (from) the City of Portland for the Environmental C Zone land referenced in Section IV, D, iv. Of the RFP. |  | P | 16 | 85 | 1360
Planning |  |  | 112 |  | 9520
I.H - Develop an access and construction coordination plan with respect to on-going construction of the Patient Care Facility on Marquam Hill |  | P | 36 | 85 | 3060
I.H - Develop an access and construction coordination plan with respect to on-going construction the Block 25 development in South Waterfront |  | P | 36 | 85 | 3060
I.F - Develop a detailed plan for provision of temporary facilities. Temporary protection of I-5, neighborhood and existing overhead utilities within the alignment. |  | P | 25 | 85 | 2125
I.F - In consultation with the Project Team and ODOT develop a construction phasing plan and traffic management plan. |  | P | 15 | 85 | 1275
I.P - Identify permanent and temporary utility conflicts relative to the permanent tram improvements and construction process. Assist staff with utility notification and coordination, and attend utility coordination meetings to resolve utility conflict issues. |  | P | 10 | 85 | 850
Pre Construction Cost Management Services |  |  | 240 |  | 20440
I.J - Recommend division of the work to facilitate bidding and ward of subcontractors. |  | EST/FAYE | 40 | 105 | 4200
II.A - Prepare and Submit Subcontractors & Suppliers selection plan. |  | EST/FAYE | 40 | 105 | 4200
II.A - Demonstrate compliance with SMP & M/W/ESB program |  | EST/FAYE | 20 | 85 | 1700
II.A - Demonstrate compliance with WORK FORCE TRAINING & HIRING program |  | EST/FAYE | 20 | 85 | 1700
II.B - Obtain Bids and other Prices adequate to prepare a GMP Bid |  | EST/FAYE | 60 | 72 | 4320
II.B - Prepare and Submit GMP proposal to Project Team |  | P/EST | 60 | 72 | 4320
| TASK SUB TOTALS = |  | 1243 | MANHOURS | 90243 |  |  |  |  | ESTIMATED DOLLARS
NOTES AND COMMENTS:
TRAVEL TO LA |  | EA | 6 | 1000 | 6000
AUTO EXPENSE |  | WKS | 23 | 450 | 10350
OFFICE EXPENSE |  | WKS | 23 | 300 | 6900
MISC WEEKLY EXPENSE |  | WKS | 23 | 300 | 6900
NOTE AND COMMENTS SUB TOTAL = |  |  |  |  | 30150
| TOTALS = |  |  |  | 120393 |  |  |  |  | ESTIMATED DOLLARS
KEY: please refer to Exhibit A - Agreement for professional , technical or expert services for reference of identification code at beginning of each task, for example
I.G, refers to section I item G in Exhibit A.