Misc. Contracts & Agreements

No. 19,420

## 2001 OREGON TRANSPORTATION INVESTMENT ACT AGREEMENT

## East Columbia Blvd. – Lombard St. Connector

## US 30 Bypass

THIS AGREEMENT is made and entered into by and between THE STATE OF OREGON, acting by and through its Department of Transportation, hereinafter referred to as "ODOT"; and THE CITY OF PORTLAND, a municipal subdivision of the State of Oregon, acting by and through its Elected Officials, hereinafter referred to as "Agency".

### RECITALS

- The 2001 Oregon Transportation Investment Act Program, hereinafter referred to as the “2001 OTIA Program”, provides funding for preservation and modernization projects chosen by the Oregon Transportation Commission.

- The Oregon Transportation Commission selected the projects to be funded under the 2001 OTIA Program at its January 16, 2002 meeting.  This selection included ODOT’s East Columbia Blvd. – Lombard Street Connector Project, as described in Exhibit A. The Oregon Transportation Commission approved this Project on the condition that an Access Management Plan be prepared and agreed to by City and ODOT; said Access Management Plan for this Project shall be documented in a subsequent agreement.

3.	By the authority granted in ORS 190.110, 366.770 and 366.775, state agencies may enter into cooperative agreements with counties, cities, and units of local government for the performance of any or all functions and activities that a party to the agreement, its officers, or agents have the authority to perform.

NOW THEREFORE, the premises being in general as stated in the foregoing recitals, it is agreed by and between the parties hereto as follows:

### TERMS OF AGREEMENT

1.	Parties shall make roadway modernization improvements on NE Columbia Boulevard and NE Lombard Street (Killingsworth) from approximately NE 82nd Avenue to the I-205 Interchange, hereinafter referred to as “Project”. The section of NE Lombard Street (Killingsworth) within the Project limits is a State Highway under the jurisdiction and control of the Oregon Transportation Commission.  NE Columbia Blvd. is a part of the city street system under the jurisdiction and control of the Agency.   A Project description and budget are shown on Exhibit “A”, and a sketch map showing the location and approximate limits of the Project is shown on Exhibit “B”, attached hereto and by this reference made a part hereof.

- The total estimated cost of the Project is $24,463,977.  The budget is shown on Exhibit “A”.

- 2001 OTIA Program funds shall be limited to $19,765,250.  Agency shall be responsible for Agency’s contribution of $4,698,727, and shall be required to pay for costs found to be nonparticipating or constitutionally ineligible for this Project.

- Agency will initiate a discussion with ODOT regarding the budget any time a significant change occurs, including at a minimum, discussions when the following events occur:

a.) at the completion of the Level 2 Environmental Site Assessment

b.) when the right-of-way process has completed the final appraisals and a        relocation plan

c.) when the type, size and location of the Project has been determined

d.) when the railroad work order is completed; and

e.) prior to award of contract.

ODOT and Agency will meet at the times listed above to determine if the Project is still on budget.  If it is found that there will be significant cost over-runs ODOT shall be responsible for 33 1/3% of the estimated cost over-runs up to $550,000.  Agency shall be responsible for 66 2/3% of said cost over-runs in addition to their required obligations stated above.

If the total for the contract over-runs will be more than $1,650,000 then Agency and ODOT shall negotiate the excess costs and the agreed upon amount of ODOT’s share shall be incorporated into this agreement by a written amendment.  If after negotiation, and agreement can not be reached, Agency shall be responsible for all cost over-runs above the $1,650,000.

- This agreement shall become effective on the date all required signatures are obtained and shall be completed according to the schedule outlined in Paragraph 6, Agency Obligations.  Only work begun after the effective date of this agreement is eligible for reimbursement with OTIA funds.

- The funds available under the 2001 OTIA Program are State Highway Funds.  To be eligible for reimbursement under the 2001 OTIA Program, expenditures must comply with the requirements of Article IX, Section 3a of the Oregon Constitution.

- Agency and ODOT have a joint obligation to ensure timely expenditure of 2001 OTIA Program monies and comply with the provisions of the bonds that finance the 2001 OTIA Program.  The Parties recognize that, while Agency is leading the Project, Project is beneficial to Agency and ODOT.    Both Parties commit to work together to assure Project success.

AGENCY OBLIGATIONS

- Agency, or its consultant, shall conduct the necessary engineering and design work required to produce final plans, specifications and cost estimates; obtain any right-of-way required for the Project in compliance with ORS 281.060; ORS 35.346, and the State of Oregon Right of Way Manual; obtain all required permits; arrange for all utility relocations or reconstruction, if any, required for Project in compliance with the standards in Agency Obligations, Paragraph 15; perform all construction engineering, including all required materials testing and quality documentation; prepare all bid

documents; advertise and award all contracts; provide Project management services; and other necessary functions for administration of the contract.

- Agency shall design and construct to ODOT standards that portion of the Project that will remain under ODOT jurisdiction.   The entire Project will conform to the current Oregon Bicycle and Pedestrian Plan, and the current edition of A Policy on Geometric Design of Highways and Streets by the American Association of State Highway and Transportation Officials (AASHTO) and shall comply with ORS 276.071.

3. 	Agency shall, prior to construction, provide the Project preliminary and final plans and specifications to ODOT’s Regional Office for review and concurrence by ODOT’s Region and District Staff, Traffic Sections, Roadway Section, and ODOT’s Rail Division.  ODOT’s written approval is necessary before Agency can begin construction of the Project.

4. 	Agency shall provide ODOT with sufficient information to complete a project prospectus so that ODOT can track Project using ODOT’s automated management system.

5. 	Agency agrees to include John Riedl, Design/Build Program Manager with ODOT’s Alternative Delivery Unit, as a Project team member to insure that the rules and regulations regarding alternative contracting are followed.

- a.	Agency shall submit documentation to ODOT’s Project Liaison that shows that Agency has met Project key milestones.  The Project key milestones,  dates, and required documentation are shown below:

Environmental:   August 31, 2003

Documentation: Letter from Agency documenting compliance with all required environmental elements, including the completion of the Phase 2 environmental site assessment. .

Right of Way Acquisition:	July 31, 2005

Documentation: Letter from Agency’s legal counsel certifying that 1) right-of-way was acquired in accordance with current FHWA directives covering the acquisition of real property,  and 2) the right-of-way needed for the Project has been obtained.

Land Use Permits:	September 1, 2005

Documentation:  Letter from Agency indicating that all Land Use Permits required for final design have been obtained.

Final Plans / Biddable Engineering Documents:	   September 30, 2005

Documentation:  A copy of completed Project plans, specifications and cost estimates.

Contract Advertisement and Award:	October 31, 2005

Documentation:  A copy of the Award of Contract submitted to the Bureau of Labor and Industries.

Construction Completion:	 September  30, 2007

Documentation:  A letter from Agency indicating that construction is substantially complete.

Project Completion:	December 10, 2007

Documentation:  Letter from Agency indicating that the Project is complete and open to traffic, accompanied by Agency’s final billing to ODOT.

- If the Agency does not meet a Project milestone date within one month of the date specified in Agency Obligations, Paragraph 6.a., reimbursement of Agency’s Project expense shall be changed to one-half of the rate specified in ODOT’s Obligations, Paragraph 1, until such time as the Project has completed the milestone and Project is back on schedule.

- Immediately upon missing a milestone date, Agency and ODOT shall establish a project review team including Agency’s Project Liaison and ODOT’s Project Liaison, at a minimum, and may include such other members as are deemed necessary.  The project review team shall determine (a) if failure to complete the milestone in question will jeopardize successful completion of Project, (b) what steps must be taken by Agency to ensure successful completion of Project, and (c) revise the Project schedule, if changes are required.

- In the event that the Project schedule itemized in Agency Obligations 6.a. is revised pursuant to Agency Obligation 6.c., the Agency’s Project Liaison and ODOT’s Project Liaison shall reduce the revision to writing.  Changes to intermediate milestones by less than 90 days that do not affect the final milestone shall be kept in the Project files by both agencies. Changes to the budget or changes to a milestone by more than 90 days shall be approved by ODOT’s Area Manager and Agency Bureau Director. The Agency’s Project Liaison and ODOT’s Project Liaison shall incorporate the revised schedule into this intergovernmental agreement by entering into a formal amendment to this agreement.

- When the Project is back on schedule according to the milestones set out in Agency Obligations 6.a., including a revised schedule adopted by formal amendment, Agency shall receive any funds withheld by ODOT under the provisions of Paragraph 1.b. of ODOT’s Obligations.

- Agency shall present invoices for the eligible, actual costs incurred by Agency on behalf of the Project directly to ODOT's Project Liaison for review and approval.  Such invoices shall be submitted in the form as shown on Exhibit “C”, OTIA Progress Billing, attached hereto and by this reference made a part hereof. Actual costs may include, but are not limited to, all direct, indirect, and overhead costs, materials, services, professional services, right of way expenses and construction expenses.  Invoices will identify the Project and agreement number, and shall itemize and explain all expenses for which reimbursement is claimed.   Invoices shall be presented for periods of not greater than one month, based on actual expenses incurred, and must clearly specify the percentage of completion of the Project as defined by the amount of remaining OTIA funding available for expenditure.

- Agency shall submit a billing at the time Agency documents that Construction Completion, as set out in Agency Obligations, Paragraph 6, is complete.  The billing will indicate total Project costs incurred to date, whether there are unresolved claims, and the anticipated timeline for resolving claims and closing the Project.

9.	If after negotiation, and agreement can not be reached, Agency shall be responsible for any and all costs of Project which are not covered by OTIA funds, including costs of the Project when the maximum amount of OTIA funds, Agency contribution, and if necessary, the $550,000 of ODOT funds for cost over-runs obligated under this Agreement have been expended.

10.	Agency agrees to comply with all federal, state, and local laws, regulations, executive orders and ordinances applicable to the work under this agreement, including, without limitation, the provisions of ORS 279.312, 279.314, 279.316, 279.320 and 279.555, which hereby are incorporated by reference.

11.	Agency shall perform the service under this agreement as an independent contractor and shall be exclusively responsible for all costs and expenses related to its employment of individuals to perform the work under this agreement including, but not limited to, retirement contributions, workers compensation, unemployment taxes, and state and federal income tax withholdings.

12.	Agency, its subcontractors, if any, and all employers working under this agreement are subject employers under the Oregon Workers Compensation Law and shall comply with ORS 656.017, which requires them to provide workers' compensation coverage for all their subject workers, unless such employers are exempt under ORS 656.126.  Agency shall ensure that each of its contractors complies with these requirements.

13.	Agency will retain ownership, control and maintenance responsibilities on the improvements made on NE Columbia Blvd. as a result of the Project at the same level as other similar facilities owned by Agency.  Agency will maitain all traffic signals constructed by Project.  In addition Agency will maintain new storm water treatment facilities or hazardous materials containment facilities constructed by the Project, if any.

14.	Agency agrees that the Project will be on the public right-of-way and will serve general transportation needs.

- Utility relocation or reconstruction may or may not be an eligible Project expense according to the following standard:

- The expense is an eligible expense if the owner of the utility facility possesses a property right for its location on the public right of way

- The expense is not an eligible expense if the owner of the utility facility does not possess a property right for its location, but the facility exists on the public right of way solely under the permission of the Agency or other road authority, whether that permission is expressed or implied, and whether written or oral.

16.	Agency certifies, at the time this agreement is executed, that sufficient funds are available and authorized for expenditure to finance costs of this agreement within Agency’s current appropriation or limitation of the current budget.  Agency further agrees that they will only submit invoices to ODOT for reimbursement on work that has been performed and paid for by Agency.

17.	Agency shall, to the extent permitted by the Oregon Constitution and the Oregon Tort Claims Act, indemnify, defend, save, and hold harmless the State of Oregon, Oregon Transportation Commission and its members, and the Oregon Department of Transportation and its officers and employees, from all claims, suits or actions of any nature arising out of activities of Agency, its consultant, its contractor, its officers, subcontractors, agents, or employees under this agreement.

18.      Agency’s Project Liaison for this agreement is Rob Barnard, City of Portland Office of Transportation Engineering and Development, 1120 SW 5th Ave, Suite 800, Portland Oregon 97204.  Phone (503) 823-7071.  Agency’s Project Liaison is granted the authority to enter into and execute formal amendments to this agreement when revisions to the Project schedule are deemed necessary by the project review team.

19.	Agency shall require contractor to obtain and keep in effect during the term of the construction contract, Comprehensive or Commercial General Liability Insurance covering bodily injury and property damage.  This insurance shall include personal injury coverage, contractual liability coverage for the indemnity provided under the agreement, and products/completed operations liability.  Combined single limit per occurrence shall not be less than $2,000,000, or the equivalent.  Each annual aggregate limit shall not be less than $4,000,000, when applicable.

The certificate of insurance shall include the State of Oregon, Transportation Commission and its members, the Department of Transportation, its officers and employees, as additional insureds.

Before start of construction, Agency shall furnish to ODOT a Certificate of Insurance for the limits set out above, which is to be in force and applicable to the Project.

The insurance coverage shall not be amended, altered, modified, or canceled insofar as the coverage contemplated herein is concerned without at least thirty (30) days prior written notice.

- Agency shall place signs that identify Project as “Another Project Funded by 2001 Oregon Transportation Investment Act”  (ODOT approved design).  Agency may affix additional signage that identifies local funds used for the Project.

- Agency agrees that it will call attention to the Project and help make it visible to the public.

- Agency agrees to provide progress information and photographs in a suitable format for posting on the OTIA web site maintained by ODOT and to provide appropriate links from Agency’s web sites to the OTIA web site.

- Agency agrees to comply with the conditions for Project approval adopted by the Oregon Transportation Commission, as set out in Exhibit A, Special Conditions, which is attached and made part of this Agreement.

- Agency will acquire property for Project using Project funds.  Any property costs beyond those of the required right-of-way (including any Project related auxiliary facilities) and damages to the properties will be paid for with matching funds and the remaining property rights will be owned by Agency.

### ODOT OBLIGATIONS

1.

- ODOT shall reimburse Agency 80.8% of eligible, actual costs incurred up to the maximum amount of OTIA funds committed for the Project specified in Terms of Agreement, Paragraph 3, provided that Agency is meeting the Project milestones set out in Agency Obligations, Paragraph 6. a.  Under no conditions shall ODOT’s total obligation exceed $19,765,250 in OTIA funds and $550,000 for possible Project over-runs, including all expenses unless negotiated for and agreed to by the parties per Terms of Agreement, Paragraph 3.

- In the event that Agency has not met a Project milestone, ODOT shall change its rate of reimbursement to Agency to be one-half of the rate specified in Paragraph 1.a. until such time as Project is back on schedule.

- When the Project is back on schedule, according to the milestones set out in Agency Obligations 4.a., including a revised schedule adopted by formal amendment per Agency Obligations 6.d., ODOT shall pay Agency any funds withheld by ODOT under the provisions of Paragraph 1.b. of ODOT’s Obligations.

- ODOT agrees to comply with the provisions of ORS 293.462 with regard to timely payment.

2.	ODOT certifies, at the time this agreement is executed, that sufficient funds are available and authorized for expenditure to finance costs of this agreement within ODOT's current appropriation or limitation of current biennial budget.

3. 	ODOT hereby grants Agency the right to enter onto and occupy ODOT right-of-way upon issuance of required ODOT permits, for the performance of necessary preliminary engineering, construction and installation of Project traffic signal equipment.

4. 	ODOT's Project Liaison for this agreement through award of the Construction Contract is Jeanette Kloos, 123 NW Flanders, Portland Or. 97209 (503-731-8234).  Following award of the Construction Contract, ODOT’s Project liaison for this agreement is Marjorie West, 9010 SE McLoughlin Blvd. Milwaukie, Oregon 97222 (503-731-3142).  ODOT’s Liaison shall:

- Receive any notices provided by Agency under this agreement.

- Review and process for payment all eligible, actual Project costs incurred within 30 days of the date of receipt of Agency’s invoices by ODOT.

- Advise Agency at Agency’s request on matters affecting the Project.

- ODOT’s Project Liaison is granted the authority to enter into and execute formal amendments to this agreement when revisions to the Project schedule are deemed necessary by the project review team.

- ODOT shall review the documentation provided by Agency to ensure that the Project undertaken by Agency is the Project approved by the Oregon Transportation Commission at its January 16, 2002 meeting.

- ODOT shall not be required to approve Agency’s selection of contractors/consultants, except as the Project design affects the state highway system or as required by the conditions of approval adopted by the Oregon Transportation Commission.

- ODOT shall maintain a web site for the 2001 OTIA Program listing Project status and accomplishment information for Agency’s Project.

- ODOT Rail Division shall review Agency’s rail order application, assist agency in obtaining a rail crossing order, and work with Agency to secure any necessary railroad right of way permits for construction of the Project.

9. 	ODOT shall retain ownership, jurisdictional control, and maintenance responsibilities on Killingsworth Street (a.k.a. Lombard Street) from curb to curb, including existing storm water drainage facilities.  Right-of-way behind the curb, including sidewalks, shall continue to be maintained by the adjacent property owner.  ODOT shall continue to maintain the sidewalk on Killingsworth where ODOT is the adjacent property owner.  ODOT will pay for a portion of the electrical costs for traffic signals on Killingsworth, as specified in existing agreements.

10.     ODOT shall provide a representative to attend project team meetings.

### GENERAL PROVISIONS

1. 	This agreement may be terminated by mutual written consent of both parties.  Such written consent shall not be unreasonably withheld.

- ODOT may terminate this agreement effective upon delivery of written notice to Agency, or at such later date as may be established by ODOT, under any of the following conditions:

- If Agency fails to provide services called for by this agreement within the time specified herein or any extension thereof.

- If Agency fails to perform any of the other provisions of this agreement or so fails to pursue the work as to endanger performance of this agreement in accordance with its terms, and after receipt of written notice from ODOT fails to correct such failures within 10 days or such longer period as ODOT may authorize.

- If ODOT fails to receive funding, appropriations, limitations or other expenditure authority at levels sufficient to pay for the work provided in the agreement.

- If Federal or State laws, regulations or guidelines are modified or interpreted in such a way that either the work under this agreement is prohibited or if ODOT is prohibited from paying for such work from the planned funding source.

If ODOT terminates this agreement for the reasons described in General Provisions, Paragraph 2., “a” or “b” above, Agency must reimburse ODOT for all Oregon Transportation Investment Act funds expended.  If Agency fails to reimburse ODOT, ODOT may withhold Agency’s proportional share of State Highway Fund distribution necessary to reimburse ODOT for costs incurred by such Agency breach.

3.	In the event that during the preliminary engineering stage, or at any time prior to advertisement for bids for the construction portion of the Project, the estimated Project cost exceeds $26,000,000, Agency may terminate this agreement.  If Agency terminates this agreement for the reasons described herein, Agency shall reimburse ODOT for all Oregon Transportation Investment Act funds expended.  If Agency fails to reimburse ODOT, ODOT may withhold Agency's proportional share of State Highway Fund distribution necessary to reimburse ODOT for costs incurred.

Any termination of this agreement shall not prejudice any rights or obligations accrued to the parties prior to termination.

4.	Agency acknowledges and agrees that ODOT, the Secretary of State's Office of the State of Oregon, and their duly authorized representatives shall have access to the books, documents, papers, and records of Agency which are directly pertinent to the specific agreement for the purpose of making audit, examination, excerpts, and transcripts during the course of the Project and for a period of three years after final payment.  Copies of applicable records shall be made available upon request.  Payment for costs of copies is reimbursable by ODOT.

5. 	This agreement and attached exhibits constitute the entire agreement between the parties on the subject matter hereof.  There are no understandings, agreements, or representations, oral or written, not specified herein regarding this agreement.  No waiver, consent, modification or change of terms of this agreement shall bind either party unless in writing and signed by both parties and all necessary approvals have been obtained.  Such waiver, consent, modification or change, if made, shall be effective only in the specific instance and for the specific purpose given. The failure of either party to enforce any provision of this agreement shall not constitute a waiver by that party of that or any other provision.

IN WITNESS WHEREOF, the parties hereto have set their hands and affixed their seals as of the day and year hereinafter written.

The Oregon Transportation Commission approved this Project on January 16, 2002.

The Oregon Transportation Commission on February 13, 2002, approved Delegation Order No. 2, which authorizes the Director to approve and execute agreements for day-to-day operations when the work is related to a project included in the Statewide Transportation Improvement Program or a line item in the biennial budget approved by the Commission.

The Director on September 6, 2002, approved Subdelegation Order No. 2, which grants authority to the Deputy Director for the Oregon Transportation Investment Act to approve and execute agreements over $75,000 when the work is related to a project included in the Statewide Transportation Improvement Program, in the Oregon Transportation Investment Act project list, or in the approved biennial budget.

APPROVAL RECOMMENDED		STATE OF OREGON, by and through

Its Department of Transportation

By_________________________	By____________________________

Region 1 Manager	 Executive Deputy Director for Highways

Date_______________________

Date__________________________

By_________________________

Tech Serv Mgr/Chief Engineer

Date_______________________

CITY OF PORTLAND, by and through

APPROVED AS TO LEGAL 	its Elected Officials

SUFFICIENCY

By____________________________

By_________________________	      Mayor

Assistant Attorney General

By____________________________

Auditor

Date _______________________

Date__________________________

APPROVED AS TO LEGAL

SUFFICIENCY				RETURN AGREEMENT TO AGENCY:

Contact:      Rob Barnard

By_________________________

Agency Attorney 	Address: C/O Office of Transportation
		    1120 SW Fifth Ave., Suite 800

Date__________________________	  Portland, OR 97204

## EXHIBIT A

PROJECT DESCRIPTION

CITY OF PORTLAND OFFICE OF TRANSPORTATION

East columbia Boulevard to LOMBARD sTREET connector

Project to construct a new wider underpass and at-grade intersection at a location further from the I-205 Interchange.  The Columbia Blvd. approach to the intersection will be wider to increase storage and add additional left-turn lanes.

| Project Cost Estimate Preliminary engineering & design $ 599,427 Right-of-way purchase $ 7,642,000 Construction $ 16,222,550 Total $ 24,463,977 | Project Financing Agency Contribution $ 4,698,727 19.2% OTIA $19,765,250 80.8% Total $24,463,977 100% |
| --- | --- |

## SPECIAL CONDITIONS

The Oregon Transportation Commission approved Projects for funding under OTIA subject to certain conditions:

- City of Portland, Port of Portland and ODOT shall jointly develop an access management plan for the Project.  The City of Portland shall adopt the access management plan as part of a development agreement between the City of Portland and ODOT as provided in ORS 94.504.  In addition to the requirements of ORS 94.504, the development agreement shall include the following elements:

- An automatic renewal of the agreement unless the City of Portland takes a positive action to terminate the agreement.

- If the agreement is to be terminated that the City of Portland give notice to ODOT in advance of a public hearing on the matter and that the public hearing be held prior to the expiration of the agreement.

- Changes or termination of the agreement in advance of expiration shall require formal affirmative action by the Oregon Transportation Commission and the City of Portland.

- The agreement can expire if the City of Portland includes the access management plan in its Transportation System Plan.

## EXHIBIT B

Project Location Map

CITY OF PORTLAND OFFICE OF TRANSPORTATION

Approximate limits of work: NE 82nd to I-205

## EXHIBIT C

Oregon Transportation Investment Act (OTIA)

Progress Billing

(form)

Agency:	City of Portland Office of Transportation

Project:	East Columbia Blvd. to Lombard Street Connector

Agreement No:     19,420

Billing Period:			    to

|  | Costs Incurred This Period | Costs Billed Previously | Total Cost To Date | Participation Rate | Total Amount Claimed | Prior Total Claimed | Amount Claimed This Period | Percent Complete This Phase |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning |  |  |  |  |  |  |  |  |
| Engineering Design |  |  |  |  |  |  |  |  |
| Right of Way |  |  |  |  |  |  |  |  |
| Construction |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |

Submission of this request certifies that, in accordance with the laws of the State of Oregon and under the conditions of approval for the project identified above, actual costs claimed have been incurred and are eligible pursuant to the Intergovernmental Agreement between Agency and the Oregon Department of Transportation.  Also, no other claims have been presented to, or payment made by, the State of Oregon for those costs claimed for reimbursement.

Agency Project Liaison

___________________________

Date

(for ODOT use)

I have reviewed the above project and related costs and, in my opinion, subject to audit, the costs reflect the progress to date and are eligible for reimbursement in the amount of $				.

ODOT Project Liaison

____________________________

Date