AMENDMENT NO

Purchase Order NO.

## FOR

This purchase order was issued on to Carlson Communications hereinafter called Contractor, and the City of Portland, a municipal corporation of the State of Oregon, by and through its duly authorized representatives, hereinafter called City.

- This contract is hereby extended through December 31, 2005.

- Additional work is necessary as described in the Scope of Work attached hereto as Exhibit A to this Amendment:

- Additional compensation is necessary and shall not exceed $5,000 for a revised purchase order amount of $10,000.

All other terms and conditions shall remain unchanged and in full force and effect.

Carlson Communications

Authorized Signature 		Date

(Name and Title)

Mailing Address

Mailing Address

# Approved as to Form:	CITY OF PORTLAND

By:

City Attorney	Date	          Auditor	 	          	Date

By:

Mayor/Elected Official	Date

Purchase Order ________

Amendment #1

Exhibit A

Scope of Services

Develop media roll out for 10-year plan to end homelessness to achieve the following goals:

- Announce the existence of the 10-year plan to end homelessness

- Announce some numerical targets to measure future success

- Explain concept of “housing first” model for chronically homeless

- Inform how solving chronic homeless problem will help with other homelessness, including families

- Encourage giving to non-profits working on homelessness

- Get buy-in from business community, neighborhoods, churches and other external groups on the plan

Plan and organize Initial roll out event to include the following:

- Create a visual event that will appeal to both print and broadcast media

- Provide specific, numerical targets for ending chronic homelessness to media that they can measure later (next year)

- Provide specific non-profits to media to solicit donations

- Create message/materials that simply explain:

- The chronic homeless problem

- How the plan solves chronic homelessness

- How solving chronic can help other kinds of homelessness

- Use business and community leaders as spokespeople at events

- Approach one media outlet (the Oregonian) prior to others to give them a chance to write a bigger story

Develop follow up events to continue interest in the roll out of the 10-year plan.  Such events could include:

- Family homelessness event/announcement—ask people to contribute & help in spirit of holiday

- Church announcement—sponsorship of XX number of homeless people by Portland churches (coordinate with EMO; include outreach to church newsletters as well as media)

- Announcement of additional funding from foundations/other groups

- One-year Homelessness Report Card event (update the plan/report progress); hold this annually

- Other press events per community partner involvement (the contract signing event, etc.)

- I still like the idea of some formal “signing” ceremony.  Having all of the major stakeholders get together to sign a symbolic contract to implement different parts of the plan.

- Speech or forum on homelessness? Maybe we could do something in conjunction with PBA, or City Club, or neighborhood associations? Or all of the above?

## Budget:  $5,000

Schedule of actions and payments:

December 20 event:

Tour and determine first rollout event site: 	December 2

Start drafting media materials, talking points:	December 2

Media materials circulated for comment:		December 8

Final media materials:				December 16

Speakers, attendees invited:			December 10

Schedule of speakers, speakers prepped:	December 16

News advisory issued about event:		December 16

Call downs to media				December 17

Manager event details:				Ongoing up to December 20

## First payment					$1000

Other events/outreach:

Draft communications plan for 2005:		January 15

## Second Payment				$1,000

Coordinate other events & outreach:		Ongoing through 2005

Announce other events to media:		Ongoing through 2005

## Other payments:  				$500 - 1,000 for each additional event