The City of Portland (“City”) and Cayenta Canada (“Cayenta”) agree to amend Contract #35151as described below:

- Exhibit A to the Contract, Statement of Work, and Exhibit B to the Contract, Pricing Schedule, identify the date of Live Operation for the replacement CIS as December 15, 2005.

- Exhibit B to the Contract also identifies total fixed fees to be paid to Cayenta based on progress and completion of specific tasks and products, and their acceptance by the City.

- The City has determined that the date of Live Operation for the replacement CIS should be adjusted to March 13, 2006.

# Dates of the following milestones identified in Section 8 of Exhibit A, Statement of Work, are therefore adjusted as follows:

## Milestone Description	Amended Completion Date

Integrated Test Plan Signed Off	3/4/2005

Operations Training Delivered	3/11/2005

Batch Process Integration Testing Completed	8/5/2005

Initial Mock Production Milestone Completed	8/26/2005

Integrated Testing-Functional Business Area Signed Off	9/23/2005

City Acceptance/Non-Acceptance of System-Pre go-live	12/12/2005

Data Conversion-Mock Production Audit #4 Delivered	1/9/2006

Live Operation	3/13/2006

Cutover to Standard Support	4/24/2006

On-site Transition Support Second Level (90 days)	6/26/2006

On-site Transition Support – Close Off (180 days)	9/25/2006

# As a result of the changes noted above, it is necessary to modify the dates when progress payments will be made to Cayenta.  The new dates are as follows:

## Amended

## Payment Schedule	Completion Date	Amount

### Integrated Test Plan Signed Off	3/4/2005	$126,487.00

Operations Training Delivered	3/11/2005	$143,400.00

Batch Process Integration Testing Completed	8/5/2005	$121,035.00

Initial Mock Production Milestone Completed	8/26/2005	$79,375.00

Integrated Testing-Functional Business Area Signed Off	9/23/2005	$87,225.00

City Acceptance/Non-Acceptance of System-Pre go-live	12/12/2005	$125,825.00

Data Conversion-Mock Production Audit #4 Delivered	1/9/2006	$143,125.00

Live Operation	3/13/2006	$106,900.00

Cayenta Software due on Live Operation	3/13/2006	$400,000.00

Cayenta Software Maintenance & Support Fees	3/13/2006	$160,000.00

Cutover to Standard Support	4/24/2006	$0.00

On-site Transition Support Second Level (90 days)	6/26/2006	$300,000.00

On-site Transition Support – Close Off (180 days)	9/25/2006	$100,000.00

- Other than these changes, all other portions of the original contract remain in full force and effect.

- This Amendment shall be effective as of the date of the last signature, below.

IT IS SO AGREED:

CAYENTA CANADA INC.

By:	Craig Ross

Title:	President

___________________________________

Date:

CITY OF PORTLAND, OREGON

By:	Timothy Grewe

Title:  Chief Administrative Officer

___________________________________

Date:

Approved as to Form

City Attorney’s Office