# OREGON DEPARTMENT OF TRANSPORTATION

# Transportation Safety Division

# GRANT PROJECT APPLICATION

Project No:	 SA-08-25-05

Project Name:	 Portland Safe Community

Answer each question in the boxes provided. Answer each question completely and according to the instructions in Italics. All fields are required. Do not attempt to paste images or Excel tables into the text fields provided.

- Project Description

This community-based, coalition-led project will develop and implement specific strategies to improve vehicle, pedestrian, and bicycle safety on the high crash corridor of the 82nd Ave. of Roses. This roadway has the highest quantity of serious ped injuries and fatalities of any single road segment in the City of Portland. The Portland Safe Communities Coordination Council Coalition will oversee efforts to conduct community outreach, bring together community stakeholders, identify safety issues, develop a 3-E based Safety Action Plan, and propose strategies that will reduce traffic-related injuries and fatalities along this stretch of roadway.

II.	Problem Statement

A.	Describe the problem(s) this project will try to impact:

(Describe the problem(s) you intend to impact with this grant.)

Based on crash data and information obtained from the 82nd Ave. of Roses High Crash Corridor safety survey, the Safe Communities Coordination Council Coalition identified a need for engineering, education, and enforcement enhancements to improve vehicle, pedestrian, and bicycle safety along the 82nd Ave. of Roses. The Coalition believes that the development of specific efforts to improve traffic safety along the 82nd Ave. of Roses is necessary to accomplish the following: Increase prevention of traffic collisions for all modes; Increase coordination of traffic safety partners and community stakeholders; Increase implementation of strategic traffic safety enhancements; Increase understanding of pedestrian and bicycle transportation and safety issues; Increase awareness of aggressive driving and vehicular collisions with pedestrians, bicycles, and young drivers; Increase awareness and compliance of Oregon crosswalk laws and DMV driving laws; Increase sidewalk clearance and compliance of ADA requirements.

B.	Provide summary data about the problem(s):

(Give summary data regarding the problem as it exists in your jurisdiction.)

The 82nd Avenue of Roses is a heavily used eight-mile section of roadway, a designated city Main Street, and a designated freight route. Between 1995 to 2004, Portland traffic data shows a mere 4% of Portland’s streets, all high-volume major arterials like the 82nd Avenue of Roses, accounted for over 66% of Portland’s pedestrian fatalities and 58% of pedestrian serious injuries. The 82nd Avenue of Roses has the highest incidence of traffic crashes, injuries, and fatalities for other road segement in the City of Portland. Pedestrians walking along the 82nd Ave. of Roses are more likely to die from a collision than in any other single road segment in Portland. The 82nd Ave. of Roses averages 1 pedestrian fatality per year. The 82nd Ave. of Roses has high pedestrian usage: Bus line #72 that runs along the 82nd Ave. of Roses, has more transit riders than any other line outside the downtown bus mall. The 82nd Ave. of Roses is a transit junction for TriMet, MAX light rail, and I-84. Three schools front 82nd Ave. – Portland Community College, Madison High School, and Vestal Elementary School. Many high density senior living facilities are located at or within close proximity to the 82nd Ave. of Roses including Kirkland Union Manor, St. Anthony’s Village, and The Heights at Columbia Knoll. The 82nd Ave. or Roses is zoned for commercial use in most of the area and has many commercial businesses including car lots, restaurants, retail shops, and liquor establishments. A significant number of low-income neighborhoods are located off of the 82nd Ave. of Roses including Lents, Powellhurst-Gilbert, and Montavilla. Low-income families frequently rely on mass transit more frequently than non-low income families. The pedestrian walking distance between traffic signals is greater than 600’ at every signal locations with the exception of two signals. The pedestrian walking distance between traffic signals is greater tan 1,000’ at 18 signal locations. According to a survey conducted in the spring and summer of 2007, 63 individuals reported the following traffic safety concerns along the 82nd Ave. of Roses: 93.4% of people have concerns about traffic safety that limit their ability or willingness to walk, bike, or take transit along this roadway. Slightly more than half of respondents (59%) express safety concerns about taking public transit along othis roadway. Approximately 2/3 of the respondents stated that they do feel safe driving this stretch of roadway. 11 of 63 respondents (17.5%) feel safe walking along or across this roadway, 7 of 63 respondents (11.1%) feel safe walking along this street segment only during the day, and 45 of 63 respondents (71.4%) do not feel safe walking along or across this roadway. No respondents reported feeling safe bicycling along the 82nd Ave. of Roses; 4 respondents reported feeling safe bicycling while crossing the 82nd Ave. of Roses. The top three traffic safety issues expressed by survey respondents include: 1) Pedestrians jaywalking, 2) Issues at the 82nd/ Halsey MAX stop, and 3) Speeders and too much traffic or congestion (tie).

C.	List current activities and associated agencies already involved in solving the problem(s):

(Include all related activities and agencies involved.  If you have a current project, list the objectives of that project and progress in achieving them.)

Pedestrian and Bicycle Safety Technical Advisory Committee -- technical advisory committee to Portland Traffic Safety Coordination Council Coalition DUII Technical Advisory Committee -- technical advisory committee to Portland Traffic Safety Coordination Council Coalition Driver Error Technical Advisory Committee -- technical advisory committee to Portland Traffic Safety Coordination Council Coalition Safer Routes to School Technical Advisory Committee -- technical advisory committee to Portland Traffic Safety Coordination Council Coalition Portland Office of Transportation -- traffic safety engineering, enforcement, education, and encouragement activities Portland Police Bureau -- traffic safety enforcement Bicycle Transportation Alliance – bicycle safety, enforcement, and education programs Willamette Pedestrian Coalition -- pedestrian safety, enforcement, and education programs Elders in Action -- pedestrian and bicycle safety, enforcement, and education programs SWTrails Group -- pedestrian and bicycle safety and education programs Oregon Department of Transportation, TriMet, Portland Office of Neighborhood Involvement, the 82nd Ave. of Roses Business Association, multiple Neighborhood Associations, and members of the disabled community -- education, enforcement, and encouragement for all modes of transportation along the 82nd Ave. of Roses

III.	Objectives

(Describe quantifiable products or outcomes that address those problems identified in Section I that should result from the proposed activities. Normally at least three very specific objectives should be given and each should include beginning and ending date.

The following are examples:

“To increase safety belt usage in (funded jurisdiction) from 85% to 90% by September 30, 2004, with the use rate determined by conducting observed use surveys.”

“To reduce nighttime fatal and injury crashes occurring in (funded jurisdiction) by 20% from 60, the average for the 1998-2001 period, to 48 during the 12-month period starting October 1, 2003, and ending September 30, 2004.”

“To provide intensive probation supervision to a minimum of 30 additional persons convicted of DUII in (funded jurisdiction) by making at least three face-to-face contacts with each person weekly from October 1, 2003, through September 30, 2004.”

“To complete an evaluation by July 1, 2004, to determine if using photo radar will lead to a significant reduction in fatal and injury traffic crashes in that location.”)

|  | Start Date | End Date | Objective |
| --- | --- | --- | --- |
|  | 10/1/2007 | 9/30/2008 | Develop a survey to identify traffic safety concerns and perceptions along the 82nd Ave. of Roses during the 12-month period from October 1, 2007 through September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Develop an overall strategy to reduce and eliminate vehicle, pedestrian, and bike injuries and fatalities along the 82nd Ave. of Roses during the 12-month period from October 1, 2007 through September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Work with organizational stakeholders to secure staff and funding commitments for implementing the engineering, education, and/or enforcement action items identified by the Technical Advisory Committee during the 12-month period from October 1, 2007 through September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Develop a methodology to prioritize the installation of pedestrian refuge islands proposed for the 82nd Ave. of Roses during the 12-month period from October 1, 2007 through September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Develop a “typical” pedestrian refuge median island model that can be built and installed on the 82nd Ave. of Roses during the 12-month period from October 1, 2007 through September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Increase awareness of existing sidewalk conditions along the 82nd Ave. of Roses by creating an inventory of existing conditions for areas that can be changed or modified within 1-2 years during the 12-month period from October 1, 2007 through September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Increase community awareness about Oregon Crosswalk laws and other traffic safety issues along 82nd Ave. by implementing a pedestrian safety campaign and delivering “Portland Walks – Be Safe!” trainings to a minimum of 20 groups during the 12-month period from October 1, 2007 through September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Increase community awareness about transit safety at intersections and crossings by implementing an education campaign targeting transit drivers and riders during the 12-month period from October 1, 2007 through September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Increase community awareness about excessive vehicle speeds, rear-end crashes, tailgating, and red-light running by implementing a media campaign about aggressive driving during the 12-month period from October 1, 2007 through September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Increase enforcement of Oregon crosswalk and driving laws by implementing a minimum of 2 Crosswalk Enforcement Actions at pedestrian refuge islands along the 82nd Ave. of Roses during the 12-month period from October 1, 2007 and ending September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Increase opportunities for a minimum of 200 older people living at or near the 82nd Ave. of Roses to engage in walking education and encouragement activities during the 12-month period from October 1, 2007 and ending September 30, 2008. |
|  | 10/1/2007 | 9/30/2008 | Develop an evaluation tool to identify traffic safety concerns and perceptions along the 82nd Ave. of Roses after implementation of the 3-Es identified by the Technical Advisory Committee during the 12-month period from October 1, 2007 through September 30, 2008. |

IV.	Proposed Activities

A.	Major Activities

(List major activities to be carried out to achieve objectives stated in Section II above. List the start and end date for each activity, and include in your description what will be done, who will do it, and who will be affected.)

|  | Start Date | End Date | Activity |
| --- | --- | --- | --- |
|  | 10/1/2007 | 9/30/2008 | What: Distribute and collect the 82nd Ave. of Roses High Crash Corridor safety surveys from community members. Translate into multiple languages if necessary. Who: PDOT Staff Who Affected: Individuals that use the 82nd Ave. of Roses - residents, business owners, etc. |
|  | 10/1/2007 | 9/30/2008 | What: Develop a Safety Action Plan Matrix that identifies safety issues, potential near term actions that can be completed within 1-2 years, funding status, next steps, and long term actions. Who: PDOT staff Who Affected: Residents, businesses, PDOT, ODOT, TriMet, etc. |
|  | 10/1/2007 | 9/30/2008 | What: Encourage and record stakeholder commitments to provide staff and/or funding to support the Safety Action Plan Matrix. Who: PDOT staff Who Affected: Residents, businesses, PDOT, ODOT, TriMet, etc. |
|  | 10/1/2007 | 9/30/2008 | What: Research existing models and discuss alternative methods for determining the placement of pedestrian refuge median islands along the 82nd Ave. Roses. Who: PDOT staff Who Affected: Residents, businesses, PDOT, ODOT, TriMet, etc. |
|  | 10/1/2007 | 9/30/2008 | What: Implement the 3-Es identified in the Safety Action Plan Matrix. Who: PDOT and ODOT staff Who Affected: PDOT, ODOT, TriMet, PPB, Schools, BTA, Alta Planning & Design, ONI, Legacy Emanuel Hospital, Multnomah County Courts, PAC, Business Associations, Neighborhood Associations, Media, Elders In Action, WPC. |

Plans for sharing the project activities with others:

This project will develop and foster healthy and sustainable public dialogue around Portland’s traffic safety issues through the City Council-supported Safe Communities Coordination Council Coalition. In addition, Safe Community Grant project details will be shared with the media, Portland Neighborhood Associations, Business Associations, and other community groups.

B.	Coordination

(List the groups and agencies with which you will be cooperating to complete the activities of the project. Explain how you will be working together.  Include Letters of Commitment in Exhibit C if you will be relying on other agencies to accomplish the objectives of the project.   In those projects not requiring the involvement of other agencies, a statement justifying the ability of the applicant to carry out the project independently should be included.)

Is coordination with outside agencies or groups required? If yes, check here:

1) If you checked the box above, please fill in the following. Otherwise skip to item 2) below:

Name/role of groups and agencies involved:

Safe Communities Coordination Council Coalition – project lead PDOT and ODOT – engineering PDOT, ODOT, TriMet, ONI, Elders In Action, Legacy Emanuel Hospital, Multnomah County Courts – education Portland Police Bureau – enforcement

2) Fill this if you did not check the box above:

Ability to complete the project independently:

C.	Continuation

Plans to continue the project activities after funding ceases:

The Safe Communities Coordination Council Coalition will continue to develop, implement, monitor, and evaluate traffic safety services. A Community and School Traffic Safety Account was established with increased traffic fine revenue.

V.	Evaluation Plan

A.	Evaluation Questions

## (You will be reporting on your objectives in your Project Evaluation. At a minimum each objective should be rephrased as an evaluation question. For example, what percentage of the public in (funded jurisdiction) wears a safety belt?  What percentage increase is this?  Add questions that demonstrate expected or potential impact of the project on the state or jurisdiction's traffic safety environment. Avoid yes/no evaluation questions.)

|  | Evaluation Question |
| --- | --- |
|  | How many people responded to the survey? Where were the surveys distributed? From what zip codes were the survey respondents? Was outreach conducted to include non-English speaking and/or low-income community members? |
|  | What is the number of injuries/fatalities at the 82nd Ave. of Roses? What transportation safety systems were proposed to improve transportation safety strategies along the 82nd Ave. of Roses? What organizational and community stakeholders were involved and how often did they meet? What strategies were implemented? |
|  | What commitments did organizational stakeholders make to improve traffic safety along the 82nd Ave. of Roses? Did organizational stakeholders follow-through on their commitments? What was the total dollar amount invested? |
|  | What methodology was developed to prioritize installations for pedestrian median refuge islands? What other models were examined? |
|  | Was a “typical” pedestrian refuge median island model developed that could be utilized along the 82nd Ave. of Roses? What was the process used to develop the prototype? |
|  | Was an inventory of existing sidewalk conditions developed? What the inventory shared with community stakeholders? Was a plan developed to correct deficiencies and were any deficiencies corrected? |
|  | Was a pedestrian safety campaign created? What were the components? Who were the partners? How was it delivered to the community? How many pedestrian safety trainings were delivered and how many people attended? |
|  | Was a transit safety campaign created? What were the components? Who were the partners? How was it delivered to the community? Describe how community stakeholder and members of the media participated. |
|  | Was an aggressive driver campaign created? What were the components? Who were the partners? How was it delivered to the community? Describe how community stakeholder and members of the media participated. |
|  | How many pedestrian crosswalk and/or intersection safety enforcement actions were conducted? Describe how community stakeholder and members of the media participated. |
|  | How many programs for older people living at or near the 82nd Ave. of Roses were implemented? What programs or services were offered? How many people participated? We non-English speaking community members involved? |
|  | Was an evaluation tool developed? Have there been changes in the number of pedestrian, bicycle, and/or vehicle collisions along the 82nd Ave. of Roses? Has the perception of transportation safety changed? |

B.	Data Requirements

1.      Data to be collected: The Data Table presented as Exhibit A will be submitted with required quarterly reports.

2.      Data System

Describe how the data will be collected, stored, and tabulated:

Information from Police Bureau enforcement actions, SAFE locations, and DMV crash reports, and more will be available for review. Staff will track delivery of project activities and community participation in the activities.

C.	Evaluation Design

Describe how the data will be analyzed:

The Safe Communities Coalition will correlate Police enforcement actions with crash histories and traffic safety service requests in an attempt to show clear relationships between enforcement, public safety concerns, and improvements to public safety.

D.	Project Evaluation Preparation

A Project Evaluation Report will be submitted to TSD following the requirements given in the Agreements and Assurances, Section B, Paragraph 6.

### VI.	Grant Project Budget Summary

- List of major budget items:

Materials: Research report, senior walking and cycle incentives, Ped Crosswalk Safety video, young driver bumper stickers, yard signs Equipment: Older adult 3-wheel cycle storage and trailer, speed-reader boards & deployment needs Staff: TRI Staff

- Budget Allotment

The agency named in this document hereby applies for $100,000.00  in Transportation Safety funds to be matched with $0.00 in funds from source Portland Office of Transportation to carry out a traffic safety project described in this document.

VII.	Budget and Cost Sharing

(Complete Form 737-1003 Budget and Cost Sharing.  You may attach one page to explain specific requests.  If you are applying for a multiple-year grant, you must include a separate budget for each year for which you are requesting funding.)

# VIII.	Exhibits

A.	Exhibit A: Data Table

(To be developed at a later date.)

B.	Exhibit B: Job Descriptions

(Provide copy of job descriptions of all positions assigned to the project 500 hours or more paid with grant funds.)

C.	Exhibit C: Letters of Commitment

(Provide copies of letters of commitment from those agencies you will be relying upon to accomplish the objectives of the project.)

D.	Exhibit D: Conditions of Approval

(To be developed at a later date.)

IX.	Agreements and Assurances

(READ, but do not sign until grant is approved by TSD and returned to you for signature.  Do not attach to the grant project application.)

X.	Approval Signatures

I have read and understand the Agreements and Assurances stipulating the conditions under which the funds for which are being applied will be available and can be utilized. The agency named in this document is prepared to become a recipient of the funds should the grant funds be awarded.

A. 	Agency Information

| Agency Name*: | Portland, City of |
| --- | --- |
| Street Address: | 1120 SW 5th Avenue |
| City: | Portland |
| State: | OR |
| Zip: | 97204 |

- Project Director

| First Name: | Robert | Last Name: | Burchfield |
| --- | --- | --- | --- |
| Title: | Traffic Operations Manager | Email: | robert.burchfield@pdxtrans.org |
| Phone: | (503) 823-7604 | Fax: | (503) 823-5175 |
| Street Address: | 1120 SW 5th Avenue |  |
| City: | Portland |  |
| State: | OR |  |
| Zip: | 97204 |  |

Signature: ___________________________________ Date: ________________

- Authorizing Official of Agency Completing Application

| First Name: | Tom | Last Name: | Potter |
| --- | --- | --- | --- |
| Title: | Mayor | Email: | tpotter@ci.portland.or.us |
| Phone: | (503) 823-4120 | Fax: | (503) 823-3588 |
| Street Address: | 1221 SW 4th Ave., Suite 340 |  |
| City: | Portland |  |
| State: | OR |  |
| Zip: | 97204 |  |

Signature: ___________________________________ Date: ________________

*Non-profit agencies must submit proof of exempt status under Code Sec. 501(c)(3)

Mail signed copies to: 	Oregon Dept. of Transportation

Transportation Safety Division

235 Union Street NE

Salem, OR 97301-1054

Email completed electronic copy to your TSD Program Manager.