## INTERGOVERNMENTAL AGREEMENT

## BETWEEN TRIMET AND CITY OF PORTLAND

## FOR I-205 LIGHT RAIL PROJECT DESIGN AND CONSTRUCTION MANAGEMENT SERVICES

This i-205 light rail PROJECT DESIGN AND CONSTRUCTION MANAGEMENT SERVICES Agreement (“Agreement”) is between the TRI-COUNTY METROPOLITAN TRANSPORTATION DISTRICT OF OREGON (“TriMet”) and the CITY OF PORTLAND (“City”) (collectively hereinafter referred to as “the Parties”), effective this __________day of _________________, 2007.

# RECITALS

- TriMet owns and operates the public mass transit system serving the tri-county area of Multnomah, Washington and Clackamas Counties.

- Following public notice and a public hearing, on April 17, 2003, the Metro Council, upon recommendation of the City Council and the TriMet Board of Directors, among others, formally adopted the South Corridor Project Locally Preferred Alternative (“LPA”).  The LPA provides for a two-phased major investment strategy for light rail in the South Corridor, and identifies the next light rail project for construction as light rail on I-205 between Clackamas Town Center and Gateway (the “I-205 Project”), and light rail on the Portland Transit Mall (the “Portland Mall Revitalization Project” or “Project”) (collectively, the “South Corridor Project”).  This LPA decision was confirmed in January of 2004 to include the Portland Mall from the Steel Bridge to Portland State University.

- The City Council has identified the South Corridor Project as the region’s next priority rail transportation project and has confirmed its support through Resolution No. 36130 adopted March 19, 2003.

- On or about November 30, 2004, the Federal Transit Administration (“FTA”), Federal Highway Administration (“FHWA”), Metro and TriMet published the Final Environmental Impact Statement (“FEIS”) for the South Corridor Project.

- Under the authority of House Bill 3478 (Oregon Laws 1996, Chapter 12, hereinafter the “Act”), on January 15, 2004, the Metro Council adopted a Land Use Final Order Amendment for the South Corridor Project.

- The Act defines the relationship between TriMet and other governmental entities following the adoption of a land use final order, and states:  “The state, and all affected counties, cities, special districts and political subdivisions shall:

(a)	Amend their comprehensive or functional plans, including public facility plans and transportation system plans and their land use regulations, to the extent necessary to make them consistent with a Land Use Final Order; and

- Issue the appropriate development approvals, permits, licenses and certificates necessary for the construction of the project or project extension consistent with a land use final order.  Development approvals, permits, licenses and certificates may be subject to reasonable and necessary conditions of approval, but may not, by themselves or cumulatively, prevent implementation of a Land Use Final Order.”

- In March 2004, the FTA authorized TriMet to enter into the preliminary engineering stage of project development.

- The City Council approved Ordinance No 178673 on August 11, 2004 approving the “I-205/Mall Light Rail Project Intergovernmental Grant Agreement between TriMet and the City of Portland” (“Grant Agreement”) for the City’s financial contributions to fund the South Corridor Project, which was subsequently amended in December 2004 by Ordinance No. 178964.

- In October 2005, FTA authorized TriMet to enter into the final design stage of project development.

- TriMet cannot construct or implement the Project without the use of City right-of-way and/or property. The City is willing to allow TriMet to use City right-of-way and/or property without being compensated for such use.

- The City has a duty to the general public to provide safe and convenient streets and to protect itself from unreasonable financial burdens imposed by TriMet’s use of the streets.

- Those portions of the Project that will occupy Oregon Department of Transportation (“ODOT”) or Clackamas County right-of-way are subject to separate agreements between TriMet and ODOT or Clackamas County, respectively.

- The Project is, or will be, subject to budgetary limitations imposed by the FTA and Finance Agreements, and all terms and conditions of the FTA Full Funding Grant Agreement as a result of Federal participation in costs of the Project.

- The Parties have identified the following objectives with respect to the Project:

- Build the Project within budget and on-schedule,

- Demonstrate that light rail can be constructed in a cost-effective manner, and

- Develop the best-qualified team for management of the Project

- The Parties desire to enter into this Agreement to document each party’s understandings and agreements relating to the design and construction phases of the Project.

- The Parties shall enter into a continuing control agreement to satisfy FTA’s requirements for a permanent right of TriMet to operate on City right-of-way and/or property, upon completion of Project construction.

17.	Upon completion of Project construction, the parties plan to enter into a maintenance agreement that will detail each party’s obligations with respect to maintenance of the facilities.

NOW THEREFORE, the premises being in general as stated in the foregoing recitals, it is agreed by and between the Parties hereto as follows.

# AGREEMENT

# Article I – TERM

The term of this Agreement shall be effective from March 25, 2004 through June 30, 2010 unless terminated or extended under the provisions of this Agreement.

#### ARTICLE II – TRIMET OBLIGATIONS

- Responsibility for the Project.  Except as otherwise provided herein, TriMet shall design, construct, operate and pay all costs for the Project, in accordance with the Project’s funding arrangements. In the execution of the design and construction, except as otherwise provided herein, TriMet shall provide for the public’s health, safety, and welfare by providing the proper construction, reconstruction, and modifications to those existing public facilities in the City’s public right-of-way which are affected by the Project.

- Construction Standards for the Project.  TriMet shall use current City Standard Construction Specifications and standard drawings, except as amended and approved by the City Engineer, for all portions of the Project that will ultimately be owned and/or maintained by the City.

- City Requests and Payment for Additional Work.  TriMet shall design and construct, at the City’s expense, any Betterment (as that term is defined in Article IV, Section T below) identified and requested by the City that enhances the basic Project or public improvements in the vicinity of the light rail alignment.

- Development of Preliminary Engineering Documents.  TriMet submitted to the City copies of the preliminary engineering design (PE) documents that serve as the starting point for undertaking final design. The City will have an opportunity to review TriMet’s PE documents and provide comments for resolution during final design, including comments from involved City Bureaus, Council Persons, and Advisory Committees in accordance with the Project Milestones and Schedule, a copy of which is attached hereto as Exhibit A – Project Milestones and Schedule.  TriMet shall provide a response to the City identifying how these comments and issues will be approached during the final design of the Project.

- Development of Final Plans and Specifications.  TriMet and its Design/Build Contractor (“DB”) shall work in close cooperation with the City during preparation of final engineered plans and will submit plans and specifications (hereafter “Plans”) for official City review at the deliverable stages established by the Project, currently anticipated to be the 50%, Permit submittal, and Issued For Construction (“IFC”) completion points.

The 50% stage is the first draft of final design drawings and specifications. Other City Bureau and Commission review, to the extent required by City Code and not previously satisfied, shall be undertaken based on the 50% stage submission. This stage will include the identification and specification of all major construction work.  The Permit submittal stage is the second draft of final design drawings and specifications. It has incorporated the required changes and revisions identified at the 50% submittal stage and is to be used for permit applications.  The IFC stage is defined as the completion of all required changes and revisions identified at the Permit submittal stage. The IFC stage is intended for construction purposes, not comment and review.  However, unaddressed comments from previous reviews leading to City required changes at the IFC stage may be incorporated by addendum into construction documents.

The City and TriMet shall cooperate and exercise good faith efforts to provide documents, review and comment, and resolve comments on plans and specifications so that the Project schedule milestones identified in Exhibit A are met.  The Parties agree that should the Project schedule be revised in the future, they shall make best efforts to comply with the updated schedule milestones.

The Parties understand that City review times shall not commence until all elements appropriately included at each stage are incorporated into the submission at a level of detail that allows effective and efficient review by the City. The City shall use its best efforts to minimize the review times, however it is anticipated that a three week City review period will be needed at the 50% and Permit stages.

TriMet shall maintain records of all comments received from City reviews, including TriMet response and action taken.

- Preliminary List of Anticipated Project Approvals.  TriMet’s Project Manager, or its designee, shall work with the City’s Project Manager or its designee, to develop an agreed upon list of permits and approvals necessary for Project construction.  The list may include but not be limited to:  (1) conditional use approvals, (2) zoning adjustments (3) sign encroachment variances or waivers, (4) design review permits, (5) building and/or construction permits, (6) variances, and (7) occupancy permits.

- Issuance of Permits.  Following the City Engineer’s approval of the final plans for the Project and prior to construction, the City shall issue the appropriate permits, including a Construction Permit.  Anticipated permits are attached hereto as Exhibit B.

- Relocation of Utilities.  The City shall use its best efforts to cause relocation of privately-owned utilities without cost to the City or Project, as provided in Article III, paragraph C below.  However, if the City does not have the legal authority or power to cause such relocation, TriMet, without cost to the City, shall effect relocation of existing privately-owned utility facilities as necessary to conform utilities or facilities to the plans for the Project. The cost of relocating in-kind publicly owned utilities for purposes of the Project shall be at TriMet’s expense or shared between Parties based on contributions by The Bureau of Environmental Services (BES) and The Portland Water Bureau (PWB) as provided in this Agreement.  The Parties understand that relocation in-kind does not include Betterment(s) of the existing facilities.

- Inspection of Relocated Utilities.  TriMet shall also allow City engineers and/or inspectors or consulting engineers/inspectors to inspect any relocation of utility conduits, lines, poles, mains, pipes, and other facilities (including stray current mitigation measures) in order to determine whether they have been relocated or installed in accordance with the contract documents and the City/TriMet Agreement for the Project.

- Real Property Acquisition/Relocation Assistance.  TriMet shall be solely responsible for the acquisition of real property or interests therein for the Project, including property that will eventually become City right-of-way.  For property that will become City right-of-way, TriMet shall use standard City forms, terms, and conditions and shall obtain review and approval from the City of Portland Office of Transportation’s real property group.  TriMet shall also acquire all other property needed for the Project.  TriMet shall be responsible for providing any relocation assistance required for the Project, and such relocation assistance shall be pursuant to the Uniform Relocation Assistance and Real Property Acquisition Policies Act and other applicable Federal, State, and local laws.

- Staffing Plan.  TriMet’s Resident Engineer for the Project, under the direction of TriMet’s Project Director and the City’s Project Manager, shall create a staffing plan for construction of the Project.  Staffing for key positions shall be jointly agreed to by the City’s Director of the Office of Transportation and TriMet’s Executive Director of Capital Projects and Facilities.

- Contractor Selection, Oversight, and Payment.  TriMet will prepare procurement and contract documents, make the DB selection, manage and enforce provisions of the DB contracts, and make payments to the DB.

- Community Relations.  TriMet shall perform all community relations functions and keep the City Project Manager apprised of all activities.

- Issue Resolution.  It is understood by both Parties that a project of this size and complexity will raise issues requiring speedy resolution. In the event of any issues or disputes between the City and TriMet, it is understood by both Parties that the dispute shall be referred for resolution as follows:

    - Refer the dispute to the City Project Manager and TriMet’s Project Manager, who shall make a good faith effort to resolve it;

    - If unresolved, refer it to City of Portland’s Office of Transportation Director and to TriMet’s Executive Director of Capital Projects and Facilities Management;

    - If unresolved, refer it to the City’s Commissioner-in-Charge of Transportation and TriMet’s General Manager for resolution.

In the event that any of the issues or disputes relating to facilities owned and maintained by City bureaus other than PDOT, the corresponding bureau Project Manager, Bureau Director, or Commissioner-in-Charge will participate in resolving the issue.

O.	Changes to the Work.

- TriMet and the City agree to make timely responses as appropriate and required to keep the work progressing.

- Changes directed by the City.  Subject to the terms of this Agreement, TriMet acknowledges that the City, as permitting authority, can order changes to the work being performed in the public right-of-way as it considers necessary, and within the general scope and limits of the Project’s street, structural, sewer and water construction contracts.  In the event that TriMet disagrees with the City’s change directive, the issue will be resolved through the Issue Resolution process described above.

- Changes proposed by TriMet.  All changes proposed by TriMet, or others, which would impact work authorized by the Permit or by this Agreement will be submitted to the City Project Manager for review and approval.  The City Project Manager will coordinate any necessary reviews by City Bureaus, citizen groups, or other interested parties, as appropriate, and return a decision to TriMet as required to meet contract milestones or keep the work progressing.

- TriMet will handle any claims by the DB for change orders and will not look to the City for reimbursement or compensation for any such changes except when those changes are agreed by both Parties to be City Betterments.  Should changes result in added work by the City, the City Project Manager shall submit an estimate of added costs to TriMet.  TriMet shall review the estimate and negotiate a modification to this Agreement for added work.

P.	Services to be Provided by TriMet.  TriMet shall provide the following services through its own forces or by contract:

- Civil Design Consultants

- System Design Consultants

- Construction Inspectors

- Materials Testing and Survey Services

In addition, TriMet shall provide the following support services:

- Review, along with others of the construction management team (as defined in Article II, Section K above), the shop drawings and other contractor submittals.

- Certify substantial and final completion of the light rail transit (“LRT”) elements of the work (including but not limited to trackwork and stations) pursuant to the Project construction contract.

- Review and approve monthly progress payments.

- Review and recommend approval of Change Requests and Change Orders in accordance with contract management procedures and this Agreement.

- Coordinate with City’s Project Manager regarding work activities as they impact adjacent properties and businesses.

- Provide inspection, along with others from the project team, for the work provided below.

- Accept the completed work for maintenance in accordance with maintenance agreement(s) to be approved by TriMet and the City and warranty provisions of construction and materials contracts.

- Construct any City Betterments to the Project or associated work (as defined below) for which the City has agreed to reimburse TriMet.

- Assist City in its obligation to comply with all federal provisions prescribed for third-party contracts by the federal grant agreement, as set forth in Article III.L.

Q.	TriMet Staff.  TriMet shall assign the following personnel to the Project:

- Project Director

- Resident Engineer

- Assistant Resident Engineer

- Inspectors as agreed to between the City and TriMet

- Office Engineer

- Community Affairs Specialists for community relations work, media releases, newsletters, and other special events

- Design support staff during construction

R.	Easements.  TriMet shall obtain construction and permanent easements for all TriMet, private and City facilities, outside of City right-of-way.  Permanent easements for City facilities shall use standard City form, terms, and conditions and shall be reviewed and approved by the appropriate City Bureau.

S. Maintenance Agreement.  TriMet shall, in good faith, prepare and negotiate with the City and others as appropriate a maintenance agreement that defines maintenance responsibilities for the Project.

T. Continuing Control Agreement.  TriMet shall, in good faith, prepare and negotiate with City a continuing control agreement.  The parties understand and agree that the continuing control agreement will provide for the permanent use of City streets and other City property necessary for construction, operation and maintenance of those elements of the Project within City right-of-way, in accordance with the continuing control requirements of federal law as administered by the Federal Transit Administration.

# Article III – City Obligations

A.	Project Design Standard.  The City and TriMet agree that starting point for the final design of the Project shall be the final PE Program Requirements, dated September 30, 2004, together with City comments.  The documents, together with TriMet response to City comments, and other work products developed between September 30, 2004 and the start of final engineering shall be the design standard for the Project.

B. Maintaining Project Schedule.  The City agrees to use its best efforts to assist TriMet in maintaining the Project schedule.  To this end, City staff shall assist TriMet with all permit/approval processes including, but not limited to, scheduling all hearings and briefings before City Council, commissions or other City entities.

C.	Relocations in Right-of-Way.  The City, at TriMet’s expense unless otherwise apportioned in this Agreement, shall relocate, cause to be relocated, or assist in the relocation of all City-owned conduits, lines, poles, mains, pipes, and other facilities, whether located within the public right-of-way or not, as required by the Project. The Project plans and specifications shall include all relocations necessary to conform facilities to the Project. The City shall endeavor to conduct this relocation work in accordance with the Construction Phasing/Scheduling Plan for the Project.

The City shall cause the owners of privately-owned utility conduits, lines, poles, mains, pipes and other facilities in or on City rights-of-way and/or property to relocate their facilities at the expense of said privately-owned utility as necessary to conform to the Project, to the extent the City has the power to do so. The City shall endeavor to cause this relocation work to be accomplished in accordance with Construction Phasing/Scheduling Plan for the Project.

The City shall allow TriMet participation in review of utility relocation plans submitted by public and private utilities for the alignment area. The City shall also allow TriMet engineers or inspectors or consulting engineers or inspectors to inspect any relocation of utility conduits, lines, poles, mains, pipes, and other facilities in order to determine whether they have been relocated in accordance with the plans of the Project.

D.	Issuance of Construction Permit.  In accordance with the provisions of this Agreement, the City shall issue a Construction Permit for the Project within the City right-of-way that shall permit Project construction based on the end products referred to in Article V.

E.	End Products.  The City agrees to provide the end products identified as its responsibility in Article V of this Agreement, or a reasonable substitute product as agreed by the Parties.

F.	Coordination of City Issues.  The City Project Manager shall coordinate comments from all City bureaus and shall assist in resolution of all Project issues raised by any City bureau.

G.	Managing Services within Budget.  The City Project Manager shall exercise good faith efforts to manage the City services within the budget specified in this Agreement.

H.	Permits and Approvals.  The City Project Manager, or designee shall assist TriMet in developing a list of the permits or approvals necessary to complete the Project construction and installation.

I.	City Staffing.  City shall make available during design and construction the persons and resources identified in the staffing plan attached as Exhibit C.

J.	Continuing Control Agreement.  City shall, in good faith, negotiate with TriMet a continuing control agreement.  The parties understand and agree that the continuing control agreement will provide for the permanent use of City streets and other City property necessary for construction, operation and maintenance of those elements of the Project within City right-of-way, in accordance with the continuing control requirements of federal law as administered by the Federal Transit Administration.

K.	Maintenance Agreement. City shall, in good faith, negotiate with TriMet and others as appropriate the TriMet-developed maintenance agreement that defines the maintenance responsibilities for the Project.

L.	Federal Funding Limitation.	 The parties understand that federal funds will be used to pay for a portion of the Project.  To the extent applicable to each of the respective parties, this Agreement is subject to all federal provisions prescribed for third-party contracts by the federal grant agreement.

Article IV – City Services to be ProvideD to TriMet

A.	City Staffing Plan.  The City shall provide services in conjunction with the project’s final design and construction as described in this Article.  City shall make available during design and construction the persons identified in the “I-205 Light Rail Project Staffing Plan” attached as Exhibit C.

B.	Ensuring No Adverse Effects to City.  The City’s services are intended to ensure:   (1) that the City’s facilities and operations within the public right-of-way are adequately provided for; (2) that the City’s facilities and operation outside the public right-of-way are not adversely affected; (3) that vehicular, bicycle and pedestrian traffic is adequately provided for; and (4) that public health, safety, and welfare, including without limitation aesthetic, environmental, and commercial values, are not adversely affected.

C.	City Services – General.  Each City bureau or agency with Code authority or other responsibility over the Project shall provide to TriMet the following services:

1.	Supply copies of all available file data on all existing facilities as requested by TriMet for the Project. The City has found the completeness and accuracy of this file information to be inadequate when used as the sole basis for design and construction purposes and recommends verification before incorporation into any final design. Any reliance on the data by TriMet shall be at its own risk.

2.	Review, require revisions to, and approve the Project plans as provided for in this Agreement.

3.	Cooperate fully with the City’s Project Manager, TriMet’s Project Manager, and City and TriMet designated representatives as reasonably necessary to assist in the timely and proper completion of the Project.

D.	Noise Control.  All work performed by City Bureaus under this section shall comply with the terms and conditions of Noise Variance(s) obtained by TriMet and/or TriMet’s contractor for the Project.

E.	Portland Office of Transportation.

1.	Bureau of Transportation Engineering and Development.	Under the coordination of the City’s Project Manager, the Bureau of Transportation Engineering and Development shall provide services as described below:

(a)	Act as the lead City agency in carrying out the City’s obligations and exercising the City’s rights under this Agreement.

(b) Provide as necessary, services of the City’s Project Director, Project Manager, and other positions as identified in the Agreement.

(c )	Assist TriMet in coordinating the relocation of all publicly owned utilities.

(d) Assist in and coordinate all plan reviews, including structures.

(e)	Assist in resolution of all design and construction issues.

(f)	Coordinate and track compliance with all City permits.

(g)	Provide assistance in City budget development, monitoring, tracking, and billing for all City bureaus and other entities.

(h)	Provide necessary staffing and support services for the right-of-way acquisition of parcels to be owned or controlled by the City upon completion of construction.

2.	Traffic Design Section.  Under the coordination of the City’s Project Manager, the Bureau of Transportation Engineering and Development’s Traffic Design Section shall provide services as described below:

(a)	Review, require revisions to, and approve plans for all pavement markings, traffic signs, and other work affecting vehicular, bicycle and pedestrian traffic within City right-of-way. Notify the City’s Project Manager of all required revisions, for forwarding to TriMet.

(b)	Participate in the development of construction phasing plans for incorporation into construction documents.

(c )	Assist in resolution of all traffic related design and construction issues.

3.	Bureau of Transportation System Management.	Under the coordination of the City’s Project Manager, the Bureau of Transportation System Management shall provide services as described below:

(a)	Assign a single Project Coordinator/point of contact for all work performed under this Agreement, and coordinate all work and information covered under this Agreement with the City’s Project Manager.

(b)	Review, require revisions to, and approve plans for all traffic signaling devices and other work affecting vehicular, bicycle and pedestrian traffic within City right-of-way. Notify the City’s Project Manager of all required revisions, for forwarding to TriMet. Provide inspection services during construction.

(c )	Participate in the development of construction phasing plans for incorporation into construction documents.

(d)	Review, require revisions to, and approve plans for all City street lighting facilities, as needed. Notify the City’s Project Manager of all required revisions, for forwarding to TriMet.  Provide inspection services during construction.

(e)	Perform traffic signal modifications and signal activation/deactivation as required by TriMet, the City, and/or the Contractor.  Inspect new signals and provide turn-on services.

(f)	Develop signal timing plans as needed for construction and for final operation.

4.	Bureau of Maintenance.  Office of Transportation Bureau of Maintenance will install permanent parking/truck loading signs upon project completion. The scope of services during construction (signal turn on/offs, temporary striping and/or signage) will be determined based on IFC construction plans and this agreement will be amended as necessary.

5.	Transportation Planning Division.  Under the coordination of the City’s Project Manager, the Transportation Planning Division shall provide services as described below:

(a)	Assign a single Project Coordinator/point of contact for all work performed under this Agreement, and coordinate all work and information covered under this Agreement with the City’s Project Manager.

F.  Bureau of Environmental Services (“BES”).	 Under coordination with the City’s Project Manager, BES shall provide services as described below:

1.	Assign a single Project Coordinator/point of contact for all sewer relocation work performed under this Agreement, and coordinate all said work and information under this Agreement with the City’s Project Manager.

2.	Assign a single Project Coordinator as the point of contact for all work related to implementation of the City’s “Stormwater Management” Manual.

3.	Review, require revisions to, and approve plans for all storm, sanitary, and combined sewerage facilities. Notify the City’s Project Manager of all required revisions, for forwarding to TriMet.

4.	Adhere to the “Understandings” as agreed and identified in the Memorandum of Understanding attached as Exhibit D.

G.	Portland Water Bureau (“PWB”).	Under the coordination of the City’s Project Manager, PWB shall provide services as described below:

1.	Assign a single Project Coordinator/point of contact for all work performed under this Agreement, and coordinate all work and information under this Agreement with the City’s Project Manager.

2.	Provide design and construction project management of water relocations, improvements, and Betterments included in the Project.

3.	Make all permanent and temporary connections to water system, install valves and hydrants, service and vault installations and provide verifications of existing facilities (potholing) as indicated in the construction contract documents.

4.	Provide inspection services and engineering support services related to water relocations, improvements and Betterments during construction.

5.	Use its best efforts to accomplish all work in accordance with the Construction Phasing/Scheduling plan for the Project.

6.	Adhere to the “Understandings” as agreed and identified in the Memorandum of Understanding attached as Exhibit E.

H.	Bureau of Development Services (“BDS”).  Under the coordination of the City’s Project Manager, BDS shall provide services as described below:

1. Assign two Project Coordinators/points of contact (a Lead Planner and a Lead Plans Examiner) for all work performed under this Agreement, and coordinate all work and information under this Agreement with the City’s Project Manager.

2.	Assist in the identification of all Project elements located outside of City of Portland right-of-way requiring a land use approval or building permit. Assist in the processing of the land use approvals and/or building permits for the Project elements needing those approvals and/or permits. Review of these portions of the system shall be conducted according to the requirements of the Oregon State Specialty Codes, appropriate NFPA standards, and pertinent portions of Portland City Code Titles 24, 25, 26, 27, 32, and 33.  Review times shall conform to the requirements the City Code.  BDS shall exercise good faith efforts to review Project plans and specifications in a timely manner consistent with the Project schedule. Upon satisfactory completion of this and other reviews required by this Agreement, BDS shall issue necessary construction permit(s).

3.	Review and issues permits as needed for Project such as building, plumbing, and electrical work.

4.	Perform design, environmental, historic, design reviews and other land use actions as required.

5.	Perform building permit inspection and zoning code enforcement as needed.

6.	Assist with assignment of addresses for pay phones, buildings, and stations.

7.	The parties understand and agree that (1) the City will require Land Use review (Conditional Use) and building permits for Park and Ride lots located within ODOT right-of-way; (2) ODOT will not require building permits for work within ODOT right-of-way; and (3) TriMet will inspect all work in ODOT right-of-way requiring a City building permit, because the City Bureau of Development Services does not have inspection authority in ODOT right-of-way.

I.	Bureau of Parks and Recreation (“Parks”).	Under the coordination of the City’s Project Manager, Parks’ planning and development section shall provide services as described below:

1.	Assign a single Project Coordinator/point of contact for all work performed under this Agreement, and coordinate all work and information under this Agreement with the City’s Project Manager.

2.	Review and approve plans for street trees and monitor existing street tree removals and new street tree installations.

3.	Review and approve plans for landscaping installation in City right-of-way.

4.	Review and comment on plans and construction documents for improvements affecting Parks’ properties along the approved alignment.

5.	Review plans and construction documents for consistency and coordination with planned and existing trail locations and connections.

6.	Issue permit for construction activities occurring in and around the Springwater Corridor.

J.	Additional Support Services.  In addition to the services outlined above, during construction, the City shall provide the following support services:

1.	Review, along with other members of the construction management team (as identified in Article II, Section K), the shop drawings and other contractor submittals.

2.	Certify final completion and acceptance of work pursuant to City permit(s).

3.	Review and approve the portions of monthly progress payments related to work that is to be reimbursed by the City.

4.	Review and approve changes to the work covered under the Construction Permit in accordance with this Agreement.

5.	Coordinate with TriMet regarding work activities as they impact adjacent properties and businesses.

6.	Provide inspection, along with others from the construction management team, of the work, as provided below.

7.	Accept the completed work from TriMet’s contractors for maintenance consistent with maintenance agreement(s) to be approved by TriMet and the City, and warranty provisions of the Construction Permit.

8.	Pay for Betterments or other improvements that the City desires incorporated into the Project.

9.	Provide TriMet a quarterly financial cost report identifying the City costs incurred under this Agreement during the quarter and for which the City expects payment under this Agreement.  The report shall also reflect any payments made to the City under this Agreement.

K.  City Staff.  City shall assign the following personnel to the Project:

1.  The City Project Manager

2.  City Project Engineer

3.  City Project Inspector

4.  Traffic Engineer

5.  Bureau Project Coordinators for PWB, BES, and Parks.

6.  Specialty inspectors for street lighting, signals, water and sewers as needed

L.  Inspection.

1.	TriMet shall conduct an inspection program.  At the City’s request, TriMet shall provide the City with complete daily inspection logs or reports.  If the City inspects work, the City shall complete daily inspection logs or reports, distribute such reports to TriMet, and notify TriMet of the recommendation of action based on such logs or reports.

2.	Either Party may assign specialty inspectors to the Project.  Specialty inspectors shall coordinate their inspections through the Chief Inspector, but will continue to report to their respective agency.

M.  Others.  Other City agencies and City bureaus with Code authority or other responsibilities over the Project shall provide the required services necessary to carry out their responsibilities as defined by the City Code. Compensation shall be under the City Code on a fee basis or as set forth in this Agreement.

N.  Compensation.

1. 	The City's compensation for services provided under this Agreement shall not exceed the amounts listed in subsection 3. below, without prior written authorization from TriMet. This amount is based upon the staffing plan for design and construction services, contained in Exhibit C.  In the event any or all City bureaus' actual costs reach these maximum amounts, the City shall be released from performing further services under this Agreement to the extent that TriMet fails to approve an increase in the maximum costs.

2. 	TriMet recognizes that the amounts listed in subsection 3. below are initial budget amounts and may change due to the preliminary nature of the data on which they are based.  TriMet agrees not to withhold the timely approval of additional resources without cause, subject to available budget.  Additionally, the parties agree that line item budgets may be reallocated within this Agreement when approved by the City and TriMet Project Managers, so long as the overall approved budget amount of this Agreement is not exceeded.

3. 	Estimated maximum costs for City Services.	The services provided by the City and the costs to TriMet under this Agreement shall not exceed the following unless the Parties execute a modification signed by authorized representatives.  Such services shall be provided on a reimbursable cost basis and are detailed as follows:

# Portland Office of Transportation									$461,000

Bureau of Environmental Services									$  99,500

Portland Water Bureau												$388,000

# Parks and Recreation												$  10,500

# Fire Marshal														Code Fee Basis

Bureau of Development Services									Code Fee Basis

# Other City Agencies												Code Fee Basis

O.	Method of Payment.	Subject to the limitations stated in this Agreement, TriMet agrees to pay the City's actual costs for the performance of the services required herein.  These costs are identified in Exhibit C, Staffing Plan, attached.  The actual cost shall include direct salary costs, fringe benefits, direct non-salary costs, and general overhead to be determined as follows:

1.	Direct Salary Costs and Fringe Benefits.	The cost of salaries, wages, and fringe benefits are determined as follows:

(a) Actual time computed at the applicable hourly payroll rate and fringe benefits earned with actual time.  The City’s salary rates for any time period shall be as set out in the official City Compensation Plan or as amended by the City Council for the particular period.

(b) Charges in addition to (a) above for vacation, sick leave, holiday, jury duty, and bereavement leave are authorized but shall be charged to the Project only in proportion to the time devoted to the Project.

2.  Direct Non-Salary.	Those reasonable costs directly incurred in fulfilling the terms of this Agreement, including, but not limited to, reproduction, telephone long distance, equipment rentals, and purchase of outside services requested by TriMet.

3.  General Overhead. The Portland Office of Transportation and the Bureaus of Parks, Water,

Environmental Services, and other bureaus as deemed necessary shall charge for general overhead as provided by Chapter 5.48 of the City Code.

P.  Payment for Permits.  During the design and construction of the Project, the City will provide services related to permits and land use approvals.  TriMet will be financially responsible for payment of these services during the design phase of the Project; TriMet’s contractor will provide payment during construction.

Q.  Invoices. 	With the exception of those services provided by Code fee basis, the City, through the Office of Finance and Administration, shall to the extent possible given limitations in its financial accounting system submit to TriMet monthly billings for reimbursable costs incurred since the previous billings. TriMet shall pay the City the balance due within thirty (30) days of receipt of such billings. Financial reports accompanying requests for reimbursement shall be in accordance with FTA requirements. TriMet shall review records for suitability and provide assistance as necessary to assure compliance with FTA requirements.

(1)	Invoices shall be supported by current time sheets for each month.  The Project Managers shall review the invoices and billings against the Project budget to provide real time cost tracking and budget management.

(2) The City Project Manager shall oversee the work of the various City Bureaus or Departments to the end that their work is completed within the staffing budget for that work.

(3)	Overtime premium pay (pay in excess of straight time) shall not be invoiced to TriMet unless TriMet’s Project Manager has specifically authorized overtime in advance of the work, or in the event of an emergency.

(4)	The fringe rate applied to overtime hours shall be an adjusted rate such that items are not included in both the regular hour fringe rate and the overtime fringe rate, unless such allocation is approved by TriMet.

R. Additional Services. TriMet will not pay any claim for additional services not specifically provided for herein, unless agreed to mutually by written modification of this Agreement.

S. Status of Contractor.  The City shall perform this Agreement as an independent contractor and its staff, even though they may be assigned full time to the Project, shall not be deemed employees of TriMet.

T. Betterments/Cost Sharing.  The City agrees to share in certain costs of the Project, as provided in the I-205/Mall Light Rail Project Intergovernmental Grant Agreement between TriMet and the City of Portland, as amended, and as further identified in this Agreement.  In addition, the City agrees that it shall specify and provide or pay costs for any Betterments that are incorporated into the Project at the request of the City.  The Parties shall, through modification of this Agreement, negotiate the work scope and cost of such Betterments prior to TriMet proceeding with the design and construction of such Betterments.  As used in this Agreement, “Betterment” shall mean replacement of existing infrastructure with new where the infrastructure is beyond its useful life, or replacement with a kind, size or type of infrastructure facility that differs from that existing as of the commencement of this Agreement.  If the facility is near the end of its useful life, “Betterment” shall include that portion of the cost associated with replacing new that is equivalent to the portion of the expended useful life when compared to the entire useful life.

U. Other City Project Costs.  At Project cost, the City shall provide all necessary services to properly coordinate with this Project all design and construction work related to or required by other City projects within or near this Project’s contract limits.

Further, the Parties recognize that in some instances it may be more cost effective or result in less public impact for certain other City project work to be performed under this Project.  For any such instances, the City and TriMet shall append and incorporate into this Agreement a separate Memo of Understanding that documents each particular cost or work sharing agreement.

TriMet shall not be responsible for any of the final, actual costs for other City project work that are transferred into and performed as part of this Project.  Preliminary cost estimates may not accurately reflect final, actual costs for which the City will be responsible.

The Parties agree that costs for other City projects may be appended and incorporated into this Agreement with prior written approval from TriMet during the term of this Agreement.

V. Construction Management.  As part of the scope of work under this Agreement, the City will be providing construction management services.  Prior to the start of construction, the Parties will, in good faith, negotiate any modifications as needed to provide more specificity to the Agreement.

## ARTICLE V – END PRODUCTS

A.	This Agreement is intended to enable TriMet, with City assistance, to perform all tasks necessary to ensure the successful design, construction, operation and maintenance of the Project.  Additionally, it allows for integration of Project facilities into the City's existing public and private improvements in a manner that ensures the protection of the public health, safety, and welfare. TriMet and the City acknowledge that amendments to this Agreement may be necessary to reflect changing conditions.

The purpose of this Article is to identify the end products that TriMet and the City cooperatively must produce or accomplish to accommodate construction of the Project.  The list of end products identified in this Article is not all-inclusive. The City or TriMet may identify other required end products during final design. The Parties may produce or accomplish individual end products at any time between the date this Agreement becomes effective and the City's issuance of the Construction Permit. Prior to issuance of the Construction Permit, the City will require the production or accomplishment and approval of all end products identified herein or added hereto.

B.	End Products. The lead agency designated for the following end products shall have primary responsibility for initiating and accomplishing those end products. It is understood, however, that the accomplishment of the end products will require the cooperative efforts of both Parties, and TriMet and the City agree to utilize their best efforts to this end.

1.  Detailed Final Plans and Specifications					Lead Agency:	TriMet

(a)  Baseline Project

(b)  Water, Sanitary and Storm Sewers relocation plans and specifications

(c) Public Utility Relocations Plans.  Private utility plan and specifications will be completed by the private utilities themselves

(e) City Requested Extra Work/Betterments. Plans, specifications and bid documents for any such extra work shall be structured so that actual bid prices, construction costs, extra billings, post construction claims, and any and all other cost items are clearly separated from the baseline Project costs.

2.	Approval of Final Design									Lead Agency:	City

Within the framework established by the Act, design and permit approvals involving:

        - City Bureaus with City Charter or City Code Responsibility

        - Sewer, Water, Utility Relocations

        - Improvements within City right-of-way unrelated to Project

        - Private property improvements unrelated to Project

        - City Council

3.	Construction Phasing/Scheduling Plan						Lead Agency:	TriMet

(a)	Project Overall

(b)	Sewer, Water, Utility Relocations windows

(c)	Improvements within City right-of-way unrelated to Project

(d)	Private property improvements unrelated to Project

4.	Public Information/property owner liaison plan			Lead Agency: 	TriMet

5.	Conduct of Construction Plan								Lead Agency:	TriMet

To be completed on a per work-task basis, as needed.

(a)	Protection of public and private property provisions

(b)	Dirt/Debris Mitigation Provisions

(c)	Construction Drainage and Erosion Control provisions

(d)	Construction Zone Traffic Control Provisions

Traffic Control

Parking

Temporary street closures

Emergency vehicle access

Construction staging

(e) Construction Zone Private Property Access Provisions

Through pedestrian traffic

Building-pedestrian access

Driveway/Loading Zone Access

(f) Provisions to assure the protection of pedestrians and vehicles using the LRT corridor

(g) Provisions for days of the week, hours of the day construction activity may proceed

(h) City Noise Control Variance Provisions

(i) Provisions for Construction Restrictions during special civic events

(j) Provisions for conflict resolution between Project contractors and contractors performing public or private work unrelated to the Project

6.	Property owner/TriMet/City three-party agreements, if necessary	Lead Agency:	TriMet

7.	Liability/Insurance Agreement							Lead Agency: 	TriMet

(a)	During Construction

(b)	Between construction completion and City acceptance of the Project and assumption of its ongoing maintenance responsibilities

8. Amendments to City Code provisions						Lead Agency: City

Amendments to City Code provisions, if necessary, to extend to Project the same terms and conditions related to the use and control of City right-of-way, and adjacent development, as were developed for the construction and operation of the existing light rail system.

9. Maintenance Agreement								Lead Agency: TriMet

Execution of City/TriMet light rail maintenance agreement for the Project, based on terms and conditions and division of responsibilities generally reflected in the existing agreements for the existing light rail system.

10. Conditional use and other land use approvals 			Lead Agency: TriMet

Conditional use and other land use approvals to be applied for by TriMet, for any TriMet facilities on private property within the City that are not allowed outright under City zoning regulations.

11. Record drawings										Lead Agency: TriMet

Record drawings will be produced by TriMet and distributed to the City Bureaus within 120 days after completion of the work.

12. Continuing Control Agreement						Lead Agency: TriMet

Execution of City/TriMet continuing control agreement providing for the permanent use of city streets and other city property necessary for construction, operation and maintenance of those elements of the Project within City right-of-way, in accordance with the continuing control requirements of federal law as administered by the Federal Transit Administration.

# ARTICLE VI - PROJECT POLICY AND MANAGEMENT

A.	Steering Committee. The Steering Committee will be retained through design and construction phases of the Project as described in Section 2.2 of the Grant Agreement as it may be amended from time to time.

B.	Project Management Group (PMG).  The PMG shall be responsible for the overall administration and direction of the Project and this Agreement.  It will be responsible for the resolution of issues related to the design and construction of the Project within the City and will recommend and forward any unresolved issues, or issues of regional significance, to the Policy Group for consideration. The PMG shall consist of representatives from TriMet, City of Portland, Clackamas County, ODOT, PDC and Metro.

C.	Management.

1.	Managers. TriMet designates Jeff Goodling as its Construction Manager and the City designates Teresa Boyle as its Project Manager (collectively, “Managers”).  The Managers shall be responsible for coordinating all aspects of their respective work scopes for the Project and all the respective employees, consultants and contractors assigned to the Project. The Managers shall ensure that the Project and tasks related thereto are completed expeditiously and economically, shall be the contact persons through whom TriMet and the City officially communicate, and shall have the authority to make decisions and resolve disputes relating to the Project. In the event that a disagreement or dispute occurs between the Managers, it shall be resolved in accordance with Article II, Section O, Dispute Resolution.

2.	City Project Engineer.	The City shall assign a Project Engineer, reporting to the City's Project Manager, with the required engineering experience, ability, and skills necessary to perform the following tasks:

(a)	Have access to the City Engineer, City Project Manager, and TriMet's Construction Manager.

(b)	Inform the City Engineer and City Project Manager of TriMet's Project staff’s decisions.

(c) Inform Project staff of progress of required City approvals and work on end products.

(d) Assist TriMet in coordinating utility relocations.

(e)  Prepare a schedule interfacing City or City-permitted work with Project work.

(f) Assist TriMet in gathering information in a timely manner from City staff and assist TriMet's Project staff in understanding the information.

(g)	Assist TriMet in obtaining required end products and approvals.

(h) Advise TriMet of documentation necessary to obtain City approvals and permits.

(i)	Advise and assist TriMet in accomplishing City issuance of the Construction Permit.

(j)	Assist assigned TriMet design lead persons as necessary so that final design is accomplished in accordance with Project schedule milestones, budget and identified quality standards.

(k)	Provide field and/or office engineering functions during construction, as needed by TriMet.

(l)	Report to the assigned TriMet design or construction lead and interface with Project consultants or subconsultants only as permitted by the assigned TriMet lead person.

D.	Decision-Making.		Whenever either party’s decision, determination, approval or consent (each a “decision”) is required on the subject matter in this Agreement, the party will promptly exercise judgment and grant or deny the matter for which a decision was requested in a reasonable manner.  Any consent or approval granted by a party shall not constitute a waiver of the requirement for consent or approval in subsequent cases.  No change in the rights of the Parties or the term of this Agreement shall be required as a condition to granting of approval or consent.  Any denial of consent or approval will include in reasonable detail the reason for denial or aspect of the request that was not acceptable.  Consent and approval required under this Agreement shall not be unreasonably withheld, delayed, or conditioned.

# ARTICLE VII - GENERAL PROVISIONS

A.	Liability.  TriMet shall hold harmless and indemnify the City and its officers, agents, and employees against any and all liability, settlements, losses, costs, and expenses in connection with any action, suit, or claim arising out of TriMet work under this Agreement within the maximum liability limits set forth under the Oregon Constitution and the Oregon Tort Claims Act. The City shall hold harmless and indemnify TriMet and its officers, agents, and employees against any and all liability, settlements, losses, costs, and expenses in connection with any action, suit, or claim arising out of City work under this Agreement within the maximum liability limits under the Oregon Constitution and the Oregon Tort Claims Act.

B.	Interest of Members of Congress. 	No member of or delegate to the Congress of the United States shall be admitted to any share or part of this Agreement or to any benefit arising therefrom.

C.	Interest of Public Officials.  No member, officer, or employee of the City or TriMet during his or her tenure or for one year thereafter shall have any interest, direct or indirect, in this Agreement or the proceeds thereof.

D.	Disadvantaged Business Enterprise.   In connection with the performance of this Agreement, the City will cooperate with TriMet in meeting TriMet's commitments and goals with regard to the maximum utilization of disadvantaged business enterprises and will use its best efforts to ensure that disadvantaged business enterprises shall have the maximum practicable opportunity to compete for subcontract work under this Agreement.  TriMet and the City may desire to enter into an agreement whereby the City provides technical assistance for the DBE efforts.  In the event an agreement is reached on the scope and budget for this work, the Parties will modify this Agreement to provide for such scope and budget.

E.	Equal Employment Opportunity. 	In connection with the execution of this Agreement, neither the City nor TriMet shall discriminate against any employee or applicant for employment because of race, religion, color, sex, age, or natural origin. Such actions shall include, but not be limited to the following: employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; raise or pay or other forms of compensation; and selection for training, including apprenticeship.

F.	Termination for Convenience.    The City or TriMet may terminate this Agreement in whole or in part at any time by written notice to the other Party. In the event of such termination, TriMet shall pay the City's costs, including any costs necessarily incurred by the City in terminating its work or the work of others under contract to City. The City promptly shall submit its termination claim to be paid by TriMet. If, either party has any property in its possession belonging to the other Party (Owner), the party having possession will account for it and dispose of it in the manner as the Owner directs.

G.	Termination for Default.   If the City fails to perform in the manner called for in the Agreement, or if the City fails to comply with any other provisions of the Agreement, TriMet may terminate this Agreement for default. Termination for default shall be effected by serving a notice of termination on the City setting forth the manner in which the City is in default. The City will be paid only the Agreement price for authorized services performed prior to termination in accordance with the manner of performance set forth in this Agreement.

If it is later determined by TriMet that the City has an excusable reason for not performing, such as a strike, fire, flood, or events which are not the fault of, or are beyond the control of the City, TriMet shall establish a new performance schedule, and allow the City to continue work, or treat the termination as a termination for convenience.

In the event TriMet fails to pay the City for its services provided under this Agreement, such failure shall be deemed a material breach for which the City may seek any remedy available to it under the law, including but not limited to, termination of contract or suspension of its services.

H.	Maintenance of Records.	The City shall maintain records to show actual time involved in accomplishment of the Project and the cost incurred for the period of time specified. The City shall cooperate in good faith with TriMet and the FTA to provide records in a form satisfactory to FTA. TriMet shall take the lead and provide assistance to the City as necessary for compliance with FTA requirements.

I.	Audit and Inspection of Records.	The City shall permit the authorized representatives of TriMet, the United States Department of Transportation, and the Comptroller General of the United States to inspect and audit all data and records of the City relating to its performance under this Agreement. TriMet shall be responsible for all auditing costs incurred by TriMet to conduct its audits under this Agreement.

J.	Documents.	All records, reports, data, documents, systems, and concepts, whether in the form of writings, figures, graphs, or models which are prepared or developed in connection with this Project shall become public property. All design drawings and documents prepared by the City staff under this Agreement shall be property of TriMet. Nothing herein shall prevent the City from retaining original design drawings and providing reproducible copies to TriMet.

K.	Successors; No Assignment.  The benefits conferred by this Agreement, and the obligations assumed hereunder, shall inure to the benefit of and bind the successors of the Parties.  The rights and obligations of each party under this Agreement may not be assigned in whole or in part without the prior written consent of the other party.

L.	Choice of Law; Place of Enforcement.	This Agreement shall be governed by and construed in accordance with the laws of the state of Oregon.

M.	Waivers.	No waiver by either party of any provision of this Agreement shall be of any force or effect unless in writing.  Except as otherwise provided herein, no waiver made by a party with respect to the performance, or manner or time thereof, or obligation of the other party or any condition inuring to its benefit under this Agreement shall be considered a waiver of any other rights of the party making the waiver or a waiver by the other party not joining in such waiver, and no such waiver shall be construed to be a continuing waiver.

N.	No Third Party Beneficiaries.	The Parties intend that the rights, obligations, and covenants in this Agreement shall be exclusively enforceable by the Parties.  There are no third party beneficiaries to this Agreement, either express or implied.

O.	Severability/Survivability.  	If any clause, sentence, or portion of the terms and conditions of this Agreement becomes illegal, null, or void for any reason, the remaining portions will remain in full force and effect to the fullest extent permitted by law.  All provisions concerning indemnity survive the termination of this Agreement for any cause.

P.	Interpretation of Agreement.	This Agreement shall not be construed for or against any party by reason of the authorship or alleged authorship of any provision.

Q.	Integration, Modification, and Administrative Changes.  This Agreement includes the entire agreement between the Parties on the subject matter contained in this Agreement and supersedes any and all prior or contemporaneous written or oral understandings, representations, or communications of every kind.  No course of dealing between the Parties and no usage of trade will be relevant to supplement any term used in this Agreement.  This Agreement may only be modified in writing by a modification that has been signed by individuals authorized to bind each of the Parties contractually.  The Parties shall not make changes to this Agreement through the issuance of permits, approvals, or other administrative requirements or processes.

R.	Compliance with Law.	Each party agrees to comply with all local, state and federal ordinances, statutes, laws and regulations that are applicable to the services provided under this Agreement.

S.	Public Contracting Requirements.	To the extent applicable, the provisions of ORS Chapter 279 are incorporated by this reference as though fully set forth.

T.	No Partnership.  Each party is an independent contractor with regard to each other party.  No party is an agent or employee of any other party.

U.	No Participation.  No party or its employees is entitled to participate in a pension plan, insurance, bonus, or similar benefits provided by any other party.

V.  Amendments to this Agreement.  This Agreement embodies the full agreement between the Parties with regard to the subject matters set forth herein, unless amended.  City Bureau directors may authorize modifications to this Agreement, without specific Council approval, that affect the total financial commitment of that Bureau under its Agreement, for amounts up to 25% of the original amount.  Charges in excess of 25% shall require a specific Council ordinance amending this Agreement.

Exhibit List

Exhibit A- Project Milestones and Schedule

Exhibit B- Permit Matrix

Exhibit C- City of Portland Staffing Plan

Exhibit D- BES MOU

Exhibit E- PWB MOU

City of Portland									Tri-County Metropolitan Transportation

District of Oregon

By:  ___________________________		By: ______________________________

Commissioner of________				 General Manager

Dated: _________________________		Dated: _________________________

By: ___________________________

City Auditor

Dated: _________________________

Approved as to form:								Approved as to form:

_______________________________			________________________________

City Attorney										 TriMet Deputy General Counsel