AMENDMENT NO. 2

CONTRACT NO. 37428

## for

“One-Stop” Domestic Violence Center Feasibility Study

This Contract was made and entered into on the 10th day December, 2007, by and between Technical Assistance for Community Services, Inc., hereinafter called Contractor, and the City of Portland, a municipal corporation of the State of Oregon, by and through its duly authorized representatives, hereinafter called City.

- This contract is hereby extended through June 30, 2009.

- Exhibit A of the Contract is amended to include necessary additional work as described in the attached Exhibit A to this Amendment.

- Additional compensation is necessary and shall not exceed $53,075.00, as specified in the attached Exhibit A to this Amendment.

All other terms and conditions shall remain unchanged and in full force and effect.

TECHNICAL ASSISTANCE FOR

COMMUNITY SERVICES, INC.

By:

Date

(Name and Title)

Address:  1001 SE Water Avenue, Suite 490

Portland, Oregon 97214

Telephone: 503-239-4001

# Approved as to Form:	CITY OF PORTLAND

By:

City Attorney	Date	          Auditor	 	          	Date

By:

Mayor/Elected Official	Date

EXHIBIT A

Amendment No. 2 – Contract No. 37428

The following addition to the originally authorized scope of work is necessary for the continued development of the “One Stop” Domestic Violence Service Center:

Phase V: Implementation of One-Stop Domestic Violence Service Center

In accordance with The Feasibility Study for a One-Stop Domestic Violence Service Center, Implementation Approach (Section VI) as completed by the Contractor, the Contractor shall work with the City, County, and non-profit organizations to prepare to open a One-Stop Domestic Violence Service Center.

Phase V Products:

The Contractor will guide an Implementation Task Force and work with collaboratively with community partners to:

- Develop a charter for a governance council identifying composition, role, protocols and authority; and

- Development of a final staffing plan, position description and core operating budget;

- Development of operating agreement and oversight negotiation with on-site and off-site partners; and

- Work in conjunction with City and County staff to maintain oversight of the development plan to build out Center facilities, including facilities plan, revised facilities budget, and tenant relocation plan; and

- Development of forms, procedures and systems necessary to operate the center with public and non-profits entities – forms should include information to allow for the Center’s impact to be measured at a late date.

Phase V Compensation:

Phase V Compensation shall not exceed $53,075.  The following chart illustrates how the budget shall be allocated for each component of Phase V.

| One Stop Implementation Planning Budget |
| --- |
| Component | Est Hours | Rate | Cost |
| Develop charter |  |  |  |
| Sohl | 20 | 125 | 2,500 |
| Farnum | 20 | 110 | 2,200 |
| Clerical support | 5 | 40 | 200 |
| Sub-total |  |  | 4,900 |
| Develop staffing plan, position descriptions, core operating budget |  |  |  |
| Sohl | 30 | 125 | 3,750 |
| Farnum | 30 | 110 | 3,300 |
| Clerical Support | 5 | 40 | 200 |
| Sub-total |  |  | 7,250 |
| Develop facilities plan, revises facilities budget, tenant relocation plan, etc. |  |  |  |
| Sohl | 10 | 125 | 1,250 |
| Farnum | 10 | 110 | 1,100 |
| Mahoney | 60 | 125 | 7,500 |
| Clerical support | 10 | 40 | 400 |
| Sub-total |  |  | 10,250 |
| Develop operating agreements with on-site and off-site partners |  |  |  |
| Sohl | 40 | 125 | 5,000 |
| Farnum | 30 | 110 | 3,300 |
| Mahoney | 10 | 125 | 1,250 |
| Clerical support | 10 | 40 | 400 |
| Sub-total |  |  | 9,950 |
| Develop forms, procedures, and systems |  |  |  |
| Sohl | 40 | 125 | 5,000 |
| Farnum | 50 | 110 | 5,500 |
| Mahoney | 15 | 125 | 1,875 |
| Tech Support | 30 | 85 | 2,550 |
| Clerical Support | 20 | 40 | 800 |
| Sub-total |  |  | 15,725 |

| Project Management |  |  |  |
| --- | --- | --- | --- |
| Sohl |  |  |  |
| Mahoney | 10 | 125 | 1,250 |
| Sub-total | 30 | 125 | 3,750 |
|  |  |  | 5,000 |
| Project Total |  |  | 53,075 |