## Revised 8.26.08
Duration: October 2008 to June 2009
|  | John Fowler (Project Principal) | Brett Campbell (Tunneling Manager) | Scott Thibert (Overall Project Manager) | Mark Weisensee (Structures & Flow Diversion Manager) | Trang Tran (Project Scheduling / Controls) | Phil Hollingsworth (Overall Project Superintendent) | Phiet Vuong (Overall Project Engineer / Purchasing Director) | Todd Pittman (Estimating / Engineering) | Rodney Mintz (Quality Control) | Mike Sealy (Site Safety Manager) | Administrative Assistant (TBD) | Vernell West - V West Consulting (Diversity Consultant) | Mark Havekost - Jacobs Assoc. (Design Consultant) | Mike Kowalski - Jacobs Assoc. (Project Controls / Scheduling Lead) | Peter Raleigh - Jacobs Assoc. (MTBM Design Consultant) | Tom Hennings - Jacobs Assoc. (Shaft Design Consultant) | Cad Tech / Staff Engineer (TBD) | Reimbursible Direct Costs
Task No. | Task | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  | Hours |  |  | Hours | Hours |  |  | Total Cost
| Direct Labor Cost | 90 | 70 | 70 | 70 | 40 | 65 | 50 | 50 | 35 | 55 | 35 | 150 | 175 | 155 | 160 | 170 | 155
| Multiplier | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05
| Billing Rate: | 180 | 140 | 140 | 140 | 80 | 130 | 100 | 100 | 70 | 110 | 70 | 157.5 | 183.75 | 162.75 | 168 | 178.5 | 162.75
REQUIRED SERVICES
110 | Project Management Plan | 72 | 72 | 72 | 36 | [8 empty] | 36 | [5 empty] | 44775
120 | Monthly Reports / Invoices | 22 |  | 32 |  | 18 | [13 empty] | 9880
130 | Project Team Meetings | 46 | 46 | 48 | 46 |  | 40 | 40 | 40 | 40 | 20 |  |  |  | 26 |  |  |  |  | 50311.5
140 | Contractor Team Meetings | 90 | 90 | 94 | 45 |  | 90 | 90 | 90 | 90 | 50 |  |  |  | 50 |  |  |  |  | 97897.5
150 | Records Control |  |  | 18 |  | 72 |  | 36 |  | 110 |  | 1320 |  |  | 24 |  |  |  |  | 115886
160 | Partnering | 18 | 18 | 54 | 36 | [14 empty] | 18360
[19 empty] | Total Task 100 | 337110
210 | Design Support | 36 | 54 | 92 | 52 | 36 | 144 | 40 | 18 | 36 |  |  |  | 44 |  |  | 24 | 200 |  | 109039
210.1 | Field Services | [17 empty] | 100000 | 100000
220 | Construction Staging | 18 | 36 | 54 | 18 | 72 | 180 | 20 | 18 | 18 | [9 empty] | 52580
230 | Geotechnical Baseline Report | 18 | 144 | 54 | 18 |  | 90 |  | 36 |  |  |  |  | 20 | [5 empty] | 52455
240 | Risk Assessment | 36 | 36 | 56 | 36 |  | 90 | 20 | 36 |  |  |  |  | 40 | 20 |  |  |  |  | 52305
250 | MTBM Requirements | 126 | 224 | 75 |  |  | 360 | 36 |  | 20 |  |  |  | 24 |  | 128 | 80 |  |  | 156534
250.1 | Deposit on MTBM | [17 empty] | 1577000 | 1577000
250.2 | Deposit on Seperation Plant | [17 empty] | 100000 | 100000
260 | Permits | 9 | 18 | 46 |  | 18 |  |  |  | 18 | [9 empty] | 13280
270 | Construction Phasing | 126 | 36 | 150 | 108 |  | 150 | 230 | 54 | 200 |  |  | 80 | 24 |  |  | 80 |  |  | 157030
[19 empty] | Total Task 200 | 2370223
310 | Construction Management | 36 | 36 | 72 | [5 empty] | 20 | [8 empty] | 6600 | 29600
320 | Project Quality Assurance/ Quality Control Plan |  |  | 18 | [5 empty] | 180 | [9 empty] | 15120
330 | Project Document Control Program | 9 |  | 36 |  | 72 |  | 200 |  | 72 |  |  |  |  | 40 |  |  |  |  | 43970
[19 empty] | Total Task 300 | 88690
410 | Construction Schedule | 18 |  | 36 | 18 | 360 |  |  | 72 | 110 |  |  |  |  | 120 |  |  |  |  | 74030
420 | Construction Estimate - ERC | 54 |  | 92 | 18 | 360 | 72 | 526 | 500 | 72 |  |  |  |  | 200 |  |  |  |  | 203470
430 | Project Cost Control System | 9 |  | 18 |  | 90 |  | 9 | 90 | [5 empty] | 20 |  |  |  |  | 24495
[19 empty] | Total Task 400 | 301995
510 | Hazard Assessment | 9 | 9 | 9 |  |  | 72 | 40 |  |  | 140 | [8 empty] | 32900
520 | Corporate Health & Safety Plan | 9 |  | 9 | [6 empty] | 100 | [8 empty] | 13880
530 | Health & Safety Plan for Project Site | 9 | 9 | 9 | [5 empty] | 36 | 160 | [8 empty] | 24260
540 | General Construction Safety Provisions Review | 9 |  | 9 | [6 empty] | 100 | [8 empty] | 13880
550 | Safety Training Program |  |  | 9 | [5 empty] | 36 | 80 | [8 empty] | 12580
[19 empty] | Total Task 500 | 97500
610 | Project Information | 9 | 9 | 18 |  |  |  | 10 |  | 36 |  |  | 80 | [6 empty] | 21520
620 | Community Presentations | 9 | 9 | 18 |  |  |  | 9 |  | 36 | [9 empty] | 8820
630 | Site Visits | 18 | 36 | 36 |  |  | 72 | 18 | 54 | 36 | [9 empty] | 32400
[19 empty] | Total Task 600 | 62740
710 | Subcontracting Procurement Plan | 18 |  | 72 | [5 empty] | 36 | 36 |  | 100 | [6 empty] | 35550
720 | MWESB Program Construction Plan | 12 |  | 27 |  | 36 |  | 18 |  | 36 |  |  | 120 | [6 empty] | 32040
730 | Workforce Training & Hiring | 18 |  | 27 |  | 36 |  | 18 |  | 36 |  |  | 120 | [6 empty] | 33120
[19 empty] | Total Task 700 | 100710
| Total Hours: | 863 | 882 | 1360 | 431 | 1170 | 1360 | 1360 | 1008 | 1274 | 686 | 1320 | 500 | 188 | 500 | 128 | 184 | 200
| Total Cost: | 155340 | 123480 | 190400 | 60340 | 93600 | 176800 | 136000 | 100800 | 89180 | 75460 | 92400 | 78750 | 34545 | 81375 | 21504 | 32844 | 32550 | 1783600 | 3358968