AMENDMENT NO 3

CONTRACT NO.   37570

## FOR

Quality Rental Housing Workgroup Facilitation

This Contract was made and entered into on the 1st day of July, 2007 by and between Decisions Decisions], hereinafter called Contractor, and the City of Portland, a municipal corporation of the State of Oregon, by and through its duly authorized representatives, hereinafter called City.

- Additional work is necessary as described in the amended Scope of Work, attached as Exhibit A.

- Additional compensation is necessary and provided in the form of $21,675 in general fund dollars.  Total funds shall not exceed $86,110.

All other terms and conditions shall remain unchanged and in full force and effect.

Decisions Decisions

By:

Date

(Name and Title)

Address: 	1001 SE Water Avenue, #360

Portland, OR  97214

Telephone: 	(503) 249-0000

# Approved as to Form:	CITY OF PORTLAND

By:

City Attorney	Date	          Auditor	 	          	Date

By:

Mayor/Elected Official	Date

AGREEMENT FOR PROFESSIONAL, TECHNICAL, OR EXPERT SERVICES

EXHIBIT A

Amended Scope of Work

and

Payment Schedule

### Quality Rental Housing Workgroup Scope of Work and Timeline

Summary:

Interviews with workgroup members and stakeholders will begin in July. The workgroup will convene in September with the goal to report to City Council by January and conclude meetings in April and release the final report in May. Although we expect to have subcommittees on issues such as mold and lead, it is premature to reflect their meeting dates in this timeline.

| July - August | Connect with WG | Send out letter of introduction, binder |
| --- | --- | --- |
|  | Interview WG members and stakeholders | Use results to frame process and identify needs of stakeholders |
|  | Focus groups of small landlords |  |
| August 6-10 | Convene SC | Draft workgroup structure, scope (list of topics), propose timeline, milestones, review process. |
| September 10-14 | Convene WG | Finalize workgroup scope, structure, timeline, roles, and review process. Begin analysis of existing data. |
| October | Meet with SC, WG | Review existing programs and procedures. Begin framing problem statements. |
| November | Meet with SC, WG | Complete review of existing programs and procedures. Complete framing of problem statements. |
| December | Meet with SC, WG | Finalize report of evaluation and analysis. Begin to outline toolbox of strategies to address problems. |
| January | Meet with SC, WG | Continue strategy development. |
| February | Meet with SC, WG | Complete strategy development and prioritize strategies. |
|  | Draft recommendations report. |  |
| March | Meet with SC, WG | Prepare draft report for stakeholder review |
| July | Meet with SC, WG | Finalize recommendations report. Discuss implementation strategies, communication, and ongoing roles. |
| September | Release final report. |  |

BHCD Quality Rental Housing Payment Schedule

The budget revisions below correspond to the revised workgroup timeline. Estimates reflect the addition of workgroup member and stakeholder interviews, facilitation and support of up to 24 2-hour sub-committee meetings, two focus group sessions of small landlords, and co-facilitation of the steering committee and workgroup by Decisions Decisions throughout the process. The total cost is based on estimated billable hours. The project budget may be reduced if, at some point in the future, the Steering Committee feels the process is well-served by a single facilitator.

| Tasks | Estimated Hours | Cost |
| --- | --- | --- |
| Review Materials and Convene Committees to Finalize Project Scope (July-Aug) | 36 | $3,920 |
| Interview WG Members, Stakeholders, Landlords (July-Aug) | 104 | $12,420 |
| Facilitate and Support Steering Committee (Aug-May) | 90 | $17,050 |
| Facilitate and Support Workgroup (Oct-Apr) | 68 | $14,265 |
| Facilitate and Support Subcommittees (24 meetings) | 192 | $23,110 |
| Report on Recommendations | 30 | $8,725 |
| Project Assistance | 38 | $6,620 |
| Total | 768 | $86,110 |