## Slide 1: Amend Contract With Brown & Caldwell for Alder Pump Station Upgrade BES Project No: E10359 Contract No: 30003063
Paul Suto, P.E., Engineering Manager
Aaron Lawler, P.E., Engineer
May 2, 2018

## Slide 2: Ordinance
Amend Contract with Brown and Caldwell, Inc. for professional
engineering services for the Alder Pump Station Upgrades, BES Project No. E10359, in the amount of $85,000
(ordinance; amend Contract No: 30003063)
- This amendment is for additional design services during construction

## Slide 3: Location Map
Alder Pump Station Project Location

## Slide 4: Project Objectives
Upgrade the pump station to accommodate future projected flows:
  Sanitary Pumps: 2,100-gpm firm capacity
  Storm Pumps: 900-gpm firm capacity
Integrate pump station operation with the Eastside CSO System
Simplify Pump Station Operation and Configuration
Improve O&M access to the PS
Improve Seismic Resiliency

## Slide 5: Original Alder Pump Station

## Slide 6: Original Alder Pump Station

## Slide 7: Alder Pump Station – Original Configuration
Original construction in 1952
Two existing and separate pumping systems:
  - Sanitary system with a firm pumping capacity of 750-gpm that discharges to the SE interceptor sewer with flow conveyed to the Sullivan PS
  - Storm system with a firm pumping capacity of 1,500-gpm that discharges to Outfall 36
Complicated split sanitary and storm system wet well configuration

## Slide 8: Alder PS – Split Wetwell Schematic

## Slide 9: Alder PS – System Schematic
*Source: BES Asset Systems Management Division TM Alder PS Flow Analysis, July 12, 2012

## Slide 10: Construction Photos

## Slide 13: Amendments and Ordinances to Date
Ordinance No: 185681 – Contract Award
  Contract Amount - $357,693
Amendment 1 – Sub-Consultant Change
Ordinance No: 186764 –Contract Amendment No. 2
  Amendment Amount - $352,329
Amendment 3 – Sub-Consultant Change

## Slide 14: Amendments and Ordinances to Date
Ordinance No: 188065 –Contract Amendment No. 4
  Amendment Amount - $31,767
Amendment 5 – BES Project Manager Change
Amendment 6 – Contract Duration Extended
Ordinance No: 188131 – Construction Contract Award Authorization
  Authorization Amount: $3,500,000

## Slide 15: Project Schedule
2011 – Project Initiated
2012 – Brown & Caldwell Awarded PTE Design Contract
2014 – Design Approach Changed to Major Pump Station Upgrade
2017 – Construction Notice to Proceed on 8/1/2017
2019 – Substantial Completion 3/7/19

## Slide 16: Contract Amount
Current PTE Contract with Prior Council Approval: $741,789
Final Amendment 7 Request to Brown & Caldwell Contract: $85,000
Final Contract Amount: $826,789

## Slide 17: D/M/W/ESB
Current Contract Amount: $741,789
  Total D/M/W/ESB Contracts: $251,168
  D/M/W/ESB Participation: 33.9%
Amendment 7 Amount: $85,000
  Amended Contract Amount: $826,789
  Total Amended D/M/W/ESB Contracts: $278,668
  Amended D/M/W/ESB Participation: 33.7%

## Slide 18: Recommendation
Authorize Contract Amendment with Brown and Caldwell, Inc. for professional engineering services for the Alder Pump Station Upgrades, BES Project No. E10359, in the amount of $85,000
(ordinance; amend Contract No: 30003063)

## Slide 19: Questions
Thank you