## ProjectFlow - Checklist Items
Checklist Comments Report
Project Name: |  | 19-106743-REV-01-CO
Workflow Started: |  | 10/30/2019 10:04 AM
Report Generated: |  | 12/09/2019 08:48 AM
Grouping | Cycle |  | Ref # | Permit Type | Group Name | Comment Type | Category Type | Reviewer Comment | Applicant Response | Status | Updated By | Last Updated | Completed? | Date Completed
Main Workflow | 1 |  | 1 | Commercial Building Permit PF | Planning and Zoning | Plan Review | Department Review | 12/4/19 JRichling. Complete Design Review (LU 19-234469 DZ). The proposed storefront louvers and rooftop mechanical program are currently under consideration in LU 19-234469 DZ, the status of which is "pending." The Design Review must be completed to facilitate staff review of the permit revision against the approved Exhibits and Conditions of Approval. Note that the plans may need to be further modified to demonstrate conformance with the land use decision. |  | Not Met | Jason Richling | 12/04/2019 2:56 PM | False | 12/04/2019 2:56 PM
|  |  | 2 | Commercial Building Permit PF | Planning and Zoning | Plan Review | Department Review | 12/4/19 JRichling. Please include revised building elevations (Sheets A03.01 and A03.02) in the revision plan set to reflect the changes to the street-facing louvers (LU 19-234469 DZ pending) and the entrances added to the proposed retail (former Amenity) space facing SW Salmon St. |  | Not Met | Jason Richling | 12/04/2019 2:56 PM | False | 12/04/2019 2:56 PM