## Schedule
PHASE I | RESPONSIBILITY |  | CDS Staff |  |  |  |  | 2002 | [10 empty] | 2003 | [11 empty] | 2004
Through June 30, 2003 |  |  |  |  | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
[10 empty] | PHASE I | [18 empty] | PHASE II
GRANT APPLICATION | HAP | bar: 2002 JUN to 2002 SEP
X-SITE LAYOUT
PUBLIC COORDINATION | HAP TEAM | bar: APR to 2002 APR
PLANNING/TAC | PM | 1 EOR | 2 designers | none | bar: 2002 JUN to 2002 OCT
DESIGN ASSISTANCE | BTED-DM; EP; LG | bar: MAY to 2002 SEP
SITE SURVEY | BTED-SUR-Forestry | bar: APR to 2002 JUL
Includes Tree Survey |  |  |  |  | 2002 JUL: X-Base Map
Preliminary Grading Plan | bar: 2002 SEP to 2002 NOV
LAND USE REVIEW | HAP ARCH/BTED-ESD | 1 EOR | none | 2 drafters
Subdivision Pre-Application |  |  |  |  | 2002 OCT: X -Conference
Tentative Subdivision Development | bar: 2002 NOV to 2002 FEB
and review by HUD
Subdivision Application |  |  |  |  | 2002 FEB: X-Application to OPDR
OPDR Review | bar: 2002 FEB to 2003 MAY
Preliminary Plat Approval |  |  |  |  | 2003 JUN: X - Preliminary Approval
Final Plat Application | bar: 2003 JUL
OPDR Review | bar: 2003 JUL to 2003 OCT
Final Approval |  |  |  |  | 2003 OCT: X - Final Approval
STREET or PLAT VACATION | HAP/BTED-RWA | bar: 2002 SEP to 2003 JUL
Concurrent with Land Use Review |  |  |  |  | 2002 FEB: X-Planning Commission
X-Council
UTILITY COORDINATION | PM | bar: 2002 SEP to 2002 MAR
TRAFFIC STUDY | CONSULTANT | bar: 2002 SEP to 2002 DEC
PRELIMINARY STREET DESIGN | BTED-CDS | 2 EORs | 3 designers | 1 drafter | bar: 2002 JUN to 2003 JUN
SITE DEMOLITION | HAP | bar: 2003 JUN to 2003 SEP
PHASE II WORK SCOPE | bar: 2003 MAY to 2003 JUN