## Certification
CERTIFICATION FOR PAYMENT FOR ESTIMATED WORK
BLOCK 1 |  | Contractor: | Dunn Construction Inc.
|  | Address: | 10340 NE Weidler |  | Phone: | (503) 408-7601
|  | City, State, Zip: | Portlnad, OR 97220 |  | Fax: | (503) 408-7602
|  | Proj Manager | Frank Dunn
BLOCK 2 |  | Project: | SW Arboretum Hills LID |  | Progress Payment # |  | 6 Final
|  | Contractor: | Dunn Construction Inc. |  | Pay Period Ending Date: |  | 2002-04-30
|  | Contract #: | 33088 |  | Notice to Proceed Date: |  | 2000-09-15
|  | Original Contract Amount: | 152577 |  | No. of Days in Contract: |  | 71
|  | Change Orders Authorized: | 1991.76 |  | No. of Days Added by Change Order: |  | 0
|  | Total Authorized: | 165192.76 |  | Completion Date: |  | 2001-10-31
|  | Invoice Date: | 2001-10-31 |  | Days Remaining: |  | *
| P | % Complete less mobilization and Material-on-hand (percentage determines how much mobilization can be released -- i.e. @ 5% can pay 50% mob, 10% complete can pay 100% mob, per sect 201.4.01) - Row can be hidden |  | 108.3%
| Q | % Revised Authorized Amount Of Original Contract Amount (this is again an FYI that can be hidden) |  | 108.3%
BLOCK 3 | R | Estimated Work Completed To Date (Page 2 Column N Total) |  | 165192.76
| S | Material-on-Hand (Page 3, Column I Total) |  | 0
| T | Total Completed & Material On Hand (R + S) |  |  | 165192.76
| U | Retainage to date |  | 0
| V | 15% Retainage for Materials-on-hand (15% of S) |  | 0
| W | Total Retainage (U+V) |  | 0
| X | Authorized Payments to Date (T-W) |  |  | 165192.76
| Y | Total Progress Payments Made to Date |  | 156933.12
| Z | Current Midmonth Payment |  | 0
| AA | Total of Payments to Date (Y+Z) |  | 156933.12
| AB | PAYMENT DUE (X-AA) |  |  | 8259.64 |  | Pay this amount
|  | Approved for Processing: | Project Manager / Date
BLOCK 4 |  | For Accounting use only if there are multiple projects in a contract (completed by PM)
Accounting: please make the following job number charges.
|  | Job # | Current Charges
|  | Proj # _______ | 0
|  | Proj # _______ | 0
|  | Proj # _______ | 0
|  | Proj # _______ | 0
|  | Total Proj Charges | 0

## PP1-date
BLOCK 1 | APPLICATION AND CERTIFICATION FOR PAYMENT
| To: | City of Portland Bureau of Water Works | [9 empty] | Contractor: | Dunn Construction Inc.
|  | 1120 SW 5th Ave, Rm 600 | [9 empty] | Address: | 10340 NE Weidler
|  | Portland, OR 97204 | [9 empty] | City, State, Zip: | Portlnad, OR 97220
|  | Frank Dunn | [9 empty] | Phone: | (503) 408-7601
[12 empty] | Fax: | (503) 408-7602
BLOCK 2 | Project: |  | SW Arboretum Hills LID | [9 empty] | Progress Payment # |  | 6 Final
| Contractor: |  | Dunn Construction Inc. | [9 empty] | For Work Completed Through: |  | 2002-04-30
| Contract #: |  | 33088 | [8 empty] | Completion Date: |  |  | 2001-10-31
| Notice to Proceed Issued: |  | 2000-09-15 | [9 empty] | Days Remaining |  | *
BLOCK 3 | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O
[5 empty] | Bid Amount |  |  | Previous Work |  | Current Work |  |  | Total Completed to Date
| Item No. | Description of Work | QTY | Unit | Unit Price | Original Authorization | Revised Authorization | Completed Quantity | Amount | Quantity | Amount | Qty | Amount | % Complete of Original | Balance to Finish
[8 empty] | ( Previous J ) | ( Previous K ) |  | (J * E ) | (H +J) | (I + K) | (M / F ) or (M/G) | (F - M) or (G - M)
| 1 | Mobilization | 1 | LS | 7600 | 7600 | 7600 | 100% | 7600 | 0% | 0 | 100% | 7600 | 100% | 0
| 2 | Trench Excavation | 596 | CY | 5 | 2980 | 2980 | 596 | 2980 | 0 | 0 | 596 | 2980 | 100% | 0
| 3 | Rock Excavation | 10 | CY | 10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0
| 4 | Trench Backfill (Import) | 220 | CY | 10 | 2200 | 2200 | 220 | 2200 | 0 | 0 | 220 | 2200 | 100% | 0
| 5 | Trench Backfill (Native) | 15 | CY | 10 | 150 | 132 | 13.2 | 132 | 0 | 0 | 13.2 | 132 | 100% | 0
| 6 | 6" Class 52 Restrained DI Pipe w/ Pipe Zone Bedding and Backfill | 1782 | LF | 31 | 55242 | 55242 | 1782 | 55242 | 0 | 0 | 1782 | 55242 | 100% | 0
| 7 | AC Pavement (Base Lift) 1-1/2" | 245 | SY | 23 | 5635 | 5543 | 241 | 5543 | 0 | 0 | 241 | 5543 | 100% | 0
| 8 | AC Pavement Overlay (Top Lift) 2" | 2500 | SY | 10 | 25000 | 22100 | 2210 | 22100 | 0 | 0 | 2210 | 22100 | 100% | 0
| 9 | Crushed Rock Pavement Base | 41 | CY | 10 | 410 | 410 | 41 | 410 | 0 | 0 | 41 | 410 | 100% | 0
| 10 | Crush Rock Resurfacing | 156 | SY | 15 | 2340 | 2619 | 174.6 | 2619 | 0 | 0 | 174.6 | 2619 | 100% | 0
| 11 | 6" Gate Valve | 4 | EA | 400 | 1600 | 1600 | 4 | 1600 | 0 | 0 | 4 | 1600 | 100% | 0
| 12 | Hydrant Assemblies | 4 | EA | 1900 | 7600 | 7600 | 4 | 7600 | 0 | 0 | 4 | 7600 | 100% | 0
| 13 | 3/4" Air Release Assembly | 1 | EA | 500 | 500 | 500 | 1 | 500 | 0 | 0 | 1 | 500 | 100% | 0
| 14 | 3/4" Service Lateral | 150 | LF | 12 | 1800 | 1740 | 145 | 1740 | 0 | 0 | 145 | 1740 | 100% | 0
| 15 | 3/4" Backside Water Service | 540 | LF | 53 | 28620 | 42135 | 795 | 42135 | 0 | 0 | 795 | 42135 | 100% | 0
| 16 | Connections for Other Backside Work | 14 | EA | 200 | 2800 | 2800 | 14 | 2800 | 0 | 0 | 14 | 2800 | 100% | 0
| 17 | Erosion Control | 1 | LS | 2500 | 2500 | 2500 | 1 | 2500 | 0 | 0 | 1 | 2500 | 100% | 0
| 18 | Construction Sign | 1 | EA | 500 | 500 | 500 | 1 | 500 | 0 | 0 | 1 | 500 | 100% | 0
| 19 | Landscape Restoration | 1 | LS | 5000 | 5000 | 5000 | 1 | 5000 | 0 | 0 | 1 | 5000 | 100% | 0
|  | Subtotal 1 |  |  |  | 152577 | 163201 |  | 163201 |  | 0 |  | 163201 |  | 0
| 20 | Change Order 1 | 1 | LS | 873.49 | 0 | 873.49 | 1 | 873.49 | 0 | 0 | 1 | 873.49 | 100% | 0
| 21 | Change Order 2 | 1 | LS | 1118.27 | 0 | 1118.27 | 1 | 1118.27 | 0 | 0 | 1 | 1118.27 | 100% | 0
| 22 | Change Order 3 | 1 | LS | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 100% | 0
|  | Subtotal 2 |  |  |  | 0 | 1991.76 |  | 1991.76 |  | 0 |  | 1991.76 |  | 0
|  | TOTALS |  |  |  | 152577 | 165192.76 |  | 165192.76 |  | 0 |  | 165192.76 |  | 0
|  | % Complete less mobilization and material on hand | [7 empty] | 108.3%
|  | % Revised Schedule Over Original | [7 empty] | 108.3%
| P | Work Completed To Date | [7 empty] | 0
| Q | Material On Hand (Calculated from Separate Sheet) | [7 empty] | #REF!
| R | Total Completed & Material On Hand | [8 empty] | #REF!
| S | 5% Retainage of Work Completed | [7 empty] | 0
| T | 15% Retainage of Stored Materials | [7 empty] | #REF!
| U | Total Retainage | [8 empty] | #REF!
| V | Authorized Payments to Date | [8 empty] | #REF!
|  | Total Previous Progress Payments | [7 empty] | 5
|  | Current Midmonth Payment | [7 empty] | 1
| W | Total of Previous Payments | [8 empty] | 6
| X | PAYMENT DUE | [8 empty] | #REF!
| Signed: | [6 empty] | Date: |  |  | Pay this amount
Three Dimensional Contracting, Inc.