## Task_Export_Table
Exhibit B:Schedule, Phase 1, Security Vulnerability Assessment
(for those not able to read MS Project files)
ID | Unique_ID | Task_Name | Duration | Type | Outline_Level | Predecessors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Free_Slack | Total_Slack | Leveling_Delay | Percent_Complete | Actual_Start | Actual_Finish | Baseline_Start | Baseline_Finish | Constraint_Type | Constraint_Date | Stop | Resume | Created | Scheduled_Work | Baseline_Work | Actual_Work | Cost | Fixed_Cost | Baseline_Cost | Actual_Cost | Remaining_Cost | WBS | Priority | Milestone | Summary | Rollup | Text1 | Text2 | Text3 | Text4 | Text5 | Text6 | Text7 | Text8 | Text9 | Text10 | Cost1 | Cost2 | Cost3 | Duration1 | Duration2 | Duration3 | Flag1 | Flag2 | Flag3 | Flag4 | Flag5 | Flag6 | Flag7 | Flag8 | Flag9 | Flag10 | Marked | Number1 | Number2 | Number3 | Number4 | Number5 | Subproject_File
1 | 26 | Phase 1 Vulnerability Assessment | 97 days | Fixed Duration | 1 |  | 2002-08-19 08:00 | 2002-12-31 17:00 | 2002-08-19 08:00 | 2002-12-31 17:00 | 2002-08-19 08:00 | 2002-12-31 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-06-11 08:50 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1 | 500 |  | Yes | Yes | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2 | 1 | Notice To Proceed | 1 day | Fixed Units | 2 |  | 2002-08-19 08:00 | 2002-08-19 17:00 | 2002-08-19 08:00 | 2002-08-19 17:00 | 2002-08-19 08:00 | 2002-08-19 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | Start No Earlier Than | 2002-08-19 08:00 | NA | NA | 2002-05-06 22:35 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.1 | 500 | Yes | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
3 | 27 | Establish Security Planning Team | 3 days | Fixed Units | 2 | 2 | 2002-08-20 08:00 | 2002-08-22 17:00 | 2002-08-20 08:00 | 2002-08-22 17:00 | 2002-08-20 08:00 | 2002-08-22 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-06-19 12:24 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.2 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
4 | 2 | Request Background Information | 4 days | Fixed Units | 2 | 3 | 2002-08-23 08:00 | 2002-08-28 17:00 | 2002-08-23 08:00 | 2002-08-28 17:00 | 2002-08-23 08:00 | 2002-08-28 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:36 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.3 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
5 | 3 | BWW Deliver Background Info | 6 days | Fixed Units | 2 | 4 | 2002-08-29 08:00 | 2002-09-05 17:00 | 2002-08-29 08:00 | 2002-09-05 17:00 | 2002-08-29 08:00 | 2002-09-05 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:38 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.4 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
6 | 4 | Review Background Info | 5 days | Fixed Units | 2 | 5 | 2002-09-06 08:00 | 2002-09-12 17:00 | 2002-09-06 08:00 | 2002-09-12 17:00 | 2002-09-06 08:00 | 2002-09-12 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:39 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.5 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
7 | 28 | Rank Mission Objectives | 10 days | Fixed Units | 2 | 6 | 2002-09-13 08:00 | 2002-09-26 17:00 | 2002-09-13 08:00 | 2002-09-26 17:00 | 2002-09-13 08:00 | 2002-09-26 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-06-19 12:56 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.6 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
8 | 5 | System Threat and Characterization Analysis | 12 days | Fixed Units | 2 | 7FS-5 days | 2002-09-20 08:00 | 2002-10-07 17:00 | 2002-09-20 08:00 | 2002-10-07 17:00 | 2002-09-20 08:00 | 2002-10-07 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:40 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.7 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
9 | 6 | Site assessment meeting | 1 day | Fixed Units | 2 | 8 | 2002-10-08 08:00 | 2002-10-08 17:00 | 2002-10-08 08:00 | 2002-10-08 17:00 | 2002-10-08 08:00 | 2002-10-08 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:43 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.8 | 500 | Yes | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
10 | 7 | Physical Site Assessment | 10 days | Fixed Units | 2 | 9FS-4 days | 2002-10-03 08:00 | 2002-10-16 17:00 | 2002-10-03 08:00 | 2002-10-16 17:00 | 2002-10-03 08:00 | 2002-10-16 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:44 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.9 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
11 | 29 | Risk Analysis | 15 days | Fixed Units | 2 | 10 | 2002-10-17 08:00 | 2002-11-06 17:00 | 2002-10-17 08:00 | 2002-11-06 17:00 | 2002-10-17 08:00 | 2002-11-06 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-06-19 12:58 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.10 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
12 | 8 | Draft of Findings | 12 days | Fixed Units | 2 | 11 | 2002-11-07 08:00 | 2002-11-22 17:00 | 2002-11-07 08:00 | 2002-11-22 17:00 | 2002-11-07 08:00 | 2002-11-22 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:45 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.11 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
13 | 9 | Findings Review Meeting | 1 day | Fixed Units | 2 | 12FS+2 days | 2002-11-27 08:00 | 2002-11-27 17:00 | 2002-11-27 08:00 | 2002-11-27 17:00 | 2002-11-27 08:00 | 2002-11-27 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:47 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.12 | 500 | Yes | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
14 | 10 | Final Security Plan | 5 days | Fixed Units | 2 | 13 | 2002-11-28 08:00 | 2002-12-04 17:00 | 2002-11-28 08:00 | 2002-12-04 17:00 | 2002-11-28 08:00 | 2002-12-04 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:50 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.13 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
15 | 11 | Implementation Programming | 5 days | Fixed Units | 2 | 14 | 2002-12-05 08:00 | 2002-12-11 17:00 | 2002-12-05 08:00 | 2002-12-11 17:00 | 2003-02-07 08:00 | 2003-02-13 17:00 | 3 days | 46 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:51 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.14 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
16 | 12 | Draft Report | 8 days | Fixed Units | 2 | 14 | 2002-12-05 08:00 | 2002-12-16 17:00 | 2002-12-05 08:00 | 2002-12-16 17:00 | 2002-12-05 08:00 | 2002-12-16 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:52 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.15 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
17 | 13 | BWW Review Draft Report | 7 days | Fixed Units | 2 | 15,16 | 2002-12-17 08:00 | 2002-12-25 17:00 | 2002-12-17 08:00 | 2002-12-25 17:00 | 2002-12-17 08:00 | 2002-12-25 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:53 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.16 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
18 | 14 | Final Report Development | 3 days | Fixed Units | 2 | 17 | 2002-12-26 08:00 | 2002-12-30 17:00 | 2002-12-26 08:00 | 2002-12-30 17:00 | 2002-12-26 08:00 | 2002-12-30 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:54 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.17 | 500 | No | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
19 | 15 | Final Report Submittal | 1 day | Fixed Units | 2 | 18 | 2002-12-31 08:00 | 2002-12-31 17:00 | 2002-12-31 08:00 | 2002-12-31 17:00 | 2002-12-31 08:00 | 2002-12-31 17:00 | 0 days | 0 days | 0 edays | 0% | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 2002-05-06 22:55 | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0 | 0 | 0 | 1.18 | 500 | Yes | No | No | Cost1: 0; Cost2: 0; Cost3: 0 | 0 days | 0 days | 0 days | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0