## Final Estimate
CITY OF PORTLAND, OREGON
BUREAU OF TRANSPORTATION ENGINEERING AND DEVELOPMENT
Construction
Copenhagen Utilities & Construction Inc.
|  | Base Contract | 2483242
|  | Changes in Quantities | 210865.25
|  | Change Orders | 458746.79
3152854.04
Construction Claim
|  | Partial Payment | 230056.54
|  | Final Payment | 227980.18
|  | Construction Claim |  | 458036.72
| Construction Total |  |  |  | 3610890.76
Engineering
Design Engineering
|  | Street | 64719.16
|  | Stormwater | 117861.82
182580.98
Construction Engineering
|  | Street | 225365.88
|  | Stormwater | 10223.7
235589.58
Credits
|  | Water Bureau | -17409.07
|  | Portland Office of Transportation | -45.08
-17454.15
| Engineering Total |  |  |  | 400716.41
Project Management |  |  |  |  | 62624.69
SUBTOTAL INCURRED COSTS |  |  |  |  | 4074231.86
Auditor's Costs
| Advertising |  |  | 130.5
| LID Construction Fund - Progress Payment Interest through 9/18/02 |  |  | 1012626.37
| LID Construction Fund - Interest Credit |  |  | -10144.57
| LID Construction Fund - Superintendence |  |  | 22236.58
1024848.88
Project Management
| Project Closeout |  |  | 1877.1973
| Advertising for Final Assessment Ordinance |  |  | 125
2002.1973
Overhead
| Administrative overhead on project management and engineering @ 23.36% |  |  |  | 108704.1943
SUBTOTAL PENDING COSTS |  |  |  |  | 1135555.2716
TOTAL PROJECT COSTS |  |  |  |  | 5209787.1316
Property Owner Share
| Nauru payment prior to LID formation |  |  |  | 27520
| Estimated assessment at LID formation |  | 3194644.6
| Increase (decrease) from estimated to final assessment |  | 1776079.15
| Total property owner billing |  |  | 4970723.75
| Payment from escrow due upon final assessment |  |  |  | 2949483.84
| Total Local Improvement District billing |  |  |  | 2021239.91
Other Funding
| Slide Repair |  |  | 38172.38
| Project Closeout |  |  | 64626.8873
| Other Credit |  |  | 39.92
| Absorption of Overhead |  |  | 108704.1943
| Portland Office of Transportation |  |  |  | 211543.3816
TOTAL PROJECT FUNDING |  |  |  |  | 5209787.1316
FINAL ESTIMATE of the various kinds of work performed in the
improvement of:
NW Thompson Road from 600 Feet West of NW Pinnacle Drive to City Limits