## Engineer's Estimate
NORTH MARINE DRIVE EXTENSION PHASE 2
Final Estimate
STREET & UTILITY CONTRACT WORK
BILLED TO DATE
NO. | ITEMS OF WORK AND MATERIALS | UNIT | UNIT PRICE | QUANTITY | AMOUNT
1 | Mobilization | LS | 880000 | 1 | 880000
2 | Furnishing Field Office Trailer | LS | 29000 | 1 | 29000
3 | Temporary Protection And Direction Of Traffic | LS | 30000 | 0.99 | 29700
4 | Temporary Signs | m2 | 190 | 87.16 | 16560.4
5 | Business Directional Signs | m2 | 190 | 14.17 | 2692.3
6 | Temporary Barricades | EA | 145 | 29 | 4205
7 | Temporary Plastic Drums | EA | 45 | 613 | 27585
8 | Temporary Flexible Pavement Markers | EA | 1.3 | 346 | 449.8
9 | Sequential Arrow Signs | EA | 12000 | 1 | 12000
10 | Temporary Striping | m | 0.26 | 8029.73 | 2087.7298
11 | Flaggers | HR | 29 | 5242.75 | 152039.75
12 | Temporary Connection - Asphalt Concrete Pavement | Mg | 46 | 2162.13 | 99457.98
13 | Temporary Connection - Aggregate Base | Mg | 13.25 | 1154.2 | 15293.15
14 | Erosion Control | LS | 93000 | 0.99 | 92070
15 | Aggregate Construction Entrance | EA | 800 | 4 | 3200
16 | Silt Fence, Unsupported | m | 5.5 | 4962.5 | 27293.75
17 | Inlet Protection | EA | 75 | 69 | 5175
18 | Biofilter Bags | m | 10 | 427 | 4270
19 | Erosion Control Matting | m2 | 3.25 | 0 | 0
20 | Silt Curtain | m | 6.55 | 15.4 | 100.87
21 | Temporary Seeding | HA | 6000 | 0 | 0
22 | Removal Of Structures And Obstructions | LS | 150000 | 1.0003 | 150049.8
23 | Clearing And Grubbing | LS | 47000 | 1 | 47000
24 | Plastic Mesh Fencing | m | 5.6 | 277.5 | 1554
25 | Contingent Tree Removal | EA | 170 | 2 | 340
26 | General Excavation | m3 | 9 | 23070.99 | 207638.91
27 | Berm Embankment | m3 | 3.4 | 8600 | 29240
28 | Eps Geofoam Blocks | m3 | 66 | 750.32 | 49521.12
29 | 300mm Subgrade Stabilization | m2 | 10 | 0 | 0
30 | Nordstrom Site Improvements | LS | 38600 | 1 | 38600
31 | Trench Dewatering | LS | 50000 | 1 | 50000
32 | Trench Foundation Stabilization | m3 | 42 | 678.97 | 28516.74
33 | Exploratory Excavation | EA | 275 | 94 | 25850
34 | 75mm Drain Pipe | m | 15.7 | 6862 | 107733.4
35 | 300 mm Concrete Storm Sewer Pipe | m | 123 | 2402.8 | 295544.4
36 | 375 mm Concrete Storm Sewer Pipe | m | 148 | 244.8 | 36230.4
37 | 450 mm Concrete Storm Sewer Pipe | m | 144 | 873.79 | 125825.76
38 | 600 mm Concrete Storm Sewer Pipe | m | 240 | 51.3 | 12312
39 | 300 mm Ductile Iron Storm Sewer Pipe | m | 129 | 696.5 | 89848.5
40 | 375 mm Ductile Iron Storm Sewer Pipe | m | 222 | 0 | 0
41 | 450 mm Ductile Iron Storm Sewer Pipe | m | 280 | 119.4 | 33432
42 | 375 mm Concrete Sanitary Sewer Pipe | m | 168 | 779.94 | 131029.92
43 | Television Inspection | m | 2.3 | 3123.65 | 7184.395
44 | 300 mm PVC Utility Conduit | m | 96 | 122.1 | 11721.6
45 | 1200 mm Concrete Manholes | EA | 2050 | 44 | 90200
46 | 1350 mm Concrete Manholes | EA | 2850 | 0 | 0
47 | 1500 mm Concrete Manholes | EA | 4900 | 9 | 44100
48 | 1800 mm Concrete Manholes | EA | 6000 | 3 | 18000
49 | 2100 mm Concrete Manholes | EA | 8200 | 1 | 8200
50 | 1200 mm Concrete Manholes, Type B-P | EA | 1650 | 21 | 34650
51 | 1200 mm Concrete Sanitary Manholes | EA | 2500 | 8 | 20000
52 | Concrete Inlets, Type CG-2 | EA | 760 | 51 | 38760
53 | Concrete Inlets, Modified Type CG-3 | EA | 850 | 102 | 86700
54 | Concrete Inlets, Type G-2 | EA | 725 | 14 | 10150
55 | Drainage Curbs | m | 8.5 | 64.5 | 548.25
56 | Adjusting Inlets | EA | 200 | 0 | 0
57 | Adjusting Manholes | EA | 300 | 20 | 6000
58 | Reconstructing Manholes | EA | 800 | 12 | 9600
59 | Adjusting Boxes | EA | 180 | 58 | 10440
60 | Adjusting Monitoring Well Boxes with Traffic Bearing Lid | EA | 150 | 0 | 0
61 | 1500 mm Concrete Manholes, Flow Split | EA | 3300 | 5 | 16500
62 | 1800 mm Concrete Manholes, Flow Split | EA | 5000 | 3 | 15000
63 | 1500 mm Concrete Manholes, Sedimentation | EA | 5000 | 6 | 30000
64 | 1.8 X 2.4 Concrete Water Quality Filter Units | EA | 23000 | 1 | 23000
65 | 1.8 X 3.6 Concrete Water Quality Filter Units | EA | 27000 | 1 | 27000
66 | 2.4 X 4.8 Concrete Water Quality Filter Units | EA | 38600 | 4 | 154400
67 | 375 X 375 Aluminum Slide Gate | EA | 1575 | 0 | 0
68 | 450 X 450 Aluminum Slide Gate | EA | 1850 | 0 | 0
69 | 525 X 525 Aluminum Slide Gate | EA | 1800 | 3 | 5400
70 | 600 X 750 Aluminum Slide Gate | EA | 2600 | 1 | 2600
71 | Fiberglass Hazardous Materials Spill Containment Tanks | EA | 66400 | 4 | 265600
72 | 1200 mm X 1200 mm Concrete Valve Vaults | EA | 6250 | 4 | 25000
73 | Drop Connection | EA | 1350 | 0 | 0
74 | Outfall Protection | EA | 720 | 0 | 0
75 | Modular Retaining Wall, Type I | m2 | 208 | 74.41 | 15477.28
76 | Modular Retaining Wall, Type II | m2 | 243 | 174.99 | 42522.57
77 | Modular Retaining Wall Railing | m | 150 | 51.2 | 7680
78 | Cold Plane Pavement Removal - 50 mm Deep | m2 | 0.8 | 32619.16 | 26095.328
79 | Aggregate Base | Mg | 13.3 | 23325.46 | 310228.618
80 | Pavement Base Repair | Mg | 46.75 | 368.46 | 17225.505
81 | Level 3, 19mm ATPB HMAC | Mg | 34.7 | 14040.82 | 487216.454
82 | Level 1, 12.5mm Dense HMAC | Mg | 47.5 | 3062.96 | 145490.6
83 | Level 4, 19mm Dense HMAC | Mg | 38.8 | 2497.72 | 96911.536
84 | Level 4, 25mm Dense HMAC | Mg | 38 | 543.51 | 20653.38
85 | Extra For Asphalt Approaches | EA | 360 | 33 | 11880
86 | Plain Concrete Pavement, Undowelled, 300mm Thick | m2 | 32 | 66733.58 | 2135474.56
87 | Concrete Walks | m2 | 18 | 8316.36 | 149694.48
88 | Concrete Island, Type C | m2 | 33.7 | 146.76 | 4945.812
89 | Concrete Driveways | m2 | 31.1 | 2115.91 | 65804.801
90 | Concrete Curb, Type C | m | 15.9 | 1478.1 | 23501.79
91 | Concrete Curb, Type A For Asphalt Pavement | m | 22 | 18.4 | 404.8
92 | Concrete Curb, Type A For Concrete Pavement | m | 32 | 6664.24 | 213255.68
93 | Guard Rail, Type 2a | m | 75 | 7.62 | 571.5
94 | Guard Rail, Type 3 | m | 75 | 13.62 | 1021.5
95 | Guard Rail Anchors, Type I Modified | EA | 750 | 2 | 1500
96 | Guard Rail End Pieces, Type B | EA | 450 | 4 | 1800
97 | Guard Rail Terminals, Flared | EA | 450 | 2 | 900
98 | Single Slope Concrete Barrier | m | 175 | 600 | 105000
99 | Pavement Legend, Type C: Arrows | EA | 300 | 22 | 6600
100 | Pavement Legend, Type C: Railroad Crossing Markings | EA | 1000 | 8 | 8000
101 | Pavement Legend, Type C: Railroad Crossing Markings On Multi-Use Path/Bike Lanes | EA | 675 | 0 | 0
102 | Pavement Legend, Type C: Bicycle Lane Symbols | EA | 250 | 0 | 0
103 | Pavement Legend, Type C: Diamonds | EA | 45 | 0 | 0
104 | Pavement Line, Type A | m2 | 55 | 121.4 | 6677
105 | Painted Permanent Pavement Striping (Exisitng Pavement) | m | 0.42 | 0 | 0
106 | Permanent Pavement Striping (New Asphalt Conc.) | m | 2.75 | 0 | 0
107 | Thermoplastic, Non-Profile, 3.0 mm, Extruded (New Portland Cement Conc.) | m | 1.4 | 14782 | 20694.8
108 | Island Nose Treatment | m | 3 | 0 | 0
109 | Pavement Line Removal | m | 2 | 4238.17 | 8476.34
110 | Pavement Legend Removal | EA | 150 | 0 | 0
111 | Crosswalk Barricades | EA | 300 | 2 | 600
112 | Remove Existing Signs | LS | 2500 | 1 | 2500
113 | Remove And Reinstall Existing Signs | LS | 2000 | 0.5 | 1000
114 | Sign Support Footings | LS | 3700 | 0.39 | 1443
115 | Pipe Sign Posts | EA | 75 | 29 | 2175
116 | Luminaire Pole Sign Mounts | LS | 1850 | 0.3 | 555
117 | Type "G" Signs In Place | m2 | 249 | 0.56 | 139.44
118 | Type "W1" Signs In Place | m2 | 154 | 6.04 | 930.16
119 | Type "W4" Signs In Place | m2 | 146 | 1.49 | 217.54
120 | Type "Y1" Signs In Place | m2 | 155 | 12.97 | 2010.35
121 | Pole Foundations | LS | 99800 | 0.9902 | 98821.96
122 | Lighting Poles, Fixed Base | LS | 75000 | 0.99 | 74250
123 | Lighting Pole Arms | LS | 24200 | 0.99 | 23958
124 | Luminaires, Lamps and Ballasts | LS | 18000 | 0.99 | 17820
125 | Switching, Conduit, Wiring, Etc. | LS | 200000 | 0.99 | 198000
126 | Refurbishing And Reinstaling Exist.Illum. System | LS | 24800 | 0.94 | 23312
127 | Traffic Signal Interconnect Conduit | LS | 75000 | 0.99 | 74250
128 | Traffic Signal Installation, Complete | EA | 101300 | 0.965 | 97754.5
129 | Fire Preemtion System, Complete | EA | 8600 | 0.5 | 4300
130 | Model 170 Controller, Complete | EA | 14350 | 0.99 | 14206.5
131 | Loop Detector Installation, Complete | EA | 41600 | 0.45 | 18720
132 | Topsoil, 150 mm Depth | m2 | 4 | 15243.03 | 60972.12
133 | Topsoil, 50 mm Depth | m2 | 1.35 | 3580.8 | 4834.08
134 | Seeded Lawn | m2 | 1.9 | 2593.9 | 4928.41
135 | Rough Lawn | m2 | 1 | 0 | 0
136 | Deciduous Trees, 90 mm | EA | 380 | 0 | 0
137 | Evergreen Trees, 1.50 M | EA | 132 | 0 | 0
138 | Shrubs, No. 1 Container | EA | 6.5 | 2717 | 17660.5
139 | Shrubs, No. 2 Container | EA | 13 | 0 | 0
140 | Trees, No. 3 Container | EA | 29 | 0 | 0
141 | Trees Or Shrubs, No. 5 Container | EA | 33 | 0 | 0
142 | Groundcovers, 100 mm Pots | m2 | 2.4 | 574.4 | 1378.56
143 | Groundcovers, No. 1 Container | m2 | 5.6 | 2034.08 | 11390.848
144 | Root Barriers | EA | 64 | 45 | 2880
145 | Soil Conditioner, 50 mm Depth | m2 | 1.65 | 16970.43 | 28001.2095
146 | Soil Conditioner, 25 mm Depth | m2 | 1 | 3797.4 | 3797.4
147 | Bark Mulch, 50 mm Depth | m2 | 2.7 | 7171.4 | 19362.78
148 | Transplant Trees | EA | 230 | 0 | 0
149 | Irrigation System | LS | 100000 | 0.83 | 83000
150 | Type CL-6R Fence | m | 38 | 95.9 | 3644.2
151 | 4.8 m Double Gates | EA | 800 | 1 | 800
151A | PCC Curb Wall | m | 200 | 25.3 | 5060
151B | Deciduous Trees, 60 mm | EA | 290 | 0 | 0
152 | Adjust ARV MH | EA | 780 | 2 | 1560
153 | Trench Excavation | m3 | 12.5 | 2493.27 | 31165.875
154 | Trench Backfill (Imported - 1.2m Trench) | m3 | 17.6 | 50.06 | 881.056
155 | Trench Backfill (Native - 1.2m Trench) | m3 | 16.75 | 1344.89 | 22526.9075
156 | 600mm DI Restrained Pipe w/ Pipezone Backfill | m | 285 | 152.45 | 43448.25
157 | 600mm DI Pipe w/ Pipezone Backfill | m | 120 | 882.5 | 105900
158 | 150mm Service Line | EA | 4000 | 2 | 8000
159 | 300mm Service Line | EA | 6400 | 4 | 25600
160 | 600mm Butterfly Valves | EA | 3385 | 9 | 30465
161 | 50mm Air / Vacuum Valve Assembly | EA | 3100 | 4 | 12400
162 | 150mm Blow Off Assembly | EA | 5152 | 5 | 25760
163 | Fire Hydrant Assembly | EA | 3800 | 11 | 41800
164 | Waterline Casing & Appurtenances | LS | 38800 | 1 | 38800
165 | 75mm AC Pavement Base Lift, Class B | m2 | 44.25 | 24 | 1062
166 | 75mm AC Pavement Top Lift, Class B | m2 | 15.7 | 661 | 10377.7
167 | 150mm Crushed Rock Pavement Base | m2 | 15.6 | 100 | 1560
| SUBTOTAL |  |  |  | 9065886.6048
| Interest Paid for Payment No.'s 8,16,18 & 20 |  |  |  | 1371.4
| Materials on Hand |  |  |  | 33765
TOTAL RCI CONTRACT EXPENDITURES TO DATE |  |  |  |  | 9101023.1048
| Total Change Orders Authorized to RCI to Date |  |  |  | 10001.9384
OUTFALL CONTRACT WORK
FINAL PAYMENT
NO. | ITEMS OF WORK AND MATERIALS | UNIT | UNIT PRICE | QUANTITY | AMOUNT
1 | Mobilization | ls | 3090.8 | 1 | 3090.8
2 | Temp. Protect. & Direction of Traffic | ls | 150 | 1 | 150
3 | Flaggers | hr | 33 | 24.5 | 808.5
4 | Erosion Control | ls | 750 | 1 | 750
5 | Aggregate Construction Entrances | ea | 1200 | 2 | 2400
6 | Silt Fence, Unsupported | m | 8 | 72.4 | 579.2
7 | Inlet Protection | ea | 82.5 | 4 | 330
8 | Erosion Control Matting | m2 | 5.5 | 132 | 726
9 | Silt Curtain | ea | 600 | 1 | 600
10 | Removal of Structures & Obstructions | ls | 500 | 1 | 500
11 | Plastic Mesh Fencing | m | 5.4 | 179 | 966.6
12 | Trench Dewatering | ls | 500 | 1 | 500
13 | Trench Foundation Stabilization | m3 | 27 | 0 | 0
14 | 450 mm HDPE Storm Sewer Pipe | m | 128 | 54.6 | 6988.8
15 | Extra for Pipe under Pavement | m | 87.5 | 18 | 1575
16 | ABS Pipe Connection | ea | 900 | 1 | 900
17 | Outfall Protection | ea | 1900 | 2 | 3800
| SUBTOTAL |  |  |  | 24664.9
| Total Change Orders Authorized to Cipriano & Son Construction |  |  |  | 8898.4
TOTAL CIPRIANO & SON CONTRACT EXPENDITURES |  |  |  |  | 33563.3
PROPERTY MODIFICATIONS CONTRACT WORK
FINAL PAYMENTS
NO. | ITEMS OF WORK AND MATERIALS | UNIT | UNIT PRICE | QUANTITY | AMOUNT
1 | Mobilization | LS | 2200 | 1 | 2200
2 | Removal of Structures and Obstructions | LS | 500 | 1 | 500
3 | Clearing and Grubbing | LS | 750 | 1 | 750
4 | Silt Fence | M | 3.85 | 65 | 250.25
5 | Inlet Protection | EA | 33.33 | 5 | 166.65
6 | General Excavation | M3 | 11.42 | 712.36 | 8135.1512
7 | 250 mm Storm Sewer Pipe (Incl.: Exc., Bed, Backfill) | M | 127.65 | 6.1 | 778.665
8 | Lynch Type Catch Basin | EA | 750 | 1 | 750
9 | Drainage Curb | M | 9 | 260 | 2340
10 | Aggregate Base | MG | 14.69 | 791.55 | 11627.8695
11 | Asphalt Concrete Pavement | MG | 77 | 510.61 | 39316.97
12 | Irrigation Sleeve | M | 15 | 36.29 | 544.35
13 | Concrete Driveway | M2 | 112.9 | 27 | 3048.3
14 | Temporary Driveway Connection | M2 | 5.35 | 112.06 | 599.521
15 | Adjust Manhole | EA | 250 | 1 | 250
16 | Relocate Chain Link Fence | M | 10.25 | 136.6 | 1400.15
17 | Install Stockpiled Gate | EA | 750 | 1 | 750
| SUBTOTAL |  |  |  | 73407.8767
| Total Change Orders Authorized to NW General |  |  |  | 90.44
TOTAL NW GENERAL CONTRACT EXPENDITURES |  |  |  |  | 73498.3167
TOTAL CONTRACT BID ITEMS AUTHORIZED TO DATE |  |  |  |  | 9208084.7215
Additional Estimated Contract Bid Item Expenses |  |  |  |  | 432229.86
Contingency (RCI Change Orders) Spent To Date |  |  |  |  | 10001.9384
Additional Estimated Contingency Expenses |  |  |  |  | 250000
Construction Engineering To Date |  |  |  |  | 1277714.05
Additional Estimated Construction Engineering Expenses |  |  |  |  | 150000
Railroad Modifications |  |  |  |  | 547303
BWW Expenditures To Date |  |  |  |  | 407268.21
Additional Estimated BWW Expenditures |  |  |  |  | 20000
CH2M Hill - Design Expenditures |  |  |  |  | 1421841.47
City of Portland - Design Expenditures |  |  |  |  | 321455
Right-Of-Way |  |  |  |  | 134380
TOTAL N MARINE DRIVE PROJECT EXPENDITURES |  |  |  |  | 14180278.2499
Port of Portland Contribution per IGA:

## Final Assessment Detail
Seq | Lien Account # | Legal Description | Owner / Mailing Address | Account # | Actual S.F. | Assess. S.F. | Project Share | Extra Work | Total | Recording | Final Assessment | Real Mkt. Value | V/A Ratio | Discount
Albina
1 | 131436 | PARTITION PLAT 1996-178; TL 1200 LOT 2; LAND 97.24% EXEMPT 307.120 IMPS 75.51% EXEMPT 307.120 | PORT OF PORTLAND(LEASED HYUNDA | 2N1W24 1200 | 3267002 | 3267002 | 3297350.98 | 0 | 3297350.98 | 28 | 3297378.98 | 24058590 | 7.2963 | 0%
|  |  | P O BOX 3529 | (R649767100)
PORTLAND, OR 97208-3529
2 | 131437 | RIVERGATE INDUSTRIAL DIS, BLOCK 19, LOT 2 TL 800 | PORT OF PORTLAND | 2N1W24 800 | 3264152 | 3264152 | 3294474.5 | 0 | 3294474.5 | 28 | 3294502.5 | 16102550 | 4.8877 | 0%
|  |  | P O BOX 3529 | (R708884800)
PORTLAND, OR 97208-3529
3 | 131438 | SECTION 24 2N 1W; TL 500 7.48 ACRES | PORT OF PORTLAND | 2N1W24 500 | 322423 | 322423 | 325418.16 | 0 | 325418.16 | 28 | 325446.16 | 9186800 | 28.2283 | 0%
|  |  | P O BOX 3529 | (R971240050)
PORTLAND, OR 97208-3529
4 | 131439 | RIVERGATE INDUSTRIAL DIS; LOT 1 BLOCK 19; ALSO SEE TAXABLE SUB -4702 | PORT OF PORTLAND | 2N1W24 200 | 3192475 | 3192475 | 3222131.65 | 0 | 3222131.65 | 28 | 3222159.65 | 39486590 | 12.2547 | 0%
|  |  | P O BOX 3529 | (R708884700)
PORTLAND, OR 97208-3529
4 |  |  | Total: |  | 10046052 | 10046052 | 10139375.29 | 0 | 10139375.29 | 112 | 10139487.29 | 88834530 | 8.7612
Notes: None |  |  |  | Assessment Rate (exclusive of recording fee): |  |  | 1.0093