## Resources
RESOURCES
Federal | 5800000
ODOT Rail Funds | 600000
UPRR Design | 65000
UPRR Crossing Blockage Fines | 1000000
LID (fixed and not-to-exceed) | 3775000
SDC cash | 2537000
Tri-Met | 1986251
Tri-Met (In kind engineering services) | 350000
Water Bureau for Water Line | 295710
BES for Sewer Line | 25500
TOTAL RESOURCES | 16434461

## Summary
COST ESTIMATE
Final Costs
Contracted through Tri-Met
| Bridge and Civil | 6339537.0912 | See Const Comb Worksheet-close to final
| Raise Interstate Ave | 2486251 | Set with Tri-Met
| Subtotal Tri-Met Contract | 8825788.0912
Other Constuction
| Water by BWW Crews | 126941 | Final
| UPRR Work (Lump Sum+ Flagging) | 645576.6 | Final
| Glacier NW Access Settlement (Lump Sum) | 145000 | Final
| Utility Relocations (ELI & UPRR Fiber Optic) | 101482.79 | Final
| Demo Valvoline Building | 56901 | Final
| Total Construction | 9901689.4812
Right-of-Way
| ROW | 3804676.39 | Final
| ROW Contingency | 10000 | Very likely needed
| ROW Total | 3814676.39
Management, Engineering
| Preliminary Engineering | 1567042.7 | Final
| Construction Engineering | 1133033.93 | See Eng Worksheet- close to final
| Auditor's Fees | 18018.5
| Total Mgt, Eng & Financing | 2718095.13
| TOTAL PROJECT COSTS | 16434461.0012
| RESOURCES | 16434461
| NEEDED | 0.0012375

## Construction Combined
Lower Albina Overcrossing
Bridge & Roadway
NO. | ITEM | UNIT | QUANTITY | UNIT COST | TOTAL
Part 00200 Mobilization, Erosion and Traffic Control
1 | Mobilization | LS | 1 | 573700 | 573700
2 | Temp. Protection and Direction of Traffic | LS | 1 | 100000 | 100000
3 | Temporary Signs | M2 | 37.79 | 162 | 6121.98
4 | Temporary Barricades, Type III | Each | 16 | 96 | 1536
5 | Temporary Plastic Drums | Each | 26 | 97 | 2522
6 | Temporary Flexible Pavement Markers | Each | 15 | 3 | 45
7 | Temporary Concrete Barrier, Reflectorized | M | 342.7 | 65 | 22275.5
8 | Flaggers | Hour | 217 | 29 | 6293
9 | Erosion Control | LS | 1 | 20000 | 20000
10 | Storm Drain Inlet Protection | Each | 22 | 31 | 682
11 | Silt Fence, Unsupported | M | 115 | 6 | 690
12 | Aggregate Construction Entrances | Each | 4 | 1200 | 4800
13 | Permanent Seeding and Fertilizing, and Mulching | HA | 0.06 | 6000 | 360
14 | Construction Survey Work | LS | 1 | 60000 | 60000
799025.48
Part 00300 Roadwork
15 | Removal of Structures and Obstructions | LS | 1 | 50000 | 50000
16 | Removal of Existing Concrete Building, Complete | LS | 1 | 81000 | 81000
17 | Asbestos Abatement, Complete | LS | 1 | 27730 | 27730
18 | PCB Floor Staining Abatement | SM | 0 | 100 | 0
19 | PCB Ballast & Fluorescent Tube Abatement, Complete | LS | 1 | 9200 | 9200
20 | Clearing and Grubbing | LS | 1 | 10000 | 10000
21 | Subgrade Geotextile | M2 | 5450.71 | 1.5 | 8176.065
22 | Settlement Plates | Each | 6 | 2500 | 15000
23 | Embankment in Place | M3 | 7090 | 25 | 177250
24 | Preload Fill | LS | 1 | 47000 | 47000
425356.065
Part 00400 Drainage and Sewers
25 | Stormwater Treatment Facility | LS | 1 | 22000 | 22000
26 | 75 mm Drain Pipe | M | 360 | 24 | 8640
27 | 200 mm Sanitary Sewer Pipe | M | 68.98 | 250 | 17245
28 | 250 mm Sanitary Sewer Pipe | M | 71.5 | 250 | 17875
29 | 300 mm Sanitary Sewer Pipe | M | 50.6 | 260 | 13156
30 | 250 mm Storm Sewer Pipe | M | 79.68 | 260 | 20716.8
31 | 300 mm Storm Sewer Pipe | M | 98.45 | 290 | 28550.5
32 | Extra for Pipe Under Pavement | M | 156 | 50 | 7800
33 | Concrete Manholes, Storm and Sanitary | Each | 6 | 3000 | 18000
34 | Concrete Inlets, Type CG-2 | Each | 6 | 1500 | 9000
35 | Concrete Inlet, Type G-2 | Each | 5 | 1300 | 6500
36 | Concrete Inlet, Type G-2MA | Each | 2 | 1300 | 2600
37 | Adjusting Manholes | Each | 10 | 250 | 2500
38 | Adjusting Valves | Each | 12 | 150 | 1800
39 | Adjusting Inlets | Each | 6 | 300 | 1800
40 | Modify Manholes | Each | 0 | 1200 | 0
41 | Reconstruct Manholes | Each | 2 | 2500 | 5000
42 | Trench Foundation Stabilization | CM | 0 | 60 | 0
43 | Connection of Sanitary Lateral | Each | 2 | 500 | 1000
44 | Television Inspection | M | 180.6 | 6 | 1083.6
185266.9
NO. | ITEM | UNIT | QUANTITY | UNIT COST | TOTAL
Part 00500 Structures
Bridge
45 | Structural Concrete, Class 30 | LS | 1 | 351000 | 351000
46 | Structural Concrete, Class 35 | LS | 1 | 935000 | 935000
47 | Structural Concrete, Class 45 | LS | 1 | 400000 | 400000
48 | Reinforcement | LS | 1 | 285000 | 285000
49 | Coated Reinforcement | LS | 1 | 105000 | 105000
50 | Single Slope Concrete Bridge Rail | LS | 1 | 60000 | 60000
51 | Structure Excavation | LS | 1 | 30000 | 30000
52 | Granular Wall Backfill | M3 | 167.44 | 60 | 10046.4
53 | Granular Structure Backfill | M3 | 463.06 | 46 | 21300.76
54 | Furnish Pile Driving Equipment | LS | 1 | 20000 | 20000
55 | Furnish PP 356 X 12.7 Piles | M | 3022.68 | 65 | 196474.2
56 | Furnish PP 356 X 12.7 Test Piles | M | 89.25 | 65 | 5801.25
57 | Drive PP 356 X 12.7 Piles | Each | 166 | 400 | 66400
58 | Drive PP 356 X 12.7 Test Piles | Each | 5 | 700 | 3500
59 | PP 356 X 12.7 Steel Pile Splices | Each | 66 | 1 | 66
60 | Post Tensioning | LS | 1 | 260000 | 260000
61 | Reinf. Pile Tip | Each | 171 | 100 | 17100
62 | Bridge Drains | Each | 3 | 3500 | 10500
63 | Preformed Elastomeric Strip Seals | LS | 1 | 38000 | 38000
64 | Asphaltic Plug Joint Seal | LS | 1 | 7500 | 7500
65 | Fence, Protective-Type B (std) | M | 231 | 170 | 39270
66 | Fence, Protective-Type A (modified) | M | 60 | 184 | 11040
67 | Span 4- Lifting and Lowering | LS | 1 | 140000 | 140000
68 | Reinforced Concrete End Panels | M2 | 184 | 145 | 26680
69 | Shoring, Cribbing, etc | LS | 1 | 22000 | 22000
3061678.61
Retaining Walls
70 | Retaining Wall, Contractor Option | M2 | 169.1 | 216 | 36525.6
71 | Retaining Wall, CIP Concrete | M2 | 67 | 300 | 20100
72 | Temporary Geotextile Wall | LS | 1 | 20000 | 20000
73 | Single Slope Concrete Rail on Wall | LS | 1 | 7500 | 7500
84125.6
Part 00600 Bases
74 | Aggregate Base, Subbase and Shoulders | Mg | 3205.02 | 24 | 76920.48
75 | Level 3 19 mm Open Graded HMAC | Mg | 618.7 | 48 | 29697.6
106618.08
Part 00700 Wearing Surfaces
76 | Plain, Dowelled Concrete Pavement, 300mm | M2 | 2827.16 | 55 | 155493.8
77 | Asphalt Concrete Pavement (Commercial Mix) | Mg | 2613.68 | 49 | 128070.32
78 | Extra for Asphalt Approaches | Each | 2 | 300 | 600
79 | Extra for Rail Paving | M | 60 | 45 | 2700
80 | PCC to AC Transition | Each | 4 | 150 | 600
81 | Concrete Curb,Type C | M | 808 | 75 | 60600
82 | Concrete Curb, Type A | M | 87.33 | 90 | 7859.7
83 | Drainage Curb | M | 23.6 | 40 | 944
84 | Concrete Driveways | M2 | 180.63 | 55 | 9934.65
85 | Concrete Walks | M2 | 1237.2 | 45 | 55674
86 | Concrete Island | M2 | 0 | 30 | 0
422476.47
NO. | ITEM | UNIT | QUANTITY | UNIT COST | TOTAL
Part 00800 Permanent Traffic Control and Guidance Devices
87 | Impact Attenuator, 69" Wide | Each | 2 | 35000 | 70000
88 | Impact Attenuator, 36" Wide | Each | 2 | 25000 | 50000
89 | Concrete Shoulder Barrier, Reflectorized | M | 186.7 | 100 | 18670
90 | Concrete Barrier, Single Slope, Reflectorized | M | 21 | 95 | 1995
91 | Permanent Closure Barricades | M | 112.9 | 85 | 9596.5
92 | Permanent Closure Railroad Gates | Each | 3 | 8000 | 24000
93 | Crosswalk Closure Barricades | Each | 1 | 750 | 750
94 | Permanent Pavement Striping Tape, Hot-Inlaid | M | 0 | 6 | 0
95 | Methyl Methacrylate, Profile, 3.0mm, Extruded | M | 1409 | 6 | 8454
96 | Pavement Legend, Type B: Bicycle Lane Symbol | Each | 5 | 350 | 1750
97 | Pavement Legend, Type B: Arrows | Each | 3 | 200 | 600
98 | Pavement Line, Type A | M2 | 0 | 50 | 0
99 | Pavement Legend, Type B: Diamonds | Each | 0 | 350 | 0
185815.5
Part 00900 Permanent Traffic Control and Illumination Systems
100 | Pipe Sign Posts | LS | 1 | 12000 | 12000
101 | Luminaire Pole Sign Mounts | LS | 1 | 500 | 500
102 | Barrier Sign Mounts | LS | 1 | 1600 | 1600
103 | Type W1 Signs In Place | M2 | 6.52 | 200 | 1304
104 | Type W2 Signs In Place | M2 | 1.88 | 190 | 357.2
105 | Type Y1 Signs In Place | M2 | 10.86 | 200 | 2172
106 | Type G Signs in Place | M2 | 0.64 | 200 | 128
107 | Type R Signs In Place | M2 | 14.28 | 200 | 2856
108 | Type W4 Signs In Place | M2 | 1.88 | 200 | 376
109 | Type WA Signs In Place | M2 | 0 | 200 | 0
110 | Remove Existing Signs | LS | 1 | 6000 | 6000
111 | Remove and Reinstall Existing Signs | LS | 1 | 1500 | 1500
112 | Roadway Illumination Installation, Complete | LS | 1 | 144250 | 144250
173043.2
Part 01000 Right of Way Development and Control
113 | CL6 Chain Link Fence | M | 77 | 130 | 10010
114 | Monument Boxes, Installed | Each | 0 | 125 | 0
115 | Multiple Mailbox Supports | Each | 1 | 600 | 600
10610
Water Main Relocation
116 | Mobilization | LS | 1 | 30000 | 30000
117 | Trench Excavation | CM | 709 | 20 | 14180 | 47 | 940
118 | Trench Backfill (imported) | CM | 360 | 21 | 7560 | 77 | 1617
119 | 400mm Calss 52 Restrained D.I. Pipe, w/ Pipe Zone Bedding & Backfill | LM | 346.4 | 330 | 114312
120 | 200mm Calss 52 Restrained D.I. Pipe, w/ Pipe Zone Bedding & Backfill | LM | 17.5 | 157 | 2747.5
121 | Steel Casing, 900 mm O.D. x 16 mm Wall Thickness | LM | 30.48 | 2000 | 60960
122 | 38mm Top Lift A.C. Pavement, Class C | SM | 199.59 | 20 | 3991.8 | 49.51 | 990.2
123 | 38mm Base Lift A.C. Pavement, Class B | SM | 199.59 | 18 | 3592.62 | 49.51 | 891.18
124 | 150mm Concrete Pavement Resurfacing | SM | 202.27 | 57 | 11529.39 | 65.37 | 3726.09
125 | 200mm Crushed Rock Pavement Base | CM | 65 | 27 | 1755 | 3.5 | 94.5
126 | 400mm Butterfly Valve | EA | 6 | 2500 | 15000
127 | 200mm Gate Valve | EA | 2 | 900 | 1800
128 | 150mm Gate Valve | EA | 2 | 600 | 1200
129 | 100mm Gate Valve | EA | 0 | 500 | 0
130 | TF500 Blow-Off/Air Release Assembly | EA | 3 | 600 | 1800
131 | Hydrant Assemblies | EA | 4 | 3000 | 12000 | 1 | 3000
132 | Cathodic Protection Anodes | EA | 0 | 500 | 0
133 | Construction Signs | EA | 0 | 500 | 0
134 | Survey | LS | 1 | 2000 | 2000
135 | Flagging | HR | 71 | 35 | 2485
136 | Temporary Protection and Direction of Traffic | LS | 1 | 2000 | 2000
[5 empty] | 288913.31 |  | 11258.97
277654.34
| Subtotal: |  |  |  | 5742929.215
| CM / GC Fee @ 4.25% |  |  |  | 244074.4916
5987003.7066
Contract Change Orders
| CCO No. 18: Lower Albina Contract Time Extension |  |  |  | 0
| CCO No. 19: Remove Tucker Building Debris |  |  |  | 9348.15
| CCO No. 19: Demo Van Raden Building |  |  |  | 7888.4
| CCO No. 19: Depose leaking PCB light ballasts |  |  |  | 2285.8
| CCO No. 19: PCB Concrete Removal |  |  |  | 33386.85
| CCO No. 34: Hazmat Lower Albina Bridge |  |  |  | 129991.15
| CCO No. 35: Remove Abandoned Elevator Shaft |  |  |  | 582.37
| CCO No. 35: Abandon Piezometer Wells |  |  |  | 845.85
| CCO No. 35: Compensation for Construction Easement |  |  |  | 2500
| CCO No. 38: Add'l Pile Quantity/Splicing/Plate Tips |  |  |  | 74513.36
| CCO No. 43: Catch Basin on VanRaden Property |  |  |  | 4207.36
| CCO No. 43: 8" Water Main at Albina / River |  |  |  | 18410.98
| CCO No. 43: Install 1" Insulating Service Corps |  |  |  | 211.46 |  | 211.46
| CCO No. 43: Utility Fees for Span Wire Removal |  |  |  | 2392.49 |  | 277865.8
| CCO No. 43: Install Power Pole Guy Line Anchor |  |  |  | 349.62
| CCO No. 48: Delete Street Light Luminaire #16 |  |  |  | -2094.38
| CCO No. 48: Valvoline Spur Track Removal |  |  |  | 21960.59
| CCO No. 57: Roadway Foundation Stabilization |  |  |  | 3527.6046
| CCO No. 75: Fence Holes, RR Flaging, River St. Inlets |  |  |  | -14712.89
| CCO No. 80: Civil and Structural Revisions |  |  |  | 41716.03
| CCO No. 85: Reconcile CCO No. 34 Final Amount |  |  |  | 3545.12
| CCO No. __: Corrosion Protection Anodes |  |  |  | 10344.24
CCO No. __: Relocate WC Manhole
CCO No. __: LA Sewer Redesign, Abandon Storm / Sanitary
| Subtotal: |  |  |  | 351200.1546
| Potential Change Orders |  |  | (requested) | Latest Est.
PC246: Sewer
| 840 - Storm, Sanitary & Gas Line Conflicts |  |  | 1373.39 | 0
| 872 - Redesign Sanitary Sewer |  |  | 14904.82 | 0
| 874 - Encountered Concrete Wall | " |  | 1235.38 | 636.61
| 875 - Concrete Removal | " |  | 2421.37 | 0
| 877 - Ductbank Encounter | " |  | 829.46 | 696.62
| 950 - Concrete Rail crossing Encounter |  |  | 2233.19 | 0
| 956 - Encountered Utilities | " |  | 1673.16 | 0
PC247: Water
| 893 - Abandon Sewer Pipes | " |  | 7479.62 | 0
| 887 - Relocate WQ Manhole |  |  | 10362.51 | 0
| 979 - Adjust MH#6 and MH#7 |  |  | 0 | 0
| PC248: Accelleration | Zero!
1333.23
| Total Plus CO's and PC's |  |  |  | 6339537.0912
Raise Interstate & Traffic Signal |  | NOT UPDATED
SWI 100%
Bid Item | ITEM | UNIT | QUANTITY | UNIT COST | Subtotal
Structural Elements
2050.10 | Viaduct Removal | LS | 1 | 156000 | 156000
2227.01 | Geofoam | CY | 4348 | 110 | 478280
2233.01 | Aggregate Base | CY | 1502 | 36 | 54072
2160.01 | Curtain Wall / Crash Wall / 3' Shafts | SF | 5027 | 45 | 226215
2465.01 | Drilled Shaft, 3' dia | LF | 2330 | 350 | 815500
2513.01 | Reinforced Concrete Bridge End Panel | SF | 3013 | 18 | 54234
2525.12 | Intergral Concrete Parapet / Sidewalk | LF | 326 | 150 | 48900
2525.13 | Intergral Concrete Parapet / Sidewalk w Cantilever | LF | 46 | 210 | 9660
| Traffic control - concrete barrier | LF | 150 | 30 | 4500
| Special provisions, misc overhead items | 18.66% |  | 1847361 | 344671.5009
Civil Elements
Reconstruction due to profile change
2510 | A/C Pavement: | TN | 935 | 44 | 41140
2233.01 | 3/4"-0 Agg. Base | CY | 420 | 40 | 16800
2233.02 | 1 1/2"-0 Agg. Base | CY | 610 | 36 | 21960
2233.02 | 1 1/2"-0 Agg. Base 3.5' rock blanket over lightweight fill | CY | 3300 | 36 | 118800
| Embankment | CY | 420 | 35 | 14700
| Special provisions, misc overhead items | 18.66% |  | 213400 | 39815.1191
Reconstruction of Tillamook and adjacent parking
2510 | A/C Pavement: | TN | 60 | 44 | 2640
2233.01 | 3/4"-0 Agg. Base | CY | 25 | 40 | 1000
2233.02 | 1 1/2"-0 Agg. Base | CY | 37 | 36 | 1332
2525.07 | Sidewalk | SY | 290 | 35 | 10150
2720.05 | 10" CSP stub, plug & mark | LF | 30 | 98.5 | 2955
| Embankment | CY | 150 | 35 | 5250
| Special provisions, misc overhead items | 18.66% |  | 23327 | 4352.2366
Overlay at Existing Profile Grade, Interstate
2510 | AC, 2" Overlay | TN | 310 | 44 | 13640
2273.02 | Pavement Overlay Geotextile | SY | 500 | 15 | 7500
2050.02 | Cold Plane Pvmt. Rem. | SY | 500 | 6 | 3000
| Special provisions, misc overhead items | 18.66% |  | 24140 | 4503.9221
Overlay at Existing Profile Grade, Tillamook
2510 | AC, 2" Overlay | TN | 20 | 44 | 880
2273.02 | Pavement Overlay Geotextile | SY | 36 | 15 | 540
2050.02 | Cold Plane Pvmt. Rem. | SY | 36 | 6 | 216
| Special provisions, misc overhead items | 18.66% |  | 1636 | 305.2368
Traffic Signal Installation - Tillamook, Complete
2845.07 | Traffic Signal Installation - Complete | LS | 1 | 214000 | 214000
2845.2 | Traffic Signal Interconnection, Complete | LF | 155 | 9.4 | 1457
| Special provisions, misc overhead items | 18.66% |  | 215457 | 40198.904
| Subtotal: |  |  |  | 2759167.9195
| Minus change from drilled shaft to driven piles |  |  |  | -436467
| Total Raise Interstate |  |  |  | 2486251
Bid Item | Description | Quantity | Unit | Unit Cost | Total Amount
0.SP-04 | Permits (Contractor Furnished) | 1 | LS | 50000 | 50000
| Widmer Tenant Improvements | 1 | LS | 250000 | 250000
SP-15 | Traffic Control | 1 | LS | 3450000 | 3450000
| Ashgrove Temp Access | 1 | LS |  | 0
0.SP-21 | Special Workplace Training Program | 1 | LS | 35000 | 35000
| DBE Coordinator | 1635 | HRS | 105 | 171675
| Asbestos Removal Provisions | 0 | PS | 25000 | 0
0.SP-29 | Water Connection Permits | 20 | LS |  | 0
0.SP-59 | Pre-construction Record of Survey Monuments | 0 | LS | 0 | 0
0.SP-60 | Post-construction Record of Survey | 1 | LS | 20000 | 20000
1050.01 | Field Engineering | 1 | LS | 770000 | 770000
1150.01 | Project Noise & Vibration Control | 1 | LS | 123200 | 123200
1310.01 | Project Schedules | 1 | LS | 130000 | 130000
1400.01 | Quality Control | 1 | LS | 990000 | 990000
1450.01 | Hazardous and Contaminated Substance Health and Safety Plan | 1 | LS | 25000 | 25000
1460.01 | Unknown Hazardous & Contaminated Substances | 1 | LS | 50000 | 50000
1505.01 | Mobilization | 1 | LS | 7441500 | 7441500
1520.01 | Street Cleaning and Site Maintenance | 1 | LS | 180000 | 180000
1535.01 | Tree and Plant Protection Fencing | 0 | LS | 110000 | 0
1540.01 | Security | 1 | LS | 260000 | 260000
13946375
0.18658
|  |  | LS10ab 100% Total |  | 74749404
UPRR Track & Signal Work
Phase I: AEI Scanner relocation and Glacier Northwest track work |  |  |  |  | 444000
Phase II: Removal of spur and crossings in Railroad Avenue and associated signal work |  |  |  |  | 106000
Phase III: Remove Valvoline spur turnout & switch |  |  |  |  | 3600
Flagging |  |  |  |  | 91976.6
|  |  |  | TOTAL | 645576.6
Glacier NW Access Settlement
| Per Agreement |  |  |  | 145000
Utility Relocations (ELI & UPRR Fiber Optic)
| ELI |  |  |  | 6946.63
| Kewit |  |  |  | 94536.16
|  |  |  | TOTAL | 101482.79
Demo Valvoline Building
| City Bid |  |  |  | 43401
| Asbestos Change Order |  |  |  | 13500
| TOTAL |  |  |  | 56901
BWW Crews
| Construction (BWW project #3402 includes overhead - Betterment/Reimbursement split BWW 61%, PDOT 39%) PB #1for charges 7/1/01 - 6/30/02 & PB #6 for charges 8/1/02 - 10/23/02. |  |  |  | 89427
| Change Order (River and Albina 100% BTED) - project code Z1 |  |  |  | 21307
| Hydrant Kill and Install @ River (approx Sta 1+15 Rd)100% BTED - PB #5 for charges 7/1/02 - 7/31/02 |  |  |  | 10488
| Install IJ and reestablish Van Ryden service (3402-Z2) |  |  |  | 5719
| TOTAL |  |  |  | 126941

## ROW
Right-of-Way
| Real Estate | Relocation | Total | Contingency
Tucker Building (settled) | 1807612.71 | 331961.79 | 2139574.5
Van Raden (appraised) | 423000 | 20000 | 443000
PP&L (appraised) | 75014.67 |  | 75014.67
Gold (appraised)
Bradrick (Smith Bros)* |  |  | 20000 | 10000
Valvoline | 1067937.22 | 20000 | 1087937.22
UPRR (Crossing) | 39150 |  | 39150
TOTAL |  |  | 3804676.39 | 10000
ROW TOTAL WITH CONTINGENCY |  |  | 3814676.39
Tucker Tenant Relocations |  | (updated 1/14/2002)
TENANT | FIXED PMT | RELOCATION |  |  | STORAGE | Claims Submitted | Anticipated Claims
|  | Site Search | Move | Reestablish
Tom Tucker | [5 empty] | 0
Bob Byrd | 13865 |  |  |  |  | 13865
Cab-Tech |  | 1000 | 40081.5 |  |  | 46312.67
Cagoule |  | 242.75 | 1200 | 10000 |  | 11442.75
Don Roan |  | 1000 | 3342.3 |  |  | 12192.08
Dragon Maker |  |  | 2801.45 |  |  | 3704.93
First Inc. |  | 185 | 24500 |  |  | 24685
Geo-Hex | 20000 |  |  |  |  | 20000
Grace Weston |  | 1000 | 782.81 | 10000 |  | 11782.81
Greenbeans | 18449 |  |  |  |  | 18449
Howling Wolf (Christy Atherton-Schrack) |  | 1000 |  | 10000 |  | 20506.45
McGrath Sculpt |  | 1000 | 4001.65 | 10000 |  | 15001.65
Owen Carey | 20000 |  |  |  |  | 20000
Plazm Media |  | 1000 | 30454.3 | 10000 |  | 41454.3
Sign Scapes | 16549 |  |  |  |  | 16549
Strong Photography | 20000 |  |  |  |  | 20000
Studio J |  | 1694 | 1900 |  |  | 3594
Think Again | 7824.04 |  |  |  |  | 7824.04
Totals | 102822.04 | 8121.75 | 109064.01 | 50000 | 0 | 307363.68 | 10000
Protective Rent | 7698.11
Estimates - Moving Companies | 1900
Utilities | 5000
Grand Total | 331961.79

## Engineering
Preliminary Engineering
| Contracts |  | Expenditures Thru 6/30/99 | Expenditures FY 99-00 | Expenditures FY 00-01 | Total Design Engineering
STAFF
Signals/Street Lighting |  |  | 6094.06 | 336.65 | 1104.33 | 7535.04
Civil Design |  |  | 48296.59 | 27291.02 | 30826.78 | 106414.39
Traffic |  |  | 0 | 2242.24 | 1125.71 | 3367.95
Structures |  |  | 2948.62 | 1068.12 | 3686.03 | 7702.77
Survey |  |  | 23979.88 | 11939.56 | 2443.58 | 38363.02
ROW |  |  | 755.34 | 466.63 | 4706.86 | 5928.83
Others - Internal |  |  | 3725.62 | 466.58 | 2158.68 | 6350.88
TOTAL STAFF |  |  | 85800.11 | 43810.8 | 46051.97 | 175662.88
CH2M
Work Order F-1 | 446061.76 |  | 396833.55 | 49228.21
Amend A-1 | 116500 |  |  | 116500
Amend F-9 | 74334.77 |  |  | 74334.77
Amend A-3 | 426561.16 |  |  | 28554.47 | 398006.69
Amend A-5 | 196583.96 |  |  |  | 166159.03
Amend A-6 | 25118.23 |  |  |  | 25118.23
Total CH2M | 1285159.88 |  | 396833.55 | 268617.45 | 589283.95 | 1254734.95
Other Outside Services:
Tri-Met |  |  |  | -32554.58 |  | -32554.58
HNTB | 57000 |  |  | 27042.34 | 26132.81 | 53175.15
Olson Appraisal | 2100 | 2100 |  |  | 2325 | 2325
BES |  |  | 3789.12 | 494.68 | 12193.23 | 16477.03
Other |  |  |  | 2781.98 |  | 2781.98
M&S |  |  | 0 | 341.88 | 190.29 | 532.17
LGIP |  |  | 65000 |  |  | 65000
Total Other Services |  |  | 68789.12 | -1893.7 | 40841.33 | 107736.75
TOTAL OUTSIDE SERVICES |  |  | 465622.67 | 266723.75 | 630125.28 | 1362471.7
TOTAL DESIGN ENGINEERING |  |  | 551422.78 | 310534.55 | 676177.25 | 1538134.58
Final ODOT Billing
Work by ODOT |  |  |  |  | 25235.12
Non-Participating work by PDOT |  |  |  |  | 0.3
Remainder of deposit ($65,000 deposited into LGIP _______________) |  |  |  |  | 3672.7
28908.12
1567042.7
Construction Engineering
| Hours |  | Rate | Total | Actual to 9/25/02 | Est to Complete | Total
PDOT Staff
Project Engineer (Gailey) | 400 |  | 55 | 22000 | 9871.03 | 500
Andrew Aebi | [5 empty] | 2000
Structures | 300 |  | 50 | 15000 | 1528.22 | 500
Barrett | 2080 |  | 50 | 104000 | 76176.14
Street Lighting / Signals | 120 |  | 50 | 10000 | 3320.35 | 100
ROW |  |  |  |  | 4273.05 | 500
Traffic |  |  |  |  | 2036.88 | 500
Survey (Monumentation) |  |  |  |  | 7846.89 | 2600
Inspection |  |  |  |  | 250.87
M&S |  |  |  |  | 8636.02 | 600
Subtotal |  |  |  | 151000 | 113939.45 | 7300 | 121239.45
CH2M |  |  |  | 357154.64 | 302776.52 | 54378.12 | 357154.64
Total Original Contract |  |  | 240113.82
Total Amendment #1 |  |  | 52190.66
Total Amendment #2 |  |  | 32791.42
Total Amendment # 3 |  |  | 32058.74
Hahn & Associates |  |  |  | 30608.82 | 29345.81 |  | 29345.81
Original Contract |  |  | 18888.82
Amendment #1 |  |  | 3520
Amendment # 2 |  |  | 8200
URS / DEA for Tucker Property |  |  |  | 133200 |  |  | 130469.29
WO #1 |  |  | 17500 |  | 11460.69 | 3308.6
WO#2 (through DEA) |  |  | 75700 |  |  | 75700
Risk Assessment & Focus Feasibility Study |  |  | 40000 |  |  | 40000
DEA for Valvoline Property | [6 empty] | 5453.22
Building Permit Valvoline | [6 empty] | 1276.61
Real Property Consultants |  |  |  | 17008 | 9097.5 | 4000 | 13097.5
VanRaden reappraisal |  |  | 13508 |  | 9097.5
Valvoline leftover appraisal |  |  | 3500 |  |  | 4000
Mediator VanRaden |  |  |  | 2643.33 | 2643.33 |  | 2643.33
DEQ |  |  |  | 5000 |  |  | 11632.22
Tucker |  |  | 2000 |  | 5408.15 | 3000 | 8408.15
Valvoline PPA |  |  | 3000 |  | 2724.07 | 500 | 3224.07
PDOT SubTotal |  |  |  | 696614.79 |  |  | 672312.07
BWW Engineering |  |  |  | 35924.46 |  |  | 60705
Engineering (39% of $66,983) |  |  | 26105.82 |  | 24038.13 | 36667
BWW Crews (39% of $16,735) |  |  | 6526.65
Overhead (39% of $8,441) |  |  | 3291.99
BES Engineering | [6 empty] | 37711.32
37283.25
Tri-Met
Rabiner
Lostra | 300 |  | 100 | 30000
Liles | 2500 |  | 50 | 125000
Robbins | 800 |  | 50 | 40000
Hopkins | 500 |  | 55 | 27500
Cooper | 200 |  | 65 | 13000
Korsak | 300 |  | 100 | 30000
Project Support | 1200 |  | 65 | 78000
Subtotal |  |  |  | 350000 |  |  | 350000
Contingency |  |  |  | 50000 |  |  | 12305.54
TOTAL |  |  |  | 1132539.25 |  |  | 1133033.93