## Sheet1
2003
|  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ONE B |  | First Public Workshop | bar: JANUARY 1 to OCTOBER 44
December 2002 through January 27 2003 | bar: JANUARY 1 to JANUARY 4
| 3 | Steering Committee Meetings | bar: JANUARY 1 to JANUARY 4
| 6 | Technical Advisory Committee Meetings | bar: JANUARY 1 to JANUARY 4
| 10 | Public Workshop January 25, 2003 | bar: JANUARY 1 to JANUARY 4
Trips | bar: JANUARY 1 to JANUARY 4
Billing Points | bar: JANUARY 1 to JANUARY 5
TWO |  | Concept Alternatives & Schematic Design | bar: JANUARY 1 to FEBRUARY 9
January 28 through June 6, 2003 | bar: JANUARY 4 to JUNE 25
| 1 | Wetland/Stormwater Options Memo | bar: JANUARY 4 to JUNE 25
| 2 | Design Charette - Germany | bar: JANUARY 4 to JUNE 25
| 5 | Develop magnitude of cost estimate for each alternative | bar: JANUARY 4 to JUNE 25
| 7 | 2nd Public Workshop April 5 - Concept Alternatives | bar: JANUARY 4 to JUNE 25
Owner Review Period | bar: JANUARY 4 to JUNE 25
| 10 | Site Model of Preferred Design | bar: JANUARY 4 to JUNE 25
| 12 | Cost Estimate Preferred Alternative | bar: JANUARY 4 to JUNE 25
| 13 | 3rd Public Workshop June 4, 2003 | bar: JANUARY 4 to JUNE 25
Owner Review Period | bar: JANUARY 4 to JUNE 25
| 15 | Technical Advisory Committee Meetings (max 3) | bar: JANUARY 4 to JUNE 25
| 16 | Steering Committee Meetings (max 3) | bar: JANUARY 4 to JUNE 25
| 17 | Briefing to Design Review Commission | bar: JANUARY 4 to JUNE 25
Trips | bar: JANUARY 4 to JUNE 25
Billing Points | bar: JANUARY 4 to JUNE 25
THREE |  | Design Development | bar: JANUARY 1 to FEBRUARY 9
June 7 through October 2003 | bar: JUNE 23 to OCTOBER 44
| 7 | Pearl District Neighborhood Association Meeting | bar: JUNE 23 to OCTOBER 44
| 8 | Review of Public Art with RACC | bar: JUNE 23 to OCTOBER 44
| 9 | City/County Advisory Committee on Disabled | bar: JUNE 23 to OCTOBER 44
| 10 | Presentation to AIA/ASLA Urban Design Committees | bar: JUNE 23 to OCTOBER 44
| 11 | Meetings & Presentations to Parks Maintenance | bar: JUNE 23 to OCTOBER 44
| 12 | Design Development Cost Estimate | bar: JUNE 23 to OCTOBER 44
| 13 | Outline Specifications | bar: JUNE 23 to OCTOBER 44
| 14 | Zoning and Permitting Analysis | bar: JUNE 23 to OCTOBER 44
| 16 | Technical Advisory Committee Meetings (max 4) | bar: JUNE 23 to OCTOBER 44
| 17 | Steering Committee Meetings (max 2) | bar: JUNE 23 to OCTOBER 44
Trips | bar: JUNE 23 to OCTOBER 44
Billing Points | bar: JUNE 23 to OCTOBER 44
|  |  | 2003 cont. | [7 empty] | 2004
|  |  | JANUARY 1: NOVEMBER; JANUARY 5: DECEMBER; FEBRUARY 9: JANUARY; APRIL 14: FEBRUARY; MAY 18: MARCH; MAY 22: APRIL; JULY 27: MAY; AUGUST 31: JUNE; AUGUST 35: JULY; OCTOBER 40: AUGUST; OCTOBER 44: SEPTEMBER; DECEMBER 49: OCTOBER | NOVEMBER
|  |  | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100
FOUR |  | Construction Documents | bar: NOVEMBER 45 to JANUARY 53
November 2003 through March 2004 | bar: NOVEMBER 45 to FEBRUARY 61
| 1 | 75% Document Submittal | bar: NOVEMBER 45 to FEBRUARY 61
Owner Review Period | bar: NOVEMBER 45 to FEBRUARY 61
| 13 | 95% Document Submittal | bar: NOVEMBER 45 to FEBRUARY 61
| 23 | 95% Cost Estimate | bar: NOVEMBER 45 to FEBRUARY 61
Owner Review Period | bar: NOVEMBER 45 to FEBRUARY 61
| 25 | 100% Document Submittal | bar: NOVEMBER 45 to FEBRUARY 61
| 38 | Separation of Permit Packages | bar: NOVEMBER 45 to FEBRUARY 61; MARCH 65
| 44 | Technical Advisory Committee Meetings (max 4) | bar: NOVEMBER 45 to FEBRUARY 61
| 45 | Steering Committee Meetings (max 2) | bar: NOVEMBER 45 to FEBRUARY 61
Trips | bar: NOVEMBER 45 to FEBRUARY 61
Billing Points | bar: NOVEMBER 45 to FEBRUARY 61; MARCH 65
FIVE |  | Bid and Construction Administration | bar: DECEMBER 49 to JANUARY 57
April 2004 through November 2004 | bar: APRIL 66 to NOVEMBER 100
Contractor Selection (RFQ) | bar: MARCH 62 to NOVEMBER 100
| 6 | Bid Review and Recommendations | bar: APRIL 66 to NOVEMBER 100
| 16 | Operations and Maintenance Manuals | bar: APRIL 66 to NOVEMBER 100
| 17 | Project Closeout | bar: APRIL 66 to NOVEMBER 100
Trips | bar: APRIL 66 to NOVEMBER 100
Billing Points | bar: APRIL 66 to NOVEMBER 100