## Sheet1
Governance Transition Timeframe (October 2023 to March 2025)
| 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-23 | 2023-12-23 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01
Change Management Deliverables & Milestones
1. Short-Term Change Management Plan (City Org Proposal) - Lead: JAMEY | 2023-08-01: Aug. 31 to Nov. 30, 2023
A: Initial City Organization proposal sent to City Council | 2023-08-01: Aug. 31
B: Final City Organization proposal submitted to City Council | 2023-10-01: Oct. 5
C: City Council approves proposal | 2023-11-23: Nov. 1
D: Employee comms support for CAO and leadership | 2023-11-23: through Nov. 30
2. Long-term Change Management Plan - Lead: JENNIFER | 2023-08-01: Aug. 31 to Mar. 1, 2025
A: Draft completed | 2023-08-01: Aug. 31
B: Feedback collected, incorporated (GTAC, leadership, leads, SMEs) | 2023-10-01: Oct. 18
C: Idenitfy and include city's People & Culture strategy and approaches | 2023-10-01: Oct. 31
D: Final plan completed | 2023-11-23: Nov. 20
E: Launch plan implementation
F: Progress check-ins / process improvements | bar: 2024-01-01; 2024-04-01; 2024-07-01; 2024-11-01
G: Transition plan for CM implementation (transfer to new department) | bar: 2024-11-01 to 2025-03-01
3. Employee-centered communications strategy - Lead: JENNIFER | 2023-09-01: Sept. 1 to Mar. 1, 2025
A: Preliminary meeting on scope; *leadership approval needed | 2023-09-01: *Sept. 30
B: Work with Comms team to develop plan | 2023-10-01: Oct. 1 to Nov. 20
C: Final plan completed | 2023-11-23: Nov. 20
D: Launch strategy
E: Progress check-ins / process improvements | bar: 2024-01-01; 2024-04-01; 2024-07-01; 2024-11-01
F: Transition plan for on-going planning and implementation (to new dept.) | bar: 2024-07-01 to 2025-03-01
4. Employee Support Advisory Committee - Lead: JENNIFER | 2023-10-01: Oct. 1 to Mar. 1, 2025
A: Develop proposal scope; *leadership approval needed | 2023-10-01: *Oct. 13
B: Release committee application opening | 2023-11-23: Nov. 9
C: Employee outreach event(s) | 2023-11-23: Nov. 20
D: Committee members selected | 2023-12-23: Dec. 15
E: Convene first meeting | 2024-01-01: Jan. 20
F: Monthly meetings | bar: 2024-02-01 to 2025-01-01
G: Transition plan for committee (sunset or transfer to new department) | bar: 2024-11-01 to 2025-03-01
5. Change Management Training - Lead: JENNIFER | 2023-10-01: Oct. 1 to Mar. 1, 2025
A: Assess and proposed CM training and support needs for different groups | 2023-11-23: Nov. 20
B: Work with NEX to develop draft scope and resources; *leadership approval needed | 2023-12-23: *Dec. 30
C: Review plan w/ employee committee | 2024-02-01: Feb. 28
C: Launch implementation | bar: 2024-03-01 to 2025-03-01
D: Progress check-ins / process improvements | bar: 2024-04-01; 2024-07-01; 2024-11-01
G: Transition plan for CM training and support (transfer to new department) | bar: 2024-11-01 to 2025-03-01
6. Change Management Employee Support - Change Ambassadors Program - Lead: JAMEY | 2023-12-23: Dec. 1, 2023 to Mar. 1, 2025
A: Develop proposal concept; *leadership approval needed | 2024-01-01: *Jan. 30
B: Review proposal w/ employee committee; revise based on edits | 2024-02-01: Feb. 28
C: Launch program (include metrics and reporting schedule) | 2024-03-01: Mar. 15
D: Implement employee support events and office-hours plan | bar: 2024-03-01 to 2025-03-01
E: Progress check-ins / process improvements | bar: 2024-07-01; 2024-11-01
F: Transition plan for ambassadors program (transfer to new department) | bar: 2024-11-01 to 2025-03-01
7. Coordinate with Implementation Leads to Align on Employee Comms and Support - Lead: JAMEY | 2023-10-01: Oct. 1 to Mar. 1, 2025
A: Contact lead staff* on implementation teams and determine best ways to stay in contact. | 2023-10-01: *Oct. 13
B: Identify decisions, processes, actions, needing CM support; align messaging. | bar: 2023-11-23 to 2025-01-01
| 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-23 | 2023-12-23 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01
Notes
Sustaining change?
Next Assessment - service area work that needs to be completed by July 2024?
*Lead staff on implementation teams:
Tate - Council Operations
Odessa - Technical Implementation
Tracy - City administrator recruitment
Contact - Budget process (CBO)
Retreat Priorities
What information do you need out of the retreat?
Team Priorities
What should the team be working on?
Note on A14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Establish success indicators and shared strategic vision?
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is where I think it could be helpful to have more detail.
Note on A27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this the coalition or is there another group - the influential individuals who have the power to lead and support the change? @Chang, Jennifer What about the role of the deputy directors, City Council and ELT through this process?
Note on A71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Duhamel, Jamey @Chang, Jennifer @Tillson, Becky