## IGA_Staffing
| DESIGN |  |  | CONSTRUCTION |  |  | CLEAN-UP / START - UP
| ( 3/1/00 to 5/1/01) |  |  | ( 5/1/01 - 9/03) |  |  | (10/03 - 9/04)
| hours | rate | total | hours | rate | total | hours | rate | total
PDOT
Core Team
Karen Rabiner | 2467 | 63.7746 | 157331.9401 | 2908 | 65.69 | 191026.52 | 0 | 67.67 | 0
Teresa Boyle (.6 3/1 - 5/1, ft after 5/1) | 2026 | 55.3339 | 112106.514 | 4960 | 56.99 | 282670.4 | 1000 | 58.7 | 58700
Todd Liles (.4 3/1 - 6/1, ft after 6/1) | 1939 | 51.4006 | 99665.8429 | 2382 | 52.94 | 126103.08 |  | 54.53 | 0
Gary Hopkins (.1 3/1 - 7/1, .6 7/1- 10/1, .2 10/1- 5/1) | 784 | 51.5 | 40376 | 4960 | 53.05 | 263128 | 520 | 54.64 | 28412.8
Dan Holly |  |  |  | 1531 | 36 | 55116
Steve Barrett (first 1860 hrs starting 12/2000 charge to Lower Albina; through 6/03) | 0 |  |  | 3530 | 58.58 | 206787.4
Core Team Subtotal | 7216 |  | 409480.297 | 20271 |  | 1124831.4 |  |  | 87112.8
Street Lighting
Lisa Elbert | 0 | 45.12 | 0 | 21 | 48 | 1008
Steve Spitulski | 223 | 48.44 | 10802.12 | 528 | 49.89 | 26341.92 | 20 | 49.89 | 997.8
Bill Graham | 0 | 48.49 | 0 | 8 | 53 | 424
Dale Kurkinden |  | 45.06 | 0 | 264 | 45.06 | 11895.84 | 24 | 45.06 | 1081.44
Street Lighting Subtotal | 223 |  | 10802.12 | 821 |  | 39669.76 | 24 |  | 2079.24
Traffic Signals
John Bustraan | 667 | 55.8526 | 37253.6984 | 1415 | 57.53 | 81404.95 | 300 | 57.53 | 17259
Bill Kloos | 24 | 65.09 | 1562.16 | 16 | 67.04 | 1072.64 | 16 | 67.04 | 1072.64
Lloyd Boucke |  | 41.97 | 0 | 942 | 44 | 41448 | 24 | 44 | 1056
Paul Zebell |  |  |  | 357 | 46 | 16422 | 120 | 46 | 5520
Others | 6 | 41.97 | 251.82 | 48 | 50 | 2400
Traffic Signal Subtotal | 697 |  | 39067.6784 | 2778 |  | 142747.59 | 460 |  | 24907.64
Traffic Design Section
Rob Burchfield | 0 | 62.67 | 0 | 16 | 62.67 | 1002.72
Lewis Wardrip | 941 | 53.1321 | 49997.3354 | 2270 | 54.73 | 124237.1 | 200 | 54.73 | 10946
Mike Coleman | 271 | 55.5678 | 15058.8678 | 243 | 57.23 | 13906.89 | 50 | 57.23 | 2861.5
Others | 7 | 47.7457 |  | 11 | 49.18
Traffic Design Subtotal | 1219 |  | 65056.2032 | 2540 |  | 139146.71 | 250 |  | 13807.5
Traffic Operations
Data Collection | 319 | 48 | 15312 |  |  | 16500
Scott Batson | 55 | 48.01 | 2640.55 | 40 | 49.45 | 1978
Rob Burchfield | 8 | 62.67 | 501.36 | 12 | 62.67 | 752.04
Traffic Operations Subtotal | 63 |  | 18453.91 | 52 |  | 19230.04
Parking
Parking Enforcement | [5 empty] | 15000
Parking Signage | [5 empty] | 26012.5
Parking Subtotal | [5 empty] | 41012.5
Transportation Planning
Modal Specialists
Roger Geller | 45 | 45.1867 | 2033.4 | 60 | 46.54 | 2792.4
Courtney Duke | 0 | 39.71 | 0 | 60 | 39.71 | 2382.6
Modal Specialist Subtotal | 45 |  | 2033.4 | 120 |  | 5175
Transit/Rail
Steve Iwata | 137 | 56.815 | 7783.655 | 178 | 57 | 10146
Teresa Bliven | 525 | 23.51 | 12342.75 |  |  | 0
Lore Wintergreen | 348 | 24.97 | 8689.56 | 124 | 37 | 4588
Art Pearce | 89 | 24.51 | 2181.39 | 185 | 31 | 5735
Phillip Harris | 89 | 24.51 | 2181.39 | 247 | 23 | 5681
Transit/Rail Subtotal | 1188 |  | 33178.745 | 734 |  | 26150
Transportaion Planning Subtotal |  |  | 35212.145 |  |  | 31325
Structures
Calvin Lee | 145 | 48.1837 | 6986.6342 | 103 | 49.63 | 5111.89
Man-Chi Lai | 203 | 39.06 | 7929.18 | 0 | 40.23 | 0
Others | 11 | 49.31 | 542.41 | 27 | 50.79 | 1371.33
Structures Subtotal | 359 |  | 15458.2242 | 130 |  | 6483.22
Others
Total | 76 |  |  | 100 |  | 5000
Materials & Services
Fleet | [5 empty] | 25000
Misc. M&S |  |  | 3440 |  |  | 20000 |  |  | 5000
Smithson Fiber Optic Extension | [5 empty] | 5300
Smithson Building Permits | [5 empty] | 11801.9
Pothole by BOM Interstate & Greeley | [5 empty] | 7000
Temporary Street Lights | [5 empty] | 90000
BOM Electric | [5 empty] | 296595
Project Support |  |  |  | 89277 |  |  |  |  | 8600
Contractor Assisstance |  |  |  | 101821
Materials |  |  |  | 65798
Pole Transfers |  |  |  | 13187
Interstate/Multnomah |  |  |  | 20189
Trouble Call Contractor |  |  |  | 6323
M&S Total |  |  | 3440 |  |  | 455696.9 |  |  | 13600
PDOT SUBTOTAL |  |  | 596970.5779 |  |  | 2000143.12 |  |  | 141507.18
| FY99/00 | FY02/03
PDOT Downtown Overhead Rate | 17.7% | 13.32%
BOM Admin Rate | 12.18% | 14.17%
General Fund Overhead Recovery | 3.1% | 2.52%
PDOT IT Overhead | 3.4% | 4.39%
Office of Transportation Admin & Support OH | 1.5% | 2.58%
Overhead Rate for PDOT (except BOM) | 25.7% | 22.81% | 153421.4385 |  |  | 497664.7378 |  |  | 36367.3453
Overhead Rate for BOM | 20.18% | 23.66%
PDOT SUBTOTALS PER YEAR |  |  | 750392.0164 |  |  | 2497807.8578 |  |  | 177874.5253
PDOT TOTAL |  | 3426074.3995
Right-of Way
| hours | rate | total
45 parcels @ $1000 per parcel | 1240 | 36.37 | 45098.8
Supervision |  |  | 5000
Right-of-Way Subtotal |  |  | 50098.8
Total Overhead Rate for PDOT | 25.7% |  | 12875.3916
Right-of-Way TOTAL |  | 62974.1916
BES
| Hrs | Rate | Total
Engineering / Project Management | 600 | 43.01 | 25806
Construction Management | 2080 | 38 | 79040
Technical Support | 900 | 34 | 30600
Inspection | 7573 | 47.05 | 356309.65
BES Subtotal |  |  | 491755.65
Overhead: (10%) |  |  | 49175.565
BES Total |  | 540932
PARKS
| Hrs | Rate | Total
Plan Review | 150 | 61.77 | 9265.5
PIR Mtgs & Plan Review | 80 | 61.77 | 4941.6
Plan Review Hort & Forestry |  |  | 5000
Parks Total |  | 19207.1 | 19207.1