| CITY OF PORTLAND | CHANGE ORDER |
| --- | --- |

EXHIBIT A

| PROJECT: Child Development Center | CHANGE ORDER NUMBER: 2 |
| --- | --- |
|  | PROJECT NUMBER: 9036 |
|  | CONTRACT DATE: May 22, 2000 |
|  | CONTRACT NO: 32960 |
|  | DATE OF THIS CHANGE ORDER: 11/29/01 |

The Contract is changed as follows:

Item No.	Description of Item:					Add/Delete Amount:

01	Change in front door, sign in area	8,735.00

- Change exit door out of infant

area per Fire Marshal request	990.00

- Electrical additions & changes

including light fixtures	10,980.00

04	Misc. additions	5,620.00

- Tack board adds

- Bathroom accessory adds

- Extra Bond & Insurnace

- Appliance up-charge for delivery

05	HVAC Modifications	15,560.00

06	Outdoor play area changes	25,197.00

07	Credit-Shear wall in stairway	(3,820.00)

08	Credit-Delete basement insulation	(11,250.00)

Total Adds/Deletes	$51,552.00

Not valid until signed by the Owner. Signature of the Contractor indicates agreement herewith, including any adjustment in the contract sum or contract time.

| The original Contract Sum was……………………………………………………………………………….. | 510,214.00 |
| --- | --- |
| Net Change by previously authorized Change Orders…………………………………………………….. | 125,154.00 |
| The Contract Sum prior to this Change Order was…………………………………………………………. | 635,368.00 |
| The Contract sum will be increased by this Change Order in the amount of……………………………. | 51,552.00 |
| The new Contract Sum including this Change Order will be……………………………………………. | $ 686,920.00 |
| The new Contract Time will be increased by………………………………………………………..(289) | calendar days |
| The Date of Substantial Completion as of the date of this Change Order therefore is………………… | 08/01/01 |

|  | Contractor JVC Contractors, Inc. | Owner City of Portland Bureau of General Services |
| --- | --- | --- |
|  | Address 4916 NE 100th Portland, OR 97220 | Address 1120 S.W. 5th Avenue, #1204 Portland, OR 97204 |
|  | By: | By: |
|  | Date: | Date: |