## Sheet1
The following schedule demonstrates the major work tasks and major milestones for this project and will be the basis for the development of the detailed project plan during the project’s Initiation Phase.
Work Plan Description | Start | Finish
Cayenta Utilities Implementation | 2004-02-02 | 2006-06-02 17:00
Phase 1 - Project Initiation | 2004-02-02 | 2004-03-18 17:00
Milestone - Software Review Checklist Signed Off |  | 2004-02-05
Phase 2 – Fit Analysis and Configuration | 2004-03-08 08:00 | 2004-06-25 17:00
Milestone - Delivery of Discovery Document |  | 2004-04-16
Milestone - Configuration Signed Off |  | 2004-07-13
Phase 3 - Deployment | 2004-01-01 08:00 | 2004-12-01 17:00
Milestone - Reports Review Analysis & Sign Off |  | 2004-08-18
Phase 4 - Functional Testing | 2004-06-15 17:00 | 2004-12-07 17:00
Milestone - End User Training Plan Delivered |  | 2004-09-07
Milestone - System Administration Training Delivered |  | 2004-11-26
Phase 5 - Integrated Testing | 2004-12-08 08:00 | 2005-07-28 17:00
Milestone - Intergrated Test Plan Signed Off |  | 2005-01-10
Milestone - Operations Training Delivered |  | 2005-03-21
Milestone - Batch Process Integration Testing Completed |  | 2005-06-13
Milestone - Initial Mock Production Milestone Completed |  | 2005-07-05
Milestone - Integrated Testing - Functional Business Area Signed Off |  | 2005-08-01
Phase 6 - City Acceptance Testing | 2005-07-22 08:00 | 2005-09-15 17:00
Milestone - City Acceptance/Non-Acceptance |  | 2005-10-13
Phase 7 - Production Readiness Evaluation & Cutover | 2005-08-12 08:00 | 2005-11-17 17:00
Milestone - Live Operation |  | 2005-12-15
Phase 8 – Post Implementation Support | 2005-11-18 08:00 | 2006-05-02 17:00
Milestone - Cutover to Standard Support |  | 2006-01-26
Milestone - On-site Transition Support Second Level (90 days) |  | 2006-03-30
Milestone - On-site Transition Support Close Off (180 days) |  | 2006-06-02
Phase 9 -Data Conversion | 2004-03-22 08:00 | 2006-01-11 17:00
Milestone - Conversion Plan Finalized |  | 2004-06-24
Milestone - Data Conversion Mock Production Audit #4 Delivered |  | 2005-11-10
Cycle Simulation Test Planning | 2005-08-26 | 2005-11-02