## Bid Items - Track and Civil
ITEM | No. | ITEMS OF WORK AND MATERIALS | TOTAL QUANT | UNIT | UNIT PRICE | TOTAL PRICE
Schedule F - Gibbs Streetcar Extension
1 | RFP102328 | Preconstruction Services | 1 | LS | 5000 | 5000
2 | Appendix A | M/W/ESB Coordinator | 1 | LS | 15000 | 15000
3 | 00206 | Field Engineering | 1 | LS | 45000 | 45000
4 | 00207 | Quality Control | 1 | LS | 60000 | 60000
5 | 00208 | Hazardous Material Health and Safety Plan and Report | 1 | LS | 3985 | 3985
6 | 00208 | Hazardous Material Disposal | 1 | PS | 85000 | 85000
7 | 00210 | Mobilization | 1 | LS | 344028 | 344028
8 | 00225 | Work Zone Traffic Control | 1 | LS | 100000 | 100000
9 | 00280 | Erosion Control | 1 | LS | 20000 | 20000
10 | 00310 | Remove Existing Railroad Tracks | 1590 | TM(F) | 45 | 71550
11 | 00310 | Dispose of Existing Timber Ties | 1 | PS | 15000 | 15000
12 | 00310 | Removal of AC and Concrete Surfacings (100mm thick) | 186 | M3(F) | 200 | 37200
13 | 00320 | Clearing and Grubbing | 1 | LS | 25000 | 25000
14 | 00330 | Roadway Excavation (reconstruction) | 80 | M3 | 65 | 5200
15 | 00330 | Track Slab Excavation | 108 | M3(F) | 63 | 6804
16 | 00330 | Track Aggregate Base Excavation | 54 | M3 | 75 | 4050
17 | 00330 | Ballasted Trackbed Excavation | 2000 | M3(F) | 38 | 76000
18 | 00330 | Ballasted Trackbed Embankment | 1400 | M3(F) | 25 | 35000
19 | 00445 | 200mm SDR 35 PVC Track Drain Leads | 15 | M | 270 | 4050
20 | 00490 | Minor Adjustment of Manholes | 1 | EA | 500 | 500
21 | 00490 | Adjusting Water Valves | 13 | EA | 250 | 3250
22 | 00495 | Sewer Trench Resurfacing - Asphalt Concrete | 6 | M2 | 95 | 570
23 | 00620 | Cold Plane Pavement Removal | 700 | M2 | 15 | 10500
24 | 00641 | Subgrade Stabilization, Trackway, Roadway | 100 | M3 | 55 | 5500
25 | 00641 | Geotextile Fabric | 300 | M2 | 3.75 | 1125
26 | 00641 | Subballast Placement | 580 | M3(F) | 37 | 21460
27 | 00641 | Subballast (Imported Material) | 1100 | Mg | 17 | 18700
28 | 00641 | Trackway Aggregate Base | 54 | M3 | 85 | 4590
29 | 00641 | Aggregate Base for Roadway Construction | 50 | M3 | 140 | 7000
30 | 00744 | Asphalt Concrete Pavement | 220 | Mg | 116 | 25520
31 | 00757 | OCS Pole Foundations F1/FF1 | 32 | EA | 2500 | 80000
32 | 00757 | OCS Pole Foundations F2/FF2 | 3 | EA | 3500 | 10500
33 | 00759 | Curb Cut Spillway | 13 | EA | 700 | 9100
34 | 00759 | Concrete Curbs (outside of stops) | 297 | M | 92 | 27324
35 | 00759 | Track-side Curbs | 93 | M | 140 | 13020
36 | 00759 | Concrete Walks (outside of stops) | 53 | M2 | 62 | 3286
37 | 00759 | Truncated Dome Detectable Warning | 6 | M2 | 300 | 1800
38 | 00759 | Ballast Wall | 95 | M (F) | 180 | 17100
39 | 00762 | Stop Platform (Gibbs) | 1 | LS | 75000 | 75000
40 | 00861 | Permanent Pavement Marking & Striping | 1 | LS | 15000 | 15000
41 | 00905 | Signage | 1 | LS | 2700 | 2700
42 | 00990 | Traffic Signals, Complete (Sheridan & Moody) | 1 | LS | 68600 | 68600
43 | 01040 | Landscaping | 1 | LS | 26857 | 26857
44 | 01120 | Irrigation System Water Service | 1 | LS | 6350 | 6350
45 | 01120 | Irrigation system | 1 | LS | 6043 | 6043
46 | 01210 | Install Ri52 Paved Track - Tangent | 94 | TM(F) | 793 | 74542
47 | 01210 | Install Ri52 Paved Track - Curved | 50 | TM(F) | 880 | 44000
48 | 01210 | Furnish and Install Track Drain - Ri52 | 1 | EA | 2200 | 2200
49 | 01210 | Install Ri59 to Ri52 Transition Rails | 1 | PAIR | 5500 | 5500
50 | 1260 | 115RE Insulated Rail Joints | 3 | EA | 1500 | 4500
51 | 1260 | Furnish Concrete Ties | 910 | EA(F) | 90 | 81900
52 | 1260 | Furnish 115RE CWR | 1390 | M(F) | 115 | 159850
53 | 1260 | Construct Ballasted Track | 654 | TM(F) | 325 | 212550
54 | 1260 | Install Transition Slab to Embedded Track | 1 | EA | 3000 | 3000
55 | 1260 | Install Road Crossing Rubber Rail Interface | 20 | TM | 460 | 9200
56 | 1260 | Furnish and Install Wheel Stops | 2 | PAIR | 600 | 1200
57 | 1270 | Furnish Refurbished #5 Turnout | 1 | EA | 23000 | 23000
58 | 1270 | Furnish Powered Switch Mechanism | 1 | EA | 25000 | 25000
59 | 1270 | Install #5 Turnout Incl. Ties and Switch Mechanism | 1 | EA | 62000 | 62000
60 | 1280 | Pre-Bend Tangent Rail (Ri52 and 115RE) | 1 | LS | 20000 | 20000
61 | 1310 | Switch/Rail Bonding | 1 | LS | 7500 | 7500
62 | 01330 | Ductbank | 1 | LS | 121979 | 121979
63 | 01340 | SC Manholes | 1 | LS | 37000 | 37000
64 | 01366 | Moody Train Signal System | 1 | LS | 559509 | 559509
65 | 1390 | Track Electrical Testing | 1 | LS | 12571 | 12571
66 | 16120 | Furnish and Install 2kV Feeder Cable, Splices, Termination's, and Supports | 1 | LS | 26745 | 26745
67 | 16400 | Furnish Taper Tubular Pole PS1, PH1, PF1 | 24 | EA | 2179 | 52296
68 | 16400 | Furnish Taper Tubular Pole PS3, PH3, PF3 | 6 | EA | 3383 | 20298
69 | 16400 | Furnish Taper Tubular Pole PS6, PH6, PF6 | 2 | EA | 3014 | 6028
70 | 16400 | Furnish Taper Tubular Pole PS9, PH9, PF9 | 3 | EA | 4149 | 12447
71 | 16400 | Installation and Grounding of Taper Tubular Poles | 35 | EA | 959 | 33565
72 | 16400 | Furnish and Install Cantilever Assembly | 35 | EA | 3145 | 110075
73 | 16400 | Furnish and Install Single Track Cross Span Assembly CS1, CS1A | 1 | EA | 10502 | 10502
74 | 16400 | Furnish and Install Single Track Pull Off Assembly PO1 | 1 | EA | 6640 | 6640
75 | 16400 | Furnish and Install Single Track Backbone Assembly BB1 | 1 | EA | 8660 | 8660
76 | 16400 | Furnish and Install Fixed Termination Assembly FT | 2 | EA | 3472 | 6944
77 | 16400 | Furnish and Install Single Disconnect Switch Assembly DS1 | 1 | EA | 8857 | 8857
78 | 16400 | Furnish and Install Fixed Tension Single Contact System | 902 | TM(F) | 43 | 38786
79 | 16950 | Subsation Field Acceptance Testing | 1 | LS | 4399 | 4399
80 | 16950 | OCS Field Acceptance Testing | 1 | LS | 23243 | 23243
81 | 16950 | Integrated System Testing | 1 | LS | 12283 | 12283
82 | 16950 | Documentation Drawings and Manuals | 1 | LS | 5943 | 5943
|  |  |  | Total Schedule F |  | 3273974
|  |  |  | CM/GC FEE (3.5%) |  | 114589.09
|  |  |  | TOTAL CONSTRUCTION COST |  | 3388563.09