## Updated Budget
Attachment "C"
| City of Portland |  |  | Principal 2005 base rate: $62.50
| Payment Schedule for Woods Street Trunk Sewer Emergency Repair Project |  |  | Senior Engineer 2005 base rate: $37.16
| Proposal for Consulting Services 11/10/05 |  |  | Project Engineer 2005 base rate: $32.21
| Phase 2 Work |  |  | Administrative Personnel 2005 base rate: $18.75
| Bennett / Staheli Engineers |  |  | Labor Multiplier : 3.01015
Phase 2: Rehabilitation/New Installation of I5 Section and upstream to Manhole ABY728
Task 1 | Project Management and Meetings |  | Principal @ $188.13/hour | Senior Engineer @ $111.87/hour | Project Engineer @ $96.96/hour | Administrative @ $56.44/hour |  | Sub Total
|  | Participate in Microtunnel Design Meetings/Presentations (2 in total) | 10 | 16 |  |  |  | 3671.22
|  | Participate in BES Meetings (3 in total) |  | 24 |  |  |  | 2684.88
|  | Microtunnel pre-construction meeting |  | 4 |  |  |  | 447.48
|  | Microtunnel pre-construction workshop | 10 | 10 |  |  |  | 3000
|  | Progress Report | 8 | 24 |  | 8 |  | 4641.44
|  | Additional Project Management to Accommodate City Schedule | 8 | 24 |  | 8 |  | 4641.44
[7 empty] | Engineering Design Total | 19086.46
[7 empty] | Other Direct Costs (Estimated at 6%) | 1145.1876
[7 empty] | Travel (7 round trips for meetings/workshop) | 2100
[7 empty] | Phase Two Total | 22331.6476
Task 2 | Geotechnical Baseline Report |  | Principal @ $188.13/hour | Senior Engineer @ $111.87/hour | Project Engineer @ $96.96/hour | Administrative @ $56.44/hour |  | Sub Total
|  | Assist in Developing Additional Geotechnical Exploration Plan |  | 4 |  |  |  | 447.48
|  | Review Geotechnical Information (GDR/GIR) | 4 | 8 | 4 |  |  | 2035.32
|  | Prepare Geotechnical Baseline Report | 32 | 56 | 40 | 16 |  | 17066.32
|  | Finalize Geotechnical Baseline Report during 90% | 12 | 20 |  |  |  | 4494.96
[7 empty] | Engineering Design Total | 24044.08
[7 empty] | Other Direct Costs (Estimated at 6%) | 1442.6448
[7 empty] | Travel | 0
[7 empty] | Phase Two Total | 25486.7248
Task 3 | 30% Engineering Design Services |  | Principal @ $188.13/hour | Senior Engineer @ $111.87/hour | Project Engineer @ $96.96/hour | Administrative @ $56.44/hour |  | Sub Total
|  | Review Plan and Profiles | 2 | 6 |  |  |  | 1047.48
|  | Update Cost Estimate for Trenchless Components | 2 | 8 |  |  |  | 1271.22
[7 empty] | 30% Engineering Design Total | 2318.7
[7 empty] | Other Direct Costs (Estimated at 6%) | 139.122
[7 empty] | Travel | 0
[7 empty] | Phase Two Total | 2457.822
Task 4 | 60% Engineering Design Services |  | Principal @ $188.13/hour | Senior Engineer @ $111.87/hour | Project Engineer @ $96.96/hour | Administrative @ $56.44/hour |  | Sub Total
|  | Update Plan and Profiles and Develop Shaft Details | 8 | 16 |  |  |  | 3294.96
|  | CADD Drafting of Microtunneling Design Details |  | 12 | 96 |  |  | 10650.6
|  | Establish Staging Area Requirements | 2 | 6 |  |  |  | 1047.48
|  | Update Cost Estimate for Trenchless Components | 2 | 4 |  |  |  | 823.74
|  | Perform Design Calculations (jacking force/lateral earth pressure/settlements/thrust block) | 16 | 32 |  |  |  | 6589.92
|  | Provide Permitting Support | 4 | 8 |  |  |  | 1647.48
|  | Review Microtunnel Specification | 2 | 8 |  |  |  | 1271.22
|  | Review Jacking Pipe Specification | 2 | 8 |  |  |  | 1271.22
|  | Review Carrier Pipe Specification | 2 | 8 |  |  |  | 1271.22
|  | Review Excavation Support Systems Specification | 2 | 8 |  |  |  | 1271.22
|  | Review/Develop Settlement Monitoring Plan | 6 | 12 |  |  |  | 2471.22
|  | Review Construction Schedule | 2 | 4 |  |  |  | 823.74
[7 empty] | 60% Engineering Design Total | 32434.02
[7 empty] | Other Direct Costs (Estimated at 6%) | 1946.0412
Travel
[7 empty] | Phase Two Total | 34380.0612
Task 5 | 90% Engineering Design Services |  | Principal @ $188.13/hour | Senior Engineer @ $111.87/hour | Project Engineer @ $96.96/hour | Administrative @ $56.44/hour |  | Sub Total
|  | Update Plan and Profiles and Shaft Details | 2 | 6 |  |  |  | 1047.48
|  | Update Design Calculations (jacking force/lateral earth pressure/settlements/thrust block) | 4 | 12 |  |  |  | 2094.96
|  | Update Microtunnel Specification | 1 | 4 |  |  |  | 635.61
|  | Update Jacking Pipe Specification | 1 | 4 |  |  |  | 635.61
|  | Update Carrier Pipe Specification | 1 | 4 |  |  |  | 635.61
|  | Update Excavation Support Systems Specification | 1 | 4 |  |  |  | 635.61
|  | Update Construction Schedule |  | 2 |  |  |  | 223.74
[7 empty] | 90% Engineering Design Total | 5908.62
[7 empty] | Other Direct Costs (Estimated at 6%) | 354.5172
Travel
[7 empty] | Phase Two Total | 6263.1372
Task 6 | Final Engineering Design Services |  | Principal @ $188.13/hour | Senior Engineer @ $111.87/hour | Project Engineer @ $96.96/hour | Administrative @ $56.44/hour |  | Sub Total
|  | Update Plan and Profiles and Shaft Details |  | 4 |  |  |  | 447.48
|  | Update Cost Estimate for Trenchless Components |  | 4 |  |  |  | 447.48
|  | Update Microtunnel Specification | 2 | 4 |  |  |  | 823.74
|  | Update Jacking Pipe Specification | 2 | 4 |  |  |  | 823.74
|  | Update Carrier Pipe Specification |  | 4 |  |  |  | 447.48
|  | Update Excavation Support Systems Specification |  | 4 |  |  |  | 447.48
[7 empty] | Final Engineering Design Total | 3437.4
[7 empty] | Other Direct Costs (Estimated at 6%) | 206.244
Travel
[7 empty] | Phase Two Total | 3643.644
Task 7 | Bid Services |  | Principal @ $188.13/hour | Senior Engineer @ $111.87/hour | Project Engineer @ $96.96/hour | Administrative @ $56.44/hour |  | Sub Total
|  | Prepare Contractor Prequalification Packages | 8 | 12 |  |  |  | 2847.48
|  | Review Contractor Prequalification Packages | 2 | 8 |  |  |  | 1271.22
|  | Advise on Prequalification of Contractors | 2 | 4 |  |  |  | 823.74
|  | Attend Pre-bid Meeting |  | 8 |  |  |  | 894.96
|  | Respond to RFI's | 2 | 6 |  |  |  | 1047.48
|  | Prepare Addenda | 2 | 6 |  |  |  | 1047.48
|  | Evaluate Bidder Qualifications | 8 | 8 |  |  |  | 2400
|  | Advise on Selection/Award | 2 | 6 |  |  |  | 1047.48
|  | Attend Bid Opening |  | 8 |  |  |  | 894.96
[7 empty] | Engineering Total | 12274.8
[7 empty] | Other Direct Costs (Estimated at 6%) | 736.488
[7 empty] | Travel (2 roundtrips for bid meetings) | 600
[7 empty] | Phase Two Total | 13611.288
Task 8 | Construction Services |  | Principal @ $188.13/hour | Senior Engineer @ $111.87/hour | Project Engineer @ $96.96/hour | Administrative @ $56.44/hour |  | Sub Total
|  | Evaluate Microtunnel Submittals | 8 | 16 |  |  |  | 3294.96
|  | Respond to RFI's | 4 | 6 |  |  |  | 1423.74
|  | Office Support during Construction | 12 | 32 |  |  |  | 5837.4
|  | Inspector Training (if required) |  | 16 |  |  |  | 1789.92
[7 empty] | Engineering Total | 12346.02
[7 empty] | Other Direct Costs (Estimated at 6%) | 740.7612
Travel
[7 empty] | Phase Two Total | 13086.7812
Task 9 | Optional Construction Services |  | Principal @ $188.13/hour | Senior Engineer @ $111.87/hour | Project Engineer @ $96.96/hour | Administrative @ $56.44/hour |  | Sub Total
Resident Engineer
Interstate-5 Drive
|  | Microtunnel Setup (2 days) |  | 20 |  |  |  | 2237.4
|  | Microtunneling (1,000ft / 35ft per day = 29 days) 8 days each push plus 1 day per week for balance of tunneling duration |  | 100 |  |  |  | 11187
|  | Microtunneling Retrieval |  | 10 |  |  |  | 1118.7
|  | Contingency (1 day) |  | 10 |  |  |  | 1118.7
Naitos Parkway Drive
|  | Microtunnel Setup (2 days) |  | 20 |  |  |  | 2237.4
|  | Microtunneling (1,000ft / 35ft per day = 29 days) 8 days each push plus 1 day per week for balance of tunneling duration |  | 130 |  |  |  | 14543.1
|  | Microtunneling Retrieval |  | 10 |  |  |  | 1118.7
|  | Contingency (1 day) |  | 10 |  |  |  | 1118.7
[7 empty] | Engineering Total | 34679.7
[7 empty] | Other Direct Costs (Estimated at 6%) | 2080.782
[7 empty] | Travel (meals, food, lodging, travel) | 5850
[7 empty] | Phase Two Total | 42610.482
[7 empty] | Overall Project Total | 163871.588