Exhibit A

| ## Project Estimate Confidence Level Rating Index Defined |  |
| --- | --- |
| #### COMPLETE | - Final payment made. - Post project assessment completed comparing project estimate, amount of contract award and total amount of change orders issued during project. - Total project costs reported. |
| #### OPTIMAL | - Project scope and specifications clearly understood and well defined. - Clear understanding of materials, size and quantities needed to execute job. - Schedule and special site conditions understood. - Project estimate unlikely to change (generally at 90% or greater design and engineering phase). - Total Project contingencies (including project management, design, engineering, plus construction) range between 10%-15%. |
| ### HIGH | - Project scope and specifications nearly complete but still subject to change (70%–90% design and engineering phase) - Materials, size and quantities needed to execute job have been defined but subject to minor changes. - Schedule understood. - Total Project contingencies (including project management, design, engineering, plus construction) may range between 20%-30%. |
| MODERATE | - Project scope defined but lacks details. - Project specifications incomplete (60%-70% design and engineering phase). - Total Project contingencies (including project management, design, engineering, plus construction) may range between 30%-40%. |
| ### LOW | - Project scope is a conceptual “vision” with limited detail. - Project cost is an educated guesstimate. Limited technical information available and/or limited analysis performed. - Specifications still in infancy stage. (Less than 50% design and engineering phase). - Total Project contingencies (including project management, design, engineering, plus construction) may range up to or exceed 50%. |