## BarGraph
Riverfest Timeline
Event / Name | Start | Due | Length | Point person | Notes
finalize event plan (define RF vs. Community) | 2008-02-04 | 2008-02-21 | 17
secure event leads (RF Events) | 2008-02-04 | 2008-02-21 | 17
process/deadline for community event inclusion | 2008-02-04 | 2008-03-01 | 26
fundraising plan/strategy | 2008-02-04 | 2008-03-01 | 26
logo review & finalize | 2008-02-04 | 2008-03-01 | 26
fundraising brochure/powerpoint/talking points | 2008-02-04 | 2008-03-15 | 40
initial plans back from RF event leads (parade, education, paddle etc.) | 2008-02-04 | 2008-03-30 | 55
sponsors/funders confirmed | 2008-02-04 | 2008-04-15 | 71
Speakers Confirmed | 2008-02-04 | 2008-05-01 | 87
Headliner Band Confirmed | 2008-02-04 | 2008-05-01 | 87
final plans back from RF event leads (parade, education, paddle etc.) | 2008-02-04 | 2008-05-01 | 87
graphic designer hired | 2008-03-01 | 2008-03-15 | 14
graphic/collateral plan (web, poster, ad, postcard etc.) | 2008-03-01 | 2008-03-30 | 29
Permit Research & Schedule | 2008-03-01 | 2008-04-01 | 31
finalize venue logistics (staging, rough layout etc.) | 2008-03-01 | 2008-04-15 | 45
info/logos/event descriptions back from community events | 2008-03-01 | 2008-05-01 | 61
Community Fair plan & recruitment | 2008-03-01 | 2008-05-01 | 61
Rental Orders Confirmed | 2008-03-01 | 2008-06-01 | 92
Additional Entertainment Confirmed | 2008-03-01 | 2008-06-01 | 92
outreach to schools re: fieldtrips | 2008-03-15 | 2008-04-01 | 17
Volunteer coordination plan & contract | 2008-04-01 | 2008-05-01 | 30
event layout finalized | 2008-04-01 | 2008-05-01 | 30
event greening plan & contract | 2008-04-01 | 2008-06-01 | 61
sponsor/funder/partner logos to graphic designer | 2008-04-15 | 2008-05-01 | 16
Volunteer plan finalized | 2008-05-01 | 2008-06-01 | 31
graphic/collateral review & finalize | 2008-05-01 | 2008-06-01 | 31
day-of needs for all RF events | 2008-05-01 | 2008-06-01 | 31
security plan & contract | 2008-05-01 | 2008-06-01 | 31
Water safety plan | 2008-05-01 | 2008-06-01 | 31
Community Fair partners committed | 2008-05-01 | 2008-06-01 | 31
Commnity Fair layout & rental needs confirmed | 2008-05-01 | 2008-06-01 | 31
PR plan & contract | 2008-05-15 | 2008-06-01 | 17
collateral to/back from printer | 2008-06-01 | 2008-06-15 | 14
day-of staffing & logistics plan | 2008-06-01 | 2008-07-01 | 30
video/documentation plan & contract | 2008-06-01 | 2008-07-01 | 30
collateral distributed | 2008-06-15 | 2008-07-01 | 16
av needs from speakers/bands | 2008-07-15 | 2008-07-16 | 1
Rental Orders Reconfirmed | 2008-08-01 | 2008-08-01 | 0
Permits submitted and finalized | 2008-08-01 | 2008-08-15 | 14
Oregon Symphony Event | 2008-08-28 | 2008-08-28 | 0
Portland Triathlon & Riverfest Celebration (community fair, parade, water tours, entertainment etc.) | 2008-08-31 | 2008-08-31 | 0
Riverfest Fieldtrips | 2008-09-05 | 2008-09-05 | 0
Portland Paddle | 2008-09-06 | 2008-09-06 | 0
Dragonboat Races | 2008-09-05 | 2008-09-06 | 1
Color code:
event planning/partnership mgt
fundraising
promotion/pr
entertainment/speakers
logistics/venue