# Saint Andrews Condominiums

January 7, 2008

Estimated Project Hours

Design /  Permitting = 28 weeks total

Schematic Design = 5 weeks

- Preliminary design completion                                          = 30 hours

- Preliminary documentation completion                             = 80 hours

- (E) conditions                                                                    = 20 hours

- Project Coordination – 6 hrs x 4 weeks                            = 24 hours

- Design Administration – 4hrs x 4 weeks                          = 16 hours

- Research/ Specifications – 4hrs x 4 weeks                     = 16 hours

Total   = 186 hours

Design Development/ Construction Documents = 18 weeks total

- DD/CD design and Documentation - 25 hrs x 18 weeks   = 450 hours

- Project Coordination – 6 hrs x 18 weeks                           = 108 hours

- Design Administration – 4hrs x 18 weeks                           = 72 hours

- Research/ Specifications – 4hrs x 18 weeks                       = 72 hours

- Misc.                                – 1 hr x 18 weeks                        = 18 hours

Total   = 720 hours

Specifications/ Permitting = 6 weeks total

- Research/ Specifications – 30 hrs x 4 weeks                 = 120 hours

- Permitting/ City coordination – 30 hrs x 2 weeks             =  60 hours

- Design Administration – 4hrs x 6 weeks                           = 24 hours

- Research/ Specifications – 4hrs x 6 weeks                       = 24 hours

Total   = 228 hours

Total Design / Permitting Hours =                             1,134 hours x $60.00 =  $68,040

Design Contingency =                                                   100 hours x $60.00 =    $6,000

Profit =                                                                            $68,040 x 10%         =    $6,800

Construction Administration

- CA – 16 hrs x 47 weeks                                   =   750 hours x $60.00 = $45,000

- CA Contingency                                               =    80 hours  x $60.00 =   $4,800

- Profit =                                                                         $45,000 x 10%  =  $4,500

Total                                                                                                                   = $135,140