## Sheet1
May-June
Excavate
Pour foundation
Build CMU walls @ stair tower
July
Frame new addition
Install windows @ addition
Install new roof
Remodel master bedroom
Install steel for deck
August
New exterior stucco
Install new windows in existing home
Plumbing rough-in
Remodel master bath
Electrical rough-in
HVAC rough-in
Paint exterior of house
Install drywall
Install patios/decks
Install patios/decks handrails
Install tile on patios/decks
September
Finish drywall
Paint interior of addition
Break-through into existing kitchen
Demo kitchen
Install new wood floor on main floor
Install carpet in basement and bonus room
Install new kitchen cabinets
October
Electrical finish
Plumbing finish
HVAC finish